## Pivot
Row Labels | Sum of W.F (%)
C | 54.9432
B | 13.316
D | 41.6272
E | 21.1684
B | 2.3652
D | 18.8032
M | 22.4693
B | 2.4834
D | 19.9858
P | 1.4191
B | 1.4191
Grand Total | 100

## MDR
Main Document Registry
Phase | Department | 1 | 2 | Document Title | Document No. | POI | Rev. | Transmittal No. | Date | Comment No. | Comment Date | CM | W.F (%) | Progress | Rev. 01 | POI | Rev. | Transmittal No. | Date | Comment No. | Comment Date | CM | Rev. 02 | POI | Rev. | Transmittal No. | Date | Comment No. | Comment Date | CM | Rev. 01 | POI | Rev. | Transmittal No. | Date | Comment No. | Comment Date | CM | Rev. 02 | POI | Rev. | Transmittal No. | Date | Comment No. | Comment Date | CM
|  |  |  | Toroq Seamless Pipe Mill | [8 empty] | 100 | 27.18%
Basic | [12 empty] | 19.5837 | 61.94%
| Management and Project Control | [11 empty] | 0.5913 | 100%
B | P |  |  | Numbering Method | GEN-01-P-O-00-001 | IFI | D | 98207-4-0017 | 2020-04-19 |  |  |  | 0.23652 | 100% |  | IFI | B | 98207-4-0001 | 2020-01-25 |  |  |  |  | IFI | C | 98207-4-0005 | 2020-02-17 |  |  |  |  | IFI | D | 98207-4-0017 | 2020-04-19
B | P |  |  | Coordination Procedure | GEN-01-P-O-00-002 | IFI | A | 98207-4-0002 | 2020-01-25 |  |  |  | 0.23652 | 100% |  | IFI | A | 98207-4-0002 | 2020-01-25
B | P |  |  | Overall Time Schedule | GEN-01-P-O-00-003 | IFI | A | 98207-4-0015 | 2020-04-15 |  |  |  | 0.11826 | 100% |  | IFI | A | 98207-4-0015 | 2020-04-15
| Fluid Engineering | [11 empty] | 2.4834 | 0%
B | M |  |  | Process Flow Diagram | GEN-01-D-U-01-001 | [7 empty] | 1.7739
B | M |  |  | Fire Fighting Concept | GEN-01-S-U-01-050 | [7 empty] | 0.70956
| Civil & Structure | [11 empty] | 14.1438 | 81.58%
|  | General Basic | [10 empty] | 11.14 | 90.3%
B | C |  |  | General Layout | GEN-01-D-P-00-001 | IFC | 2 | 98207-4-0024 | 2020-05-02 |  |  |  | 3.8907 | 100% |  | IFA | A | 98207-4-0003 | 2020-01-25 |  |  |  |  | IFC | 0 | 98207-4-0006 | 2020-02-17 |  |  |  |  | IFC | 1 | 98207-4-0009 | 2020-03-11 |  |  |  |  | IFC | 2 | 98207-4-0024 | 2020-05-02
B | C |  |  | Steel work general notes | GEN-01-S-S-GN-001 | IFC | 0 | 98207-4-0026 | 2020-05-16 |  |  |  | 0.47304 | 100% |  | IFA | A | 98207-4-0014 | 2020-04-15 |  |  |  |  | IFC | 0 | 98207-4-0026 | 2020-05-16
B | C |  |  | Civil work general notes | GEN-01-S-C-GN-001 | IFC | 0 | 98207-4-0026 | 2020-05-16 |  |  |  | 0.47304 | 100% |  | IFA | A | 98207-4-0014 | 2020-04-15 |  |  |  |  | IFC | 0 | 98207-4-0026 | 2020-05-16
B | C |  |  | Road Plan & Profile | ROD-01-D-C-DR-001 | IFA | A | 98207-4-0013 | 2020-04-13 |  |  |  | 0.74503 | 70% |  | IFA | A | 98207-4-0013 | 2020-04-13
B | C |  |  | Site Condition | GEN-01-R-C-SC-001 | IFA | A | 98207-4-0020 | 2020-04-27 |  |  |  | 0.37252 | 70% |  | IFA | A | 98207-4-0020 | 2020-04-27
|  |  |  | Grading Plan | ROD-01-D-C-BS-001 | IFC | 0 | 98207-4-0027 | 2020-05-30 |  |  |  | 0.37252 | 100% |  | IFA | A | 98207-4-0025 | 2020-05-09 |  |  |  |  | IFC | 0 | 98207-4-0027 | 2020-05-30
B | C |  |  | Water Draiange System | ROD-01-D-C-00-051~100 | [7 empty] | 0.74503
B | C |  |  | MAIN Building & STORAGE BASIC
|  |  |  | MAIN Building & STORAGE BASIC-PLAN | SLN-01-D-S-BA-001 | IFC | 0 | 98207-4-0026 | 2020-05-16 |  |  |  | 0.37547 | 100% |  | IFA | A | 98207-4-0007 | 2020-03-09 |  |  |  |  | IFC | 0 | 98207-4-0026 | 2020-05-16
|  |  |  | MAIN Building & STORAGE BASIC-Building SECTION(2) | SLN-01-D-S-BA-002 | IFC | 0 | 98207-4-0026 | 2020-05-16 |  |  |  | 0.37547 | 100% |  | IFA | A | 98207-4-0007 | 2020-03-09 |  |  |  |  | IFC | 0 | 98207-4-0026 | 2020-05-16
|  |  |  | MAIN Building & STORAGE BASIC-CRANE BEAMS & WALKWAY PLAN | SLN-01-D-S-BA-003 | IFC | 0 | 98207-4-0026 | 2020-05-16 |  |  |  | 0.37547 | 100% |  | IFA | A | 98207-4-0007 | 2020-03-09 |  |  |  |  | IFC | 0 | 98207-4-0026 | 2020-05-16
|  |  |  | MAIN Building & STORAGE BASIC-FRAME PLAN | SLN-01-D-S-BA-004 | IFC | 0 | 98207-4-0026 | 2020-05-16 |  |  |  | 0.37547 | 100% |  | IFA | A | 98207-4-0007 | 2020-03-09 |  |  |  |  | IFC | 0 | 98207-4-0026 | 2020-05-16
|  |  |  | MAIN Building & STORAGE BASIC-VIEWS | SLN-01-D-S-BA-005 | IFC | 0 | 98207-4-0026 | 2020-05-16 |  |  |  | 0.37547 | 100% |  | IFA | A | 98207-4-0007 | 2020-03-09 |  |  |  |  | IFC | 0 | 98207-4-0026 | 2020-05-16
|  |  |  | MAIN Building & STORAGE BASIC-Building SECTION(1) | SLN-01-D-S-BA-006 | IFC | 0 | 98207-4-0026 | 2020-05-16 |  |  |  | 0.37547 | 100% |  | IFA | A | 98207-4-0007 | 2020-03-09 |  |  |  |  | IFC | 0 | 98207-4-0026 | 2020-05-16
|  |  |  | MAIN Building & STORAGE BASIC-VIEW FOR AXIS 01&15 | SLN-01-D-S-BA-007 | IFC | 0 | 98207-4-0026 | 2020-05-16 |  |  |  | 0.37547 | 100% |  | IFA | A | 98207-4-0007 | 2020-03-09 |  |  |  |  | IFC | 0 | 98207-4-0026 | 2020-05-16
|  |  |  | MAIN Building & STORAGE BASIC-CRANES ARRANGEMENT | SLN-01-D-S-BA-008 | IFC | 0 | 98207-4-0026 | 2020-05-16 |  |  |  | 0.37547 | 100% |  | IFA | A | 98207-4-0007 | 2020-03-09 |  |  |  |  | IFC | 0 | 98207-4-0026 | 2020-05-16
B | C |  |  | Building Basic Report | SLN-01-R-F-BA-001 | IFI | A | 98207-4-0004 | 2020-01-26 |  |  |  | 1.0643 | 100% |  | IFI | A | 98207-4-0004 | 2020-01-26
|  | Ancillary building | [10 empty] | 3.0038 | 49.25%
B | C |  |  | Conteen, Prayer room & Locker and Shower | ANC-01-D-C-BL-001~010 | IFA | A | 98207-4-0019 | 2020-04-27 |  |  |  | 0.6859 | 70% |  | IFA | A | 98207-4-0019 | 2020-04-27
B | C |  |  | Administrative building-GROUND FLOOR PLAN | ANC-01-D-C-BL-010 | IFA | A | 98207-4-0023 | 2020-05-02 |  |  |  | 1.0052 | 70% |  | IFA | A | 98207-4-0023 | 2020-05-02
|  |  |  | Administrative building-FIRST FLOOR PLAN | ANC-01-D-C-BL-011 | IFA | A | 98207-4-0023 | 2020-05-02 |  |  |  |  | 70% |  | IFA | A | 98207-4-0023 | 2020-05-02
|  |  |  | Administrative building-SECOND FLOOR PLAN | ANC-01-D-C-BL-012 | IFA | A | 98207-4-0023 | 2020-05-02 |  |  |  |  | 70% |  | IFA | A | 98207-4-0023 | 2020-05-02
B | C |  |  | Guard house | ANC-01-D-C-BL-020~030 | [7 empty] | 0.34295
B | C |  |  | Repair Work Shop | ANC-01-D-C-BL-030~040 | [7 empty] | 0.67408
| B |  |  | Initial estimation of ancillary building | ANC-01-R-C-BL-050 | IFI | A | 98207-4-0010 | 2020-03-11 |  |  |  | 0.29565 | 100% |  | IFI | A | 98207-4-0010 | 2020-03-11
| Electrical & Automation | [11 empty] | 2.3652 | 0%
B | E |  |  | Overal Single Line Diagram | GEN-01-D-E-03-001 | [7 empty] | 0.94607
B | E |  |  | Load List | GEN-01-L-E-11-001 | [7 empty] | 0.70956
B | E |  |  | P&ID for Process Water Systems | GEN-01-D-I-01-001 | [7 empty] | 0.70956
Detail | [12 empty] | 80.4163 | 18.72%
| Fluid Engineering | [11 empty] | 19.9858 | 3.787%
|  | Piping Engineering | [10 empty] | 10.5842 | 0%
|  |  | Interconnecting Piping | [9 empty] | 4.7304 | 0%
D | M |  |  | Piping Key Plan | GEN-01-D-U-11-002 | [7 empty] | 1.5374
D | M |  |  | Piping Arrangement | GEN-01-D-U-21-003 | [7 empty] | 1.4191
D | M |  |  | Standard Pipe Support | GEN-01-D-U-43-004 | [7 empty] | 1.1826
D | M |  |  | Line List | GEN-01-L-U-63-005 | [7 empty] | 0.5913
|  |  | WTP (Pump Station, Cooling System) | [9 empty] | 3.1339 | 0%
D | M |  |  | Piping Arrangement | COO-01-D-U-21-006 | [7 empty] | 3.1339
|  |  | Material Take Off | [9 empty] | 1.1235 | 0%
D | M |  |  | MTO for Metal Piping | GEN-01-D-U-61-007 | [7 empty] | 0.41391
D | M |  |  | MTO for Non-Metal piping | GEN-01-D-U-61-008 | [7 empty] | 0.41391
D | M |  |  | Valve List | GEN-01-L-U-61-009 | [7 empty] | 0.29565
|  |  | ISO Metric Drawings | [9 empty] | 1.1235 | 0%
D | M |  |  | ISO Metric for Cooling Water | GEN-01-D-U-51-010 | [7 empty] | 0.41391
D | M |  |  | ISO Metric for Natural Gas | GEN-01-D-U-51-011 | [7 empty] | 0.41391
D | M |  |  | ISO Metric for Compressed Air | GEN-01-D-U-51-012 | [7 empty] | 0.29565
|  |  | Specification | [9 empty] | 0.28382 | 0%
D | M |  |  | Specification For Coating & Wrapping Of Underground Piping | GEN-01-S-U-10-046 | [7 empty] | 0.094607
D | M |  |  | Specification For Painting | GEN-01-S-U-10-047 | [7 empty] | 0.094607
D | M |  |  | Specification For Welding | GEN-01-S-U-10-048 | [7 empty] | 0.094607
|  |  | Underground Piping | [9 empty] | 0.18921 | 0%
D | M |  |  | Underground Piping Arrangement | GEN-01-D-U-02-013 | [7 empty] | 0.094607
D | M |  |  | MTO for Underground Piping | GEN-01-D-U-61-014 | [7 empty] | 0.094607
|  | Utility Engineering | [10 empty] | 3.0747 | 0%
D | M |  |  | Equipment Arrangement For Cooling System | COO-01-D-U-11-015 | [7 empty] | 0.23652
D | M |  |  | Equipment List For Cooling System | COO-01-L-U-64-016 | [7 empty] | 0.23652
D | M |  |  | Sewage Collection Network | UTI-01-D-U-02-017 | [7 empty] | 0.70956
D | M |  |  | MTO for Sewage system | UTI-01-D-U-61-018 | [7 empty] | 0.23652
D | M |  |  | Utitlity Consumption List | UTI-01-L-U-09-049 | [7 empty] | 0.11826
D | M |  |  | Firefighting System | UTI-01-D-U-11-019 | [7 empty] | 0.23652
D | M |  |  | Industrial Wastewater System | UTI-01-D-U-11-020 | [7 empty] | 1.3009
|  | HVAC Engineering | [10 empty] | 2.5426 | 0%
|  |  | Administrative Building | [9 empty] | 0.47304 | 0%
D | M |  |  | Cooling and Heating System | ANC-01-D-U-91-021 | [7 empty] | 0.11826
D | M |  |  | Ventilation System | ANC-01-D-U-91-022 | [7 empty] | 0.11826
D | M |  |  | Sewage System | ANC-01-D-U-91-023 | [7 empty] | 0.11826
D | M |  |  | Plumbing System | ANC-01-D-U-91-024 | [7 empty] | 0.11826
|  |  | Locker and Shower Building | [9 empty] | 0.47304 | 0%
D | M |  |  | Cooling and Heating System | ANC-01-D-U-91-025 | [7 empty] | 0.11826
D | M |  |  | Ventilation System | ANC-01-D-U-91-026 | [7 empty] | 0.11826
D | M |  |  | Sewage System | ANC-01-D-U-91-027 | [7 empty] | 0.11826
D | M |  |  | Plumbing System | ANC-01-D-U-91-028 | [7 empty] | 0.11826
|  |  | Conteen Building | [9 empty] | 0.35478 | 0%
D | M |  |  | Cooling and Heating System | ANC-01-D-U-91-029 | [7 empty] | 0.094607
D | M |  |  | Ventilation System | ANC-01-D-U-91-030 | [7 empty] | 0.094607
D | M |  |  | Sewage System | ANC-01-D-U-91-031 | [7 empty] | 0.082781
D | M |  |  | Plumbing System | ANC-01-D-U-91-032 | [7 empty] | 0.082781
|  |  | Guarde Building | [9 empty] | 0.29565 | 0%
D | M |  |  | Cooling and Heating System | ANC-01-D-U-91-033 | [7 empty] | 0.082781
D | M |  |  | Ventilation System | ANC-01-D-U-91-034 | [7 empty] | 0.070956
D | M |  |  | Sewage System | ANC-01-D-U-91-035 | [7 empty] | 0.070956
D | M |  |  | Plumbing System | ANC-01-D-U-91-036 | [7 empty] | 0.070956
|  |  | Process Building | [9 empty] | 0.94607 | 0%
D | M |  |  | Ventilation System | SLN-01-D-U-91-037 | [7 empty] | 0.35478
D | M |  |  | Sewage System | SLN-01-D-U-91-038 | [7 empty] | 0.29565
D | M |  |  | Plumbing System | SLN-01-D-U-91-039 | [7 empty] | 0.29565
|  | Inquiry Documents | [10 empty] | 3.7843 | 20%
|  |  | Utility | [9 empty] | 3.2876 | 23.02%
D | M |  |  | Inquiry & Data Sheet for RO System | COO-01-I-U-62-040 | IFI | A | 98207-4-0008 | 2020-03-09 |  |  |  | 0.75686 | 100% |  | IFI | A | 98207-4-0008 | 2020-03-09
D | M |  |  | Inquiry & Data Sheet fot Cooling Tower | COO-01-I-U-62-041 | [7 empty] | 0.5913
D | M |  |  | Inquiry & Data Sheet for Water Pumps | COO-01-I-U-62-042 | [7 empty] | 0.5913
D | M |  |  | Inquiry & Data Sheet for Industrial Gas Racks | UTI-01-I-U-62-044 | [7 empty] | 0.5913
D | M |  |  | Inquiry & Data Sheet for Compressed Air System | UTI-01-I-U-62-043 | [7 empty] | 0.75686
|  |  | HVAC | [9 empty] | 0.49669 | 0%
D | M |  |  | Inquiry & Data Sheet for Package Unit | ANC-01-I-U-62-045 | [7 empty] | 0.49669
| Civil and Structure | [11 empty] | 41.6272 | 31.5%
|  | Civil and St. St. | [10 empty] | 34.8628 | 37.02%
|  |  | Main Building & Storage | [9 empty] | 17.1358 | 65.99%
D | C |  |  | Main Building & Storage structure | SLN-01-D-S-E3-001 | IFA | B | 98207-4-0021 | 2020-04-27 |  |  |  | 9.4607 | 70% |  | IFA | A | 98207-4-0011 | 2020-03-24 |  |  |  |  | IFA | B | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-GRID 1 , 15 | SLN-01-D-S-E3-002 | IFA | B | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0011 | 2020-03-24 |  |  |  |  | IFA | B | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-GRID 2 ,3,4,5,6,9,10,11,12,13,14 | SLN-01-D-S-E3-003 | IFA | B | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0011 | 2020-03-24 |  |  |  |  | IFA | B | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-GRID 7 , 8 | SLN-01-D-S-E3-004 | IFA | B | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0011 | 2020-03-24 |  |  |  |  | IFA | B | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-GRID A , B , C | SLN-01-D-S-E3-005 | IFA | B | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0011 | 2020-03-24 |  |  |  |  | IFA | B | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-PLAN +9.000 ( CRANE BEAMS & WALKWAY PLAN ) | SLN-01-D-S-E3-006 | IFA | B | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0011 | 2020-03-24 |  |  |  |  | IFA | B | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-GRID 1a, 2a ,. 3a , 4a , 5a , 6a , 9a , 10a | SLN-01-D-S-E3-007 | IFA | B | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0011 | 2020-03-24 |  |  |  |  | IFA | B | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-FRAMES PLAN | SLN-01-D-S-E3-008 | IFA | B | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0011 | 2020-03-24 |  |  |  |  | IFA | B | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE- ROOF BRACING PLAN | SLN-01-D-S-E3-009 | IFA | B | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0011 | 2020-03-24 |  |  |  |  | IFA | B | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-ROOF BEAM | SLN-01-D-S-E3-010 | IFA | B | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0011 | 2020-03-24 |  |  |  |  | IFA | B | 98207-4-0021 | 2020-04-27
|  |  |  | PURLIN & SAGROD -PLAN MAIN SALOON & STORAGE | SLN-01-D-S-E3-011 | IFA | A | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-PURLIN & SAGROD ( DETAILS ) | SLN-01-D-S-E3-012 | IFA | A | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-GRID 10a , 11a | SLN-01-D-S-E3-013 | IFA | A | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-GRID 12a , 13a | SLN-01-D-S-E3-014 | IFA | A | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR1 | SLN-01-D-S-E3-015 | IFA | B | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0011 | 2020-03-24 |  |  |  |  | IFA | B | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR1 | SLN-01-D-S-E3-016 | IFA | B | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0011 | 2020-03-24 |  |  |  |  | IFA | B | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR1 - SECTION & DETAILS | SLN-01-D-S-E3-017 | IFA | A | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR2 | SLN-01-D-S-E3-020 | IFA | B | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0011 | 2020-03-24 |  |  |  |  | IFA | B | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR2 | SLN-01-D-S-E3-021 | IFA | B | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0011 | 2020-03-24 |  |  |  |  | IFA | B | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR2 -SECTION & DETAILS | SLN-01-D-S-E3-022 | IFA | A | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR3,5 | SLN-01-D-S-E3-025 | IFA | B | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0011 | 2020-03-24 |  |  |  |  | IFA | B | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR4 | SLN-01-D-S-E3-028 | IFA | B | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0011 | 2020-03-24 |  |  |  |  | IFA | B | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR4 | SLN-01-D-S-E3-029 | IFA | B | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0011 | 2020-03-24 |  |  |  |  | IFA | B | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR4 -SECTION & DETAILS | SLN-01-D-S-E3-030 | IFA | A | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR6 | SLN-01-D-S-E3-032 | IFA | B | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0011 | 2020-03-24 |  |  |  |  | IFA | B | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR6 | SLN-01-D-S-E3-033 | IFA | B | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0011 | 2020-03-24 |  |  |  |  | IFA | B | 98207-4-0021 | 2020-04-27
|  |  |  | CRANE BEAM CR6 -SECTION & DETAILSMAIN SALOON & STORAGE- | SLN-01-D-S-E3-034 | IFA | A | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR7 | SLN-01-D-S-E3-036 | IFA | B | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0011 | 2020-03-24 |  |  |  |  | IFA | B | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR7 | SLN-01-D-S-E3-037 | IFA | B | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0011 | 2020-03-24 |  |  |  |  | IFA | B | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR7 & SECTION & DETAILS | SLN-01-D-S-E3-038 | IFA | A | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR8 | SLN-01-D-S-E3-040 | IFA | B | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0011 | 2020-03-24 |  |  |  |  | IFA | B | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR8 | SLN-01-D-S-E3-041 | IFA | B | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0011 | 2020-03-24 |  |  |  |  | IFA | B | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR8 -SECTION & DETAILS | SLN-01-D-S-E3-042 | IFA | A | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR9 | SLN-01-D-S-E3-043 | IFA | A | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR9 | SLN-01-D-S-E3-044 | IFA | A | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-BEAM B1 , B2 , B3 , B4 | SLN-01-D-S-E3-045 | IFA | B | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0011 | 2020-03-24 |  |  |  |  | IFA | B | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-BEAM B1 , B2 , B3 , B4 | SLN-01-D-S-E3-046 | IFA | A | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR10 | SLN-01-D-S-E3-047 | IFA | A | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR10 | SLN-01-D-S-E3-048 | IFA | A | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR9&10 - SECTION & DETAILS | SLN-01-D-S-E3-049 | IFA | A | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-BASE PLATE | SLN-01-D-S-E3-050 | IFA | B | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0011 | 2020-03-24 |  |  |  |  | IFA | B | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-COLUMN 2 | SLN-01-D-S-E3-052 | IFA | B | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0011 | 2020-03-24 |  |  |  |  | IFA | B | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-RAFTER | SLN-01-D-S-E3-053 | IFA | B | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0011 | 2020-03-24 |  |  |  |  | IFA | B | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-BRACING BR1 , BR 2 - SECTION & DETAILS ( 1 ) | SLN-01-D-S-E3-055 | IFA | A | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE0BRACING - SECTION & DETAILS ( 2 ) | SLN-01-D-S-E3-056 | IFA | A | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-BRACING - SECTION & DETAILS ( 3 ) | SLN-01-D-S-E3-057 | IFA | A | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-AIRAROR PLAN | SLN-01-D-S-E3-060 | IFA | A | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-CLADDING GIRT 1 , 15 | SLN-01-D-S-E3-065 | IFA | A | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-CLADDING GIRT 1 , 15 & SECTION & DETAILS | SLN-01-D-S-E3-066 | IFA | A | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-CLADDING GIRT A , B | SLN-01-D-S-E3-067 | IFA | A | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-CLADDING GIRT A , B - SECTION & DETAILS ( 1 ) | SLN-01-D-S-E3-068 | IFA | A | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-CLADDING GIRT A , B - SECTION & DETAILS ( 2 ) | SLN-01-D-S-E3-069 | IFA | A | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-CLADDING GIRT A , B - SECTION & DETAILS ( 3 ) | SLN-01-D-S-E3-070 | IFA | A | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-CLADDING GIRT 15 | SLN-01-D-S-E3-071 | IFA | A | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-LADDER & SECTION & DETAILS | SLN-01-D-S-E3-075 | IFA | A | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-LADDER - SECTION & DETAILS | SLN-01-D-S-E3-076 | IFA | A | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-STOPPER & PLAN | SLN-01-D-S-E3-077 | IFA | A | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-WALKWAY | SLN-01-D-S-E3-080 | IFA | A | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0021 | 2020-04-27
|  |  |  | WALKWAY & SECTION & DETAILS MAIN SALOON & STORAGE- | SLN-01-D-S-E3-081 | IFA | A | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0021 | 2020-04-27
|  |  |  | AERATOR MAIN SALOON & STORAGE- | SLN-01-D-S-E3-082 | IFA | A | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0021 | 2020-04-27
|  |  |  | MAIN SALOON & STORAGE-AERATOR & SECTION & VIEW | SLN-01-D-S-E3-083 | IFA | A | 98207-4-0021 | 2020-04-27 |  |  |  |  | 70% |  | IFA | A | 98207-4-0021 | 2020-04-27
|  |  |  | Main Building & Storage structure-FRAME TYPE & VERTICAL BRACE PLAN | SLN-01-D-S-E3-100 | IFA | A | [6 empty] | 70% |  | IFA | A | 98207-4-0030 | 2020-08-19
|  |  |  | Main Building & Storage structure-ROOF PLAN | SLN-01-D-S-E3-101 | IFA | A | [6 empty] | 70% |  | IFA | A | 98207-4-0030 | 2020-08-19
|  |  |  | Main Building & Storage structure-ROOF DETAILS& FRMAE AXIS "A" - PART1 | SLN-01-D-S-E3-102 | IFA | A | [6 empty] | 70% |  | IFA | A | 98207-4-0030 | 2020-08-19
|  |  |  | Main Building & Storage structure-FRAMES - PART1 | SLN-01-D-S-E3-103 | IFA | A | [6 empty] | 70% |  | IFA | A | 98207-4-0030 | 2020-08-19
|  |  |  | Main Building & Storage structure-FRAME DETAILS - PART1 | SLN-01-D-S-E3-104 | IFA | A | [6 empty] | 70% |  | IFA | A | 98207-4-0030 | 2020-08-19
|  |  |  | Main Building & Storage structure-FRAME F1&DETAIL - PART1 | SLN-01-D-S-E3-105 | IFA | A | [6 empty] | 70% |  | IFA | A | 98207-4-0030 | 2020-08-19
|  |  |  | Main Building & Storage structure-FRAME F1&DETAIL | SLN-01-D-S-E3-106 | IFA | A | [6 empty] | 70% |  | IFA | A | 98207-4-0030 | 2020-08-19
|  |  |  | Main Building & Storage structure-CRANE GIRDER DETAILS | SLN-01-D-S-E3-107 | IFA | A | [6 empty] | 70% |  | IFA | A | 98207-4-0030 | 2020-08-19
|  |  |  | Main Building & Storage structure-CRANE GIRDER DETAILS | SLN-01-D-S-E3-108 | IFA | A | [6 empty] | 70% |  | IFA | A | 98207-4-0030 | 2020-08-19
D | C |  |  | MAIN BUILDING & STORAGE FOUNDATION-EXCAVATION PLAN | SLN-01-D-C-EE-001 | IFA | A | 98207-4-0014 | 2020-04-15 |  |  |  | 2.3652 | 70% |  | IFA | A | 98207-4-0014 | 2020-04-15
|  |  |  | MAIN BUILDING & STORAGE FOUNDATION-FOUNDATIONS PLAN | SLN-01-D-C-EE-002 | IFA | A | 98207-4-0014 | 2020-04-15 |  |  |  |  | 70% |  | IFA | A | 98207-4-0014 | 2020-04-15
|  |  |  | MAIN BUILDING & STORAGE FOUNDATION-FOUNDATIONS FORMWORK | SLN-01-D-C-EE-003 | IFA | A | 98207-4-0014 | 2020-04-15 |  |  |  |  | 70% |  | IFA | A | 98207-4-0014 | 2020-04-15
|  |  |  | MAIN BUILDING & STORAGE FOUNDATION-ANCHOR "2A-056" DETAILS | SLN-01-D-C-EE-004 | IFA | A | 98207-4-0014 | 2020-04-15 |  |  |  |  | 70% |  | IFA | A | 98207-4-0014 | 2020-04-15
|  |  |  | Main Saloon & Storage Steel Structure-LIST OF DRAWINGS | SLN-01-D-C-EE-010 | [8 empty] | 70% |  | IFA | A | 98207-4-0031 | 2020-08-26
|  |  |  | Main Saloon & Storage Steel Structure-EXCAVATION PLAN "PART 1" | SLN-01-D-C-EE-011 | [8 empty] | 70% |  | IFA | A | 98207-4-0031 | 2020-08-26
|  |  |  | Main Saloon & Storage Steel Structure-FOUNDATION PLAN "PART 1" | SLN-01-D-C-EE-012 | [8 empty] | 70% |  | IFA | A | 98207-4-0031 | 2020-08-26
|  |  |  | Main Saloon & Storage Steel Structure-FOUNDATION "F.1" | SLN-01-D-C-EE-013 | [8 empty] | 70% |  | IFA | A | 98207-4-0031 | 2020-08-26
|  |  |  | Main Saloon & Storage Steel Structure-FOUNDATION "F.2" | SLN-01-D-C-EE-014 | [8 empty] | 70% |  | IFA | A | 98207-4-0031 | 2020-08-26
|  |  |  | Main Saloon & Storage Steel Structure-FOUNDATION "F.3" | SLN-01-D-C-EE-015 | [8 empty] | 70% |  | IFA | A | 98207-4-0031 | 2020-08-26
|  |  |  | Main Saloon & Storage Steel Structure-FOUNDATION "F.4" | SLN-01-D-C-EE-016 | [8 empty] | 70% |  | IFA | A | 98207-4-0031 | 2020-08-26
|  |  |  | Main Saloon & Storage Steel Structure-FOUNDATION "F.5" | SLN-01-D-C-EE-017 | [8 empty] | 70% |  | IFA | A | 98207-4-0031 | 2020-08-26
|  |  |  | Main Saloon & Storage Steel Structure-FOUNDATION "F.6" | SLN-01-D-C-EE-018 | [8 empty] | 70% |  | IFA | A | 98207-4-0031 | 2020-08-26
|  |  |  | Main Saloon & Storage Steel Structure-FOUNDATION "F.W" | SLN-01-D-C-EE-019 | [8 empty] | 70% |  | IFA | A | 98207-4-0031 | 2020-08-26
D | C |  |  | MAIN BUILDING & STORAGE FOUNDATION-FOUNDATON "F1"REINFORCEMENT | SLN-01-D-C-EF-001 | IFA | A | 98207-4-0014 | 2020-04-15 |  |  |  | 2.3652 | 70% |  | IFA | A | 98207-4-0014 | 2020-04-15
|  |  |  | MAIN BUILDING & STORAGE FOUNDATION-FOUNDATON "F1"REINFORCEMENT | SLN-01-D-C-EF-002 | IFA | A | 98207-4-0014 | 2020-04-15 |  |  |  |  | 70% |  | IFA | A | 98207-4-0014 | 2020-04-15
D | C |  |  | Main Building & Storage MTO | SLN-01-D-C-MT-001 | IFA | B | 98207-4-0021 | 2020-04-27 |  |  |  | 0.98155 | 70% |  | IFA | A | 98207-4-0011 | 2020-03-24 |  |  |  |  | IFA | B | 98207-4-0021 | 2020-04-27
D | C |  |  | Main Building & Storage Pavement | SLN-01-D-C-EM-001 | [7 empty] | 0.98155
D | C |  |  | Main Building & Storge Calculation sheet | SLN-01-C-S-CA-001 | IFA | A | 98207-4-0012 | 2020-04-04 |  |  |  | 0.98155 | 70% |  | IFA | A | 98207-4-0012 | 2020-04-04
|  |  |  | Main Building & Storage Foundation Calculation Sheet | SLN-01-C-S-CA-003 | [8 empty] | 70% |  | IFA | A | 98207-4-0031 | 2020-08-26
|  |  | Equipment Foundation | [9 empty] | 6.114 | 26.13%
D | C |  |  | COLD DISC SAW(FORMWORK)-LIST OF DRAWINGS | COL-01-D-C-EE-001 | IFA | A | 98207-4-0029 | 2020-06-24 |  |  |  | 0.29565 | 70% |  | IFA | A | 98207-4-0029 | 2020-06-24
|  |  |  | COLD DISC SAW(FORMWORK)-PLAN & SECTION A-A | COL-01-D-C-EE-002 | IFA | A | 98207-4-0029 | 2020-06-24 |  |  |  | 0.11353 | 70% |  | IFA | A | 98207-4-0029 | 2020-06-24
|  |  |  | COLD DISC SAW(FORMWORK)-SECTION B-B, C-C, D-D, E-E, G-G, K-K, V-V & Z-Z | COL-01-D-C-EE-003 | IFA | A | 98207-4-0029 | 2020-06-24 |  |  |  | 0.11353 | 70% |  | IFA | A | 98207-4-0029 | 2020-06-24
|  |  |  | COLD DISC SAW(FORMWORK)-SECTION F-F, H-H, L-L & EMBEDDED PLATE DETAILS | COL-01-D-C-EE-004 | IFA | A | 98207-4-0029 | 2020-06-24 |  |  |  | 0.11353 | 70% |  | IFA | A | 98207-4-0029 | 2020-06-24
D | C |  |  | COLD DISC SAW(REINFORCEMENT)-UNIFORM BAR PLAN(BOT.) & SECTION A-A, F-F & E-E | COL-01-D-C-EF-001 | IFA | A | 98207-4-0029 | 2020-06-24 |  |  |  | 0.28382 | 70% |  | IFA | A | 98207-4-0029 | 2020-06-24
|  |  |  | COLD DISC SAW(REINFORCEMENT)-UNIFORM BAR PLAN(TOP) & SECTION D-D, C-C & L-L | COL-01-D-C-EF-002 | IFA | A | 98207-4-0029 | 2020-06-24 |  |  |  | 0.11353 | 70% |  | IFA | A | 98207-4-0029 | 2020-06-24
|  |  |  | COLD DISC SAW(REINFORCEMENT)-SECTION B-B, G-G, H-H, K-K, V-V, Z-Z & BAR BENDING SCHEDULE | COL-01-D-C-EF-003 | IFA | A | 98207-4-0029 | 2020-06-24 |  |  |  | 0.11353 | 70% |  | IFA | A | 98207-4-0029 | 2020-06-24
D | C |  |  | Heating furnace (Formwork) | HEA-01-D-C-EE-001 | [7 empty] | 0.28382
D | C |  |  | Heating furnace (Reinforcement) | HEA-01-D-C-EF-001 | [7 empty] | 0.28382
D | C |  |  | Piercing mill (Formwork) | PIE-01-D-C-EE-001 | [7 empty] | 0.28382
D | C |  |  | Piercing mill (Reinforcement) | PIE-01-D-C-EF-001 | [7 empty] | 0.28382
D | C |  |  | Elongator (Formwork) | ELO-01-D-C-EE-001 | [7 empty] | 0.28382
D | C |  |  | Elongator (Reinforcement) | ELO-01-D-C-EF-001 | [7 empty] | 0.28382
D | C |  |  | Inductive heater (Formwork) | IND-01-D-C-EE-001 | [7 empty] | 0.28382
D | C |  |  | Inductive heater (Reinforcement) | IND-01-D-C-EF-001 | [7 empty] | 0.28382
D | C |  |  | Sizing mill (Formwork) | SIZ-01-D-C-EE-001 | [7 empty] | 0.28382
D | C |  |  | Sizing mill (Reinforcement) | SIZ-01-D-C-EF-001 | [7 empty] | 0.28382
D | C |  |  | COOLING BED (FORMWORK)-PLAN | COB-01-D-C-EE-001 | IFA | A | 98207-4-0028 | 2020-06-10 |  |  |  | 0.28382 | 70% |  | IFA | A | 98207-4-0028 | 2020-06-10
|  |  |  | COOLING BED (FORMWORK)-SECTION(1) | COB-01-D-C-EE-002 | IFA | A | 98207-4-0028 | 2020-06-10 |  |  |  | 0.081092 | 70% |  | IFA | A | 98207-4-0028 | 2020-06-10
|  |  |  | COOLING BED (FORMWORK)-SECTION (2) | COB-01-D-C-EE-003 | IFA | A | 98207-4-0028 | 2020-06-10 |  |  |  | 0.081092 | 70% |  | IFA | A | 98207-4-0028 | 2020-06-10
|  |  |  | COOLING BED (FORMWORK)-DETAILS | COB-01-D-C-EE-004 | IFA | A | 98207-4-0028 | 2020-06-10 |  |  |  | 0.081092 | 70% |  | IFA | A | 98207-4-0028 | 2020-06-10
D | C |  |  | COOLING BED (REINFORCEMENT)-FOUNDATION PLAN | COB-01-D-C-EF-001 | IFA | A | 98207-4-0028 | 2020-06-10 |  |  |  | 0.28382 | 70% |  | IFA | A | 98207-4-0028 | 2020-06-10
|  |  |  | COOLING BED (REINFORCEMENT)-WALLS (1) | COB-01-D-C-EF-002 | IFA | A | 98207-4-0028 | 2020-06-10 |  |  |  | 0.081092 | 70% |  | IFA | A | 98207-4-0028 | 2020-06-10
|  |  |  | COOLING BED (REINFORCEMENT)-WALLS (2) | COB-01-D-C-EF-003 | IFA | A | 98207-4-0028 | 2020-06-10 |  |  |  | 0.081092 | 70% |  | IFA | A | 98207-4-0028 | 2020-06-10
|  |  |  | COOLING BED (REINFORCEMENT)-WALLS (3) | COB-01-D-C-EF-004 | IFA | A | 98207-4-0028 | 2020-06-10 |  |  |  | 0.081092 | 70% |  | IFA | A | 98207-4-0028 | 2020-06-10
|  |  |  | COOLING BED (REINFORCEMENT)-PEDESTALS | COB-01-D-C-EF-005 | IFA | A | 98207-4-0028 | 2020-06-10 |  |  |  | 0.081092 | 70% |  | IFA | A | 98207-4-0028 | 2020-06-10
D | C |  |  | Cooling system (Formwork) | COO-01-D-C-EE-001 | [7 empty] | 0.28382
D | C |  |  | Cooling system (Reinforcement) | COO-01-D-C-EF-001 | [7 empty] | 0.28382
|  |  |  | FURNACE CHARGE AREA(FORMWORK)-LIST OF DRAWINGS | CHR-01-D-C-EE-001 | [8 empty] | 70% |  | IFA | A | 98207-4-0032 | 2020-09-07
|  |  |  | FURNACE CHARGE AREA(FORMWORK)-PLAN & SECTION E-E, K-K | CHR-01-D-C-EE-002 | [8 empty] | 70% |  | IFA | A | 98207-4-0032 | 2020-09-07
|  |  |  | FURNACE CHARGE AREA(FORMWORK)-SECTION A-A, C-C, D-D, G-G & F-F | CHR-01-D-C-EE-003 | [8 empty] | 70% |  | IFA | A | 98207-4-0032 | 2020-09-07
|  |  |  | FURNACE CHARGE AREA(REINFORCEMENT)-UNIFORM BAR PLAN(BOT.) & SECTION G-G | CHR-01-D-C-EF-001 | [8 empty] | 70% |  | IFA | A | 98207-4-0032 | 2020-09-07
|  |  |  | FURNACE CHARGE AREA(REINFORCEMENT)-UNIFORM BAR PLAN(TOP) & SECTION E-E, K-K, D-D, F-F | CHR-01-D-C-EF-002 | [8 empty] | 70% |  | IFA | A | 98207-4-0032 | 2020-09-07
|  |  |  | FURNACE CHARGE AREA(REINFORCEMENT)-SECTION A-A, C-C & BAR BENDING SCHEDULE | CHR-01-D-C-EF-003 | [8 empty] | 70% |  | IFA | A | 98207-4-0032 | 2020-09-07
D | C |  |  | Calculation Report for Foundations | GEN-01-D-C-CA-001 | [7 empty] | 0.42573
|  |  | Ancillary building | [9 empty] | 3.9262 | 0%
D | C |  |  | Conteen, Prayer room & Locker and Shower (Formwork) | ANC-01-D-C-EE-001~010 | [7 empty] | 0.54399
D | C |  |  | Conteen, Prayer room & Locker and Shower (Reinforcement) | ANC-01-D-C-EF-001~010 | [7 empty] | 0.54399
D | C |  |  | Administrative (Formwork) | ANC-01-D-C-EE-011~020 | [7 empty] | 0.54399
D | C |  |  | Administrative (Reinforcement) | ANC-01-D-C-EF-011~020 | [7 empty] | 0.54399
D | C |  |  | Guard house (Formwork) | ANC-01-D-C-EE-021~030 | [7 empty] | 0.17739
D | C |  |  | Guard house (Reinforcement) | ANC-01-D-C-EF-021~030 | [7 empty] | 0.18921
D | C |  |  | Bascule (Formwork) | ANC-01-D-C-EE-031~040 | [7 empty] | 0.094607
D | C |  |  | Bascule (Reinforcement) | ANC-01-D-C-EF-031~040 | [7 empty] | 0.094607
D | C |  |  | Building Toilets | ANC-01-D-C-EE-041~050 | [7 empty] | 0.17739
D | C |  |  | Repair Work Shop | ANC-01-D-C-EE-051~060 | [7 empty] | 0.57947
D | C |  |  | Laboratory (Formwork) | ANC-01-D-C-EE-061~070 | [7 empty] | 0.082781
D | C |  |  | Laboratory (Reinforcement) | ANC-01-D-C-EF-061~070 | [7 empty] | 0.082781
D | C |  |  | Calculation Report for Ancillary building | ANC-01-D-C-CA-001 | [7 empty] | 0.272
|  |  | Auxiliary buildings & FDN | [9 empty] | 7.6868 | 0%
D | C |  |  | Passage post (Formwork) | UTI-01-D-C-EE-001~010 | [7 empty] | 0.35478
D | C |  |  | Passage post (Reinforcement) | UTI-01-D-C-EF-001~010 | [7 empty] | 0.35478
D | C |  |  | Electrical room (Formwork) | UTI-01-D-C-EE-011~050 | [7 empty] | 1.0762
D | C |  |  | Electrical room (Reinforcement) | UTI-01-D-C-EF-011~050 | [7 empty] | 1.0643
D | C |  |  | Strorage Tank (Formwork) | UTI-01-D-C-EE-061~100 | [7 empty] | 0.3666
D | C |  |  | Strorage Tank (Reinforcement) | UTI-01-D-C-EF-061~100 | [7 empty] | 0.35478
D | C |  |  | Compressor room (Formwork) | UTI-01-D-C-EE-101~150 | [7 empty] | 0.3666
D | C |  |  | Compressor room (Reinforcement) | UTI-01-D-C-EF-101~150 | [7 empty] | 0.35478
D | C |  |  | WTP Buildings (Formwork) | UTI-01-D-C-EE-151~400 | [7 empty] | 1.4309
D | C |  |  | WTP Buildings (Reinforcement) | UTI-01-D-C-EF-151~400 | [7 empty] | 1.4309
D | C |  |  | Calculation Report for Auxiliary buildings | UTI-01-D-C-CA-001 | [7 empty] | 0.53217
|  | Architectural | [10 empty] | 5.2507 | 0%
|  |  | Main Building & Storage | [9 empty] | 4.281 | 0%
D | C |  |  | Main Building & Storage | SLN-01-D-C-EL-001~020 | [7 empty] | 3.7843
D | C |  |  | SITE PLAN | GEN-01-D-C-EL-0011 | [7 empty] | 0.49669
|  |  | Ancillary building | [9 empty] | 0.96973 | 0%
D | C |  |  | Conteen, Prayer room & Locker and Shower | ANC-01-D-C-EL-001~020 | [7 empty] | 0.29565
D | C |  |  | Administrative | ANC-01-D-C-EL-021~040 | [7 empty] | 0.29565
D | C |  |  | Guard house | ANC-01-D-C-EL-041~060 | [7 empty] | 0.094607
D | C |  |  | Bascule | ANC-01-D-C-EL-061~080 | [7 empty] | 0.047304
D | C |  |  | Building Toilets | ANC-01-D-C-EL-081~100 | [7 empty] | 0.047304
D | C |  |  | Repair Work Shop | ANC-01-D-C-EL-101~120 | [7 empty] | 0.15374
D | C |  |  | Laboratory | ANC-01-D-C-EL-121~130 | [7 empty] | 0.035478
|  | Road and Landscape | [10 empty] | 1.5137 | 13.67%
D | C |  |  | Access Roads | ROD-01-D-C-DR-001~100 | [7 empty] | 0.30747
D | C |  |  | Roads Plan & Profile | ROD-01-D-C-DR-100~200 | [7 empty] | 0.30747
D | C |  |  | Roads Cross Section & volume Table | ROD-01-D-C-DR-200~300 | [7 empty] | 0.30747
D | C |  |  | Water Draiange System | ROD-01-D-C-DW-001~100 | IFA | A | 98207-4-0016 | 2020-04-18 |  |  |  | 0.29565 | 70% |  | IFA | A | 98207-4-0016 | 2020-04-18
D | C |  |  | Leveling & Coding | ROD-01-D-C-DS-001~100 | [7 empty] | 0.29565
| Electrical and Automation | [11 empty] | 18.8032 | 6.296%
|  | Lighting and Low Current System | [10 empty] | 5.9484 | 7.932%
D | E |  |  | Overall Lighting Block Diagram | GEN-01-D-E-52-020 | [7 empty] | 0.16556
D | E |  |  | Main Lighting Panel Single Line Diagram | GEN-01-D-E-52-030 | [7 empty] | 0.16556
D | E |  |  | Lighting, Fire Alarm, CCTV and Intercome for Process Building | SLN-01-D-E-52-001 | [7 empty] | 0.88694
D | E |  |  | Lighting, FDA, Tel and Network System for Administrative Building | ANC-01-D-E-52-001 | [7 empty] | 0.67408
D | E |  |  | Lighting, FDA, Tel and Network System for Conteen, Prayer room & Locker and Shower | ANC-01-D-E-52-002 | [7 empty] | 0.67408
D | E |  |  | Lighting, FDA, Tel and Network System for Guard Building | ANC-01-D-E-52-003 | [7 empty] | 0.44939
D | E |  |  | Lighting, FDA, Tel and Network System for Toilet Building | ANC-01-D-E-52-004 | [7 empty] | 0.34295
D | E |  |  | Lighting, FDA, Tel and Network System for Bascule | ANC-01-D-E-52-005 | [7 empty] | 0.22469
D | E |  |  | Lighting, FDA, Tel and Network System for Repair Workshop | ANC-01-D-E-52-006 | [7 empty] | 0.34295
D | E |  |  | Lighting, FDA, Tel and Network System for Passage Post | GEN-01-D-E-52-001 | [7 empty] | 0.34295
D | E |  |  | Lighting, FDA, Tel and Network System for Electrical Room | GEN-01-D-E-52-002 | [7 empty] | 0.44939
D | E |  |  | Lighting System for Outdoor Area | GEN-01-D-E-52-003 | IFA | A | 98207-4-0018 | 2020-04-25 |  |  |  | 0.67408 | 70% |  | IFA | A | 98207-4-0018 | 2020-04-25
|  |  |  | Lighting System for Basic Road | GEN-01-D-E-52-004 | IFA | A | 98207-4-0018 | 2020-04-25 |  |  |  |  | 70% |  | IFA | A | 98207-4-0018 | 2020-04-25
|  |  |  | Lighting & Socket System-Lighting Panel LP01 | GEN-01-D-E-52-031 | IFA | A | 98207-4-0018 | 2020-04-25 |  |  |  |  | 70% |  | IFA | A | 98207-4-0018 | 2020-04-25
D | E |  |  | Bill of Material for Lighting, FDA, Tel and Network System | GEN-01-D-E-52-010 | [7 empty] | 0.55582
|  | Cabling System | [10 empty] | 2.8146 | 0%
D | E |  |  | Embedded Cable Way, Route and Section | GEN-01-D-E-32-001 | [7 empty] | 0.78051
D | E |  |  | Exposed Cable Way, Route and Section | GEN-01-D-E-33-001 | [7 empty] | 0.67408
D | E |  |  | Power Cable List | GEN-01-L-E-43-001 | [7 empty] | 0.67408
D | E |  |  | Bill of Material for Power Cables | GEN-01-D-E-43-010 | [7 empty] | 0.34295
D | E |  |  | Bill of Material for Cable Route and Bulk Material | GEN-01-D-E-33-010 | [7 empty] | 0.34295
|  | Electrical and Instrumentation for Process Water Systems | [10 empty] | 4.1391 | 0%
D | E |  |  | MCC Panel Single Line Diagram and Typical wiring for Process Water Systems | UTI-01-D-E-03-001 | [7 empty] | 0.73321
D | E |  |  | Cable Route for Process Water Systems | UTI-01-D-E-32-001 | [7 empty] | 0.44939
D | E |  |  | Lighting, FDA and Communication System for Process Water Systems | UTI-01-D-E-52-003 | [7 empty] | 0.44939
D | E |  |  | Instrument Datasheet for Process Water Systems | UTI-01-D-I-06-001 | [7 empty] | 0.73321
D | E |  |  | Power and Control Cable list for Process Water Systems | UTI-01-L-E-43-001 | [7 empty] | 0.66225
D | E |  |  | LCP Typical Wiring for Process Water Systems | UTI-01-D-E-L4-001 | [7 empty] | 0.33113
D | E |  |  | Junction Box Termination for Process Water Systems | UTI-01-D-I-13-001 | [7 empty] | 0.44939
D | E |  |  | Automation & Control Specification & BOM for Process Water Systems | UTI-01-D-I-13-010 | [7 empty] | 0.33113
|  | Electrical Panel | [10 empty] | 0.89877 | 35%
D | E |  |  | 20kV Panels Single Line Diagram | GEN-01-D-E-03-012 | IFA | A | 98207-4-0022 | 2020-04-28 |  |  |  | 0.44939 | 70% |  | IFA | A | 98207-4-0022 | 2020-04-28
D | E |  |  | Main Low Voltage Panels Single Line Diagram | GEN-01-D-E-03-013 | [7 empty] | 0.44939
D |  | Electrical Equipment Inquiry and Datasheet | [10 empty] | 0.44939 | 0%
D | E |  |  | Inquiy & Datasheet for Transformers | GEN-01-D-E-MA-001 | [7 empty] | 0.22469
D | E |  |  | Inquiy & Datasheet for UPS | GEN-01-D-E-MA-002 | [7 empty] | 0.22469
|  | Electrical Equipment Location | [10 empty] | 1.6911 | 23.5%
D | E |  |  | Passage post Layout | GEN-01-D-E-21-001 | IFA | A | 98207-4-0022 | 2020-04-28 |  |  |  | 0.56764 | 70% |  | IFA | A | 98207-4-0022 | 2020-04-28
D | E |  |  | Electrical Panel Location for Process Building | SLN-01-D-E-21-001 | [7 empty] | 0.67408
D | E |  |  | Electrical Equipment Location for Process Water Systems | UTI-01-D-E-21-001 | [7 empty] | 0.44939
|  | Earthing and Lightning System | [10 empty] | 1.9158 | 0%
D | E |  |  | Primary Earthing Layout | GEN-01-D-E-51-001 | [7 empty] | 0.67408
D | E |  |  | Typical Secondary Earthing System | GEN-01-D-E-51-002 | [7 empty] | 0.34295
D | E |  |  | Lightning System Layout | GEN-01-D-E-51-003 | [7 empty] | 0.55582
D | E |  |  | Bill of Material for Earthing and Lightning System | GEN-01-D-E-51-010 | [7 empty] | 0.34295
|  | Fire Alarm System | [10 empty] | 0.94607 | 0%
D | E |  |  | Fire Alarm System Layout | GEN-01-D-E-FA-001 | [7 empty] | 0.35478
D | E |  |  | Fire Alarm System Block Diagram | GEN-01-D-E-FA-002 | [7 empty] | 0.35478
D | E |  |  | Fire Alarm System BOM | GEN-01-D-E-FA-003 | [7 empty] | 0.23652
[9 empty] | Management and Project Control |  |  |  | 0.5913 | 100%
[9 empty] | Fluid Engineering |  |  |  | 22.4693 | 3.368%
[9 empty] | Civil & Structure |  |  |  | 55.7711 | 44.2%
[9 empty] | Electrical & Automation |  |  |  | 21.1684 | 5.592%
Formulas:
Date = IF([Date]<>"",[Date],IF([Date]<>"",[Date],IF([Date]<>"",[Date],IF([Date]<>"",[Date],""))))

## Cover E
|  |  |  | شماره قرارداد : |  |  | 980216
موضوع قرارداد: ارائه خدمات مشاوره، مدیریت طرح، طراحی، نظارت، کنترل پروژه و بازرسی طرح احداث خط نورد گرم لوله های بدون درز
شماره صورت وضعيت : |  |  | 3 | [10 empty] | تاريخ تهيه : | 1999-03-27
نوع صورت وضعيت: |  |  |  |  | موقت |  |  |  | قطعي |  |  | پيش پرداخت
دوره صورت وضعيت : |  |  | 1999-01-31 |  |  | لغایت |  | 1999-03-26
شرح صورت وضعيت : |  |  | صورت وضعیت موقت شماره 3
مبلغ كل قرارداد : |  |  | به حروف: |  | شش میلیارد و هشتصد میلیون ریال | [5 empty] | ريالي : |  | 6800000000 |  |  |  | ریال
رديف هاي WBS :
ارسال مدارک بیسیک و دیتیل در کلیه دیسیپلین ها
شرح |  |  |  |  | پيشرفت |  | مبلغ صورت وضعيت
ريالي (ريال )
تجمعي دوره قبل ( تاييد شده ) |  |  |  |  | 14.91% |  | 1013880000 | [10 empty] | 0
اين دوره |  |  |  |  | 11.07% |  | 752986130.5582
تجمعي تا كنون |  |  |  |  | 25.98% |  | 1766866130.5582
مبلغ صورت وضعيت دوره :
ریالی | عدد | 752986130.5582 | [13 empty] | ریال
| حروف | هتصد و پنجاه و دو میلیون و نهصد و هشتاد شش هزار و یکصد و سی و یک | [13 empty] | ریال
آدرس و تلفن مشاور :
اصفهان-شهرک علمی و تحقیقاتی خیابان 12 پلاک A211
مهر و امضاء پيمانكار | [9 empty] | مهر و امضاء كارفرما
* مستندات و مدارك لازم ضميمه صورت وضعيت مي باشد. * صورت وضعيت ارزش افزوده پس از نهايي شدن و پرداخت صورت وضعيت تهيه و براي كارفرما ارسال گردد.
مشاور:شرکت فراتحقیق سپاهان
کارفرما:شرکت فولاد تجارت طرق

## Invoice 01 (hidden)
Main Document Registry
Phase | Department | 1 | 2 | Document Title | Document No. | POI | Rev. | Transmittal No. | Date | W.F (%) | Progress | Contract Price
|  |  |  | Toroq Seamless Pipe Mill | [5 empty] | 100 | 7.353% | 6800000000 | 500028382.2138
Basic | [9 empty] | 19.5837 | 37.55% | 1331693472.0908 | 500028382.2138
| Management and Project Control | [8 empty] | 1.4191 | 83.33% | 96499526.9631 | 80416272.4693
B | P |  |  | Numbering Method | GEN-01-P-O-00-001 | IFI | C | 98207-4-0005 | 2020-02-17 | 0.5913 | 100% | 40208136.2346 | 40208136.2346
B | P |  |  | Coordination Procedure | GEN-01-P-O-00-002 | IFI | A | 98207-4-0002 | 2020-01-25 | 0.5913 | 100% | 40208136.2346 | 40208136.2346
B | P |  |  | Overall Time Schedule | [5 empty] | 0.23652 |  | 16083254.4939 | 0
| Fluid Engineering | [8 empty] | 2.4834 | 0% | 168874172.1854 | 0
B | M |  |  | Process Flow Diagram | GEN-01-D-U-01-001 |  |  |  |  | 2.4834 |  | 168874172.1854 | 0
| Civil & Structure | [8 empty] | 13.316 | 46.34% | 905487228.0038 | 419612109.7446
|  | General Basic | [7 empty] | 9.307 | 66.3% | 632876064.333 | 419612109.7446
B | C |  |  | General Layout | GEN-01-D-P-00-001 | IFC | 0 | 98207-4-0006 | 2020-02-17 | 3.0038 | 100% | 204257332.0719 | 204257332.0719
B | C |  |  | Access Roads | ROD-01-D-P-00-001~050 |  |  |  |  | 0.74503 |  | 50662251.6556 | 0
B | C |  |  | Water Draiange System | ROD-01-D-P-00-051~100 |  |  |  |  | 0.74503 |  | 50662251.6556 | 0
B | C |  |  | Rough Leveling | ROD-01-D-P-00-101~ |  |  |  |  | 0.74503 |  | 50662251.6556 | 0
B | C |  |  | MAIN SALOON AND STORAGE BASIC-SALOON SECTION | SLN-01-D-F-BA-001 | IFA | A | 98207-4-0004 | 2020-01-26 | 3.0038 | 70% | 204257332.0719 | 142980132.4503
|  |  |  | MAIN SALOON AND STORAGE BASIC-PLAN | SLN-01-D-F-BA-002 | IFA | A | 98207-4-0004 | 2020-01-26 |  | 70% | 0 | 0
B | C |  |  | Saloon Basic Report | SLN-01-R-F-BA-001 | IFI | A | 98207-4-0004 | 2020-01-26 | 1.0643 | 100% | 72374645.2223 | 72374645.2223
|  | Ancillary building | [7 empty] | 4.009 | 0% | 272611163.6708 | 0
B | C |  |  | Conteen, Prayer room & Locker and Shower | ANC-01-D-C-BL-001~010 |  |  |  |  | 1.0052 |  | 68353831.5989 | 0
B | C |  |  | Administrative | ANC-01-D-C-BL-010~020 |  |  |  |  | 1.5019 |  | 102128666.036 | 0
B | C |  |  | Guard house | ANC-01-D-C-BL-020~030 |  |  |  |  | 0.49669 |  | 33774834.4371 | 0
B | C |  |  | Repair Work Shop | ANC-01-D-C-BL-030~040 |  |  |  |  | 1.0052 |  | 68353831.5989 | 0
| Electrical & Automation | [8 empty] | 2.3652 | 0% | 160832544.9385 | 0
B | E |  |  | Overal Single Line Diagram | [5 empty] | 0.94607 |  | 64333017.9754 | 0
B | E |  |  | Load List | [5 empty] | 0.70956 |  | 48249763.4816 | 0
B | E |  |  | P&ID for Process Water Systems | [5 empty] | 0.70956 |  | 48249763.4816 | 0
Detail | [9 empty] | 80.4163 | 0% | 5468306527.9092 | 0
| Fluid Engineering | [8 empty] | 19.9858 | 0% | 1359035004.7304 | 0
|  | Piping Engineering | [7 empty] | 10.5842 | 0% | 719725638.5998 | 0
|  |  | Interconnecting Piping | [6 empty] | 4.7304 | 0% | 321665089.877 | 0
D | M |  |  | Piping Key Plan | GEN-01-D-U-11-002 |  |  |  |  | 1.5374 |  | 104541154.21 | 0
D | M |  |  | Piping Arrangement | GEN-01-D-U-21-003 |  |  |  |  | 1.4191 |  | 96499526.9631 | 0
D | M |  |  | Standard Pipe Support | GEN-01-D-U-43-004 |  |  |  |  | 1.1826 |  | 80416272.4693 | 0
D | M |  |  | Line List | GEN-01-L-U-63-005 |  |  |  |  | 0.5913 |  | 40208136.2346 | 0
|  |  | WTP (Pump Station, Cooling System) | [6 empty] | 3.4177 | 0% | 232403027.4361 | 0
D | M |  |  | Piping Arrangement | COO-01-D-U-21-006 |  |  |  |  | 3.4177 |  | 232403027.4361 | 0
|  |  | Material Take Off | [6 empty] | 1.1235 | 0% | 76395458.8458 | 0
D | M |  |  | MTO for Metal Piping | GEN-01-D-U-61-007 |  |  |  |  | 0.41391 |  | 28145695.3642 | 0
D | M |  |  | MTO for Non-Metal piping | GEN-01-D-U-61-008 |  |  |  |  | 0.41391 |  | 28145695.3642 | 0
D | M |  |  | Valve List | GEN-01-L-U-61-009 |  |  |  |  | 0.29565 |  | 20104068.1173 | 0
|  |  | ISO Metric Drawings | [6 empty] | 1.1235 | 0% | 76395458.8458 | 0
D | M |  |  | ISO Metric for Cooling Water | GEN-01-D-U-51-010 |  |  |  |  | 0.41391 |  | 28145695.3642 | 0
D | M |  |  | ISO Metric for Natural Gas | GEN-01-D-U-51-011 |  |  |  |  | 0.41391 |  | 28145695.3642 | 0
D | M |  |  | ISO Metric for Compressed Air | GEN-01-D-U-51-012 |  |  |  |  | 0.29565 |  | 20104068.1173 | 0
|  |  | Underground Piping | [6 empty] | 0.18921 | 0% | 12866603.5951 | 0
D | M |  |  | Underground Piping Arrangement | GEN-01-D-U-02-013 |  |  |  |  | 0.094607 |  | 6433301.7975 | 0
D | M |  |  | MTO for Underground Piping | GEN-01-D-U-61-014 |  |  |  |  | 0.094607 |  | 6433301.7975 | 0
|  | Utility Engineering | [7 empty] | 3.0747 | 0% | 209082308.4201 | 0
D | M |  |  | Equipment Arrangement For Cooling System | COO-01-D-U-11-015 |  |  |  |  | 0.23652 |  | 16083254.4939 | 0
D | M |  |  | Equipment List For Cooling System | COO-01-L-U-64-016 |  |  |  |  | 0.23652 |  | 16083254.4939 | 0
D | M |  |  | Sewage Collection Network | UTI-01-D-U-02-017 |  |  |  |  | 0.70956 |  | 48249763.4816 | 0
D | M |  |  | MTO for Sewage system | UTI-01-D-U-61-018 |  |  |  |  | 0.23652 |  | 16083254.4939 | 0
D | M |  |  | Firefighting System | UTI-01-D-U-11-019 |  |  |  |  | 0.23652 |  | 16083254.4939 | 0
D | M |  |  | Industrial Wastewater System | UTI-01-D-U-11-020 |  |  |  |  | 1.4191 |  | 96499526.9631 | 0
|  | HVAC Engineering | [7 empty] | 2.5426 | 0% | 172894985.8089 | 0
|  |  | Administrative Building | [6 empty] | 0.47304 | 0% | 32166508.9877 | 0
D | M |  |  | Cooling and Heating System | ANC-01-D-U-91-021 |  |  |  |  | 0.11826 |  | 8041627.2469 | 0
D | M |  |  | Ventilation System | ANC-01-D-U-91-022 |  |  |  |  | 0.11826 |  | 8041627.2469 | 0
D | M |  |  | Sewage System | ANC-01-D-U-91-023 |  |  |  |  | 0.11826 |  | 8041627.2469 | 0
D | M |  |  | Plumbing System | ANC-01-D-U-91-024 |  |  |  |  | 0.11826 |  | 8041627.2469 | 0
|  |  | Locker and Shower Building | [6 empty] | 0.47304 | 0% | 32166508.9877 | 0
D | M |  |  | Cooling and Heating System | ANC-01-D-U-91-025 |  |  |  |  | 0.11826 |  | 8041627.2469 | 0
D | M |  |  | Ventilation System | ANC-01-D-U-91-026 |  |  |  |  | 0.11826 |  | 8041627.2469 | 0
D | M |  |  | Sewage System | ANC-01-D-U-91-027 |  |  |  |  | 0.11826 |  | 8041627.2469 | 0
D | M |  |  | Plumbing System | ANC-01-D-U-91-028 |  |  |  |  | 0.11826 |  | 8041627.2469 | 0
|  |  | Conteen Building | [6 empty] | 0.35478 | 0% | 24124881.7408 | 0
D | M |  |  | Cooling and Heating System | ANC-01-D-U-91-029 |  |  |  |  | 0.094607 |  | 6433301.7975 | 0
D | M |  |  | Ventilation System | ANC-01-D-U-91-030 |  |  |  |  | 0.094607 |  | 6433301.7975 | 0
D | M |  |  | Sewage System | ANC-01-D-U-91-031 |  |  |  |  | 0.082781 |  | 5629139.0728 | 0
D | M |  |  | Plumbing System | ANC-01-D-U-91-032 |  |  |  |  | 0.082781 |  | 5629139.0728 | 0
|  |  | Guarde Building | [6 empty] | 0.29565 | 0% | 20104068.1173 | 0
D | M |  |  | Cooling and Heating System | ANC-01-D-U-91-033 |  |  |  |  | 0.082781 |  | 5629139.0728 | 0
D | M |  |  | Ventilation System | ANC-01-D-U-91-034 |  |  |  |  | 0.070956 |  | 4824976.3482 | 0
D | M |  |  | Sewage System | ANC-01-D-U-91-035 |  |  |  |  | 0.070956 |  | 4824976.3482 | 0
D | M |  |  | Plumbing System | ANC-01-D-U-91-036 |  |  |  |  | 0.070956 |  | 4824976.3482 | 0
|  |  | Process Building | [6 empty] | 0.94607 | 0% | 64333017.9754 | 0
D | M |  |  | Ventilation System | SLN-01-D-U-91-037 |  |  |  |  | 0.35478 |  | 24124881.7408 | 0
D | M |  |  | Sewage System | SLN-01-D-U-91-038 |  |  |  |  | 0.29565 |  | 20104068.1173 | 0
D | M |  |  | Plumbing System | SLN-01-D-U-91-039 |  |  |  |  | 0.29565 |  | 20104068.1173 | 0
|  | Inquiry Documents | [7 empty] | 3.7843 | 0% | 257332071.9016 | 0
|  |  | Utility | [6 empty] | 3.2876 | 0% | 223557237.4645 | 0
D | M |  |  | Inquiry & Data Sheet for RO System | COO-01-I-U-62-040 |  |  |  |  | 0.75686 |  | 51466414.3803 | 0
D | M |  |  | Inquiry & Data Sheet fot Cooling Tower | COO-01-I-U-62-041 |  |  |  |  | 0.5913 |  | 40208136.2346 | 0
D | M |  |  | Inquiry & Data Sheet for Water Pumps | COO-01-I-U-62-042 |  |  |  |  | 0.5913 |  | 40208136.2346 | 0
D | M |  |  | Inquiry & Data Sheet for Industrial Gas Racks | UTI-01-I-U-62-044 |  |  |  |  | 0.5913 |  | 40208136.2346 | 0
D | M |  |  | Inquiry & Data Sheet for Compressed Air System | UTI-01-I-U-62-043 |  |  |  |  | 0.75686 |  | 51466414.3803 | 0
|  |  | HVAC | [6 empty] | 0.49669 | 0% | 33774834.4371 | 0
D | M |  |  | Inquiry & Data Sheet for Package Unit | ANC-01-I-U-62-045 |  |  |  |  | 0.49669 |  | 33774834.4371 | 0
| Civil and Structure | [8 empty] | 41.6272 | 0% | 2830652790.9177 | 0
|  | Civil and St. St. | [7 empty] | 34.8628 | 0% | 2370671712.3936 | 0
|  |  | Main saloon & Storage | [6 empty] | 17.1358 | 0% | 1165231788.0795 | 0
D | C |  |  | Main saloon & Sotrage structure | SLN-01-D-S-E3-001 |  |  |  |  | 4.7304 |  | 321665089.877 | 0
D | C |  |  | Main saloon & Sotrage founation (Formwork) | SLN-01-D-C-EE-001 |  |  |  |  | 4.7304 |  | 321665089.877 | 0
D | C |  |  | Main saloon & Sotrage founation (Reinforcement) | SLN-01-D-C-EF-001 |  |  |  |  | 4.7304 |  | 321665089.877 | 0
D | C |  |  | Main saloon & Sotrage Pavement | SLN-01-D-C-EM-001 |  |  |  |  | 2.9447 |  | 200236518.4484 | 0
|  |  | Equipment Foundation | [6 empty] | 6.114 | 0% | 415752128.666 | 0
D | C |  |  | Cold disk saw (Formwork) | COL-01-D-C-EE-001 |  |  |  |  | 0.30747 |  | 20908230.842 | 0
D | C |  |  | Cold disk saw (Reinforcement) | COL-01-D-C-EF-001 |  |  |  |  | 0.30747 |  | 20908230.842 | 0
D | C |  |  | Heating furnace (Formwork) | HEA-01-D-C-EE-001 |  |  |  |  | 0.30747 |  | 20908230.842 | 0
D | C |  |  | Heating furnace (Reinforcement) | HEA-01-D-C-EF-001 |  |  |  |  | 0.30747 |  | 20908230.842 | 0
D | C |  |  | Piercing mill (Formwork) | PIE-01-D-C-EE-001 |  |  |  |  | 0.30747 |  | 20908230.842 | 0
D | C |  |  | Piercing mill (Reinforcement) | PIE-01-D-C-EF-001 |  |  |  |  | 0.30747 |  | 20908230.842 | 0
D | C |  |  | Elongator (Formwork) | ELO-01-D-C-EE-001 |  |  |  |  | 0.30747 |  | 20908230.842 | 0
D | C |  |  | Elongator (Reinforcement) | ELO-01-D-C-EF-001 |  |  |  |  | 0.30747 |  | 20908230.842 | 0
D | C |  |  | Inductive heater (Formwork) | IND-01-D-C-EE-001 |  |  |  |  | 0.30747 |  | 20908230.842 | 0
D | C |  |  | Inductive heater (Reinforcement) | IND-01-D-C-EF-001 |  |  |  |  | 0.30747 |  | 20908230.842 | 0
D | C |  |  | Sizing mill (Formwork) | SIZ-01-D-C-EE-001 |  |  |  |  | 0.30747 |  | 20908230.842 | 0
D | C |  |  | Sizing mill (Reinforcement) | SIZ-01-D-C-EF-001 |  |  |  |  | 0.30747 |  | 20908230.842 | 0
D | C |  |  | Cooling bed (Formwork) | COB-01-D-C-EE-001 |  |  |  |  | 0.30747 |  | 20908230.842 | 0
D | C |  |  | Cooling bed (Reinforcement) | COB-01-D-C-EF-001 |  |  |  |  | 0.30747 |  | 20908230.842 | 0
D | C |  |  | Fluid lubricantion system (Formwork) | FLU-01-D-C-EE-001 |  |  |  |  | 0.30747 |  | 20908230.842 | 0
D | C |  |  | Fluid lubricantion system (Reinforcement) | FLU-01-D-C-EF-001 |  |  |  |  | 0.30747 |  | 20908230.842 | 0
D | C |  |  | Grease lubricantion system (Formwork) | GRE-01-D-C-EE-001 |  |  |  |  | 0.30747 |  | 20908230.842 | 0
D | C |  |  | Grease lubricantion system (Reinforcement) | GRE-01-D-C-EF-001 |  |  |  |  | 0.29565 |  | 20104068.1173 | 0
D | C |  |  | Cooling system (Formwork) | COO-01-D-C-EE-001 |  |  |  |  | 0.29565 |  | 20104068.1173 | 0
D | C |  |  | Cooling system (Reinforcement) | COO-01-D-C-EF-001 |  |  |  |  | 0.29565 |  | 20104068.1173 | 0
|  |  | Ancillary building | [6 empty] | 3.9262 | 0% | 266982024.5979 | 0
D | C |  |  | Conteen, Prayer room & Locker and Shower (Formwork) | ANC-01-D-C-EE-001~010 |  |  |  |  | 0.5913 |  | 40208136.2346 | 0
D | C |  |  | Conteen, Prayer room & Locker and Shower (Reinforcement) | ANC-01-D-C-EF-001~010 |  |  |  |  | 0.5913 |  | 40208136.2346 | 0
D | C |  |  | Administrative (Formwork) | ANC-01-D-C-EE-011~020 |  |  |  |  | 0.5913 |  | 40208136.2346 | 0
D | C |  |  | Administrative (Reinforcement) | ANC-01-D-C-EF-011~020 |  |  |  |  | 0.5913 |  | 40208136.2346 | 0
D | C |  |  | Guard house (Formwork) | ANC-01-D-C-EE-021~030 |  |  |  |  | 0.18921 |  | 12866603.5951 | 0
D | C |  |  | Guard house (Reinforcement) | ANC-01-D-C-EF-021~030 |  |  |  |  | 0.20104 |  | 13670766.3198 | 0
D | C |  |  | Bascule (Formwork) | ANC-01-D-C-EE-031~040 |  |  |  |  | 0.094607 |  | 6433301.7975 | 0
D | C |  |  | Bascule (Reinforcement) | ANC-01-D-C-EF-031~040 |  |  |  |  | 0.094607 |  | 6433301.7975 | 0
D | C |  |  | Saloon Toilets | ANC-01-D-C-EE-041~050 |  |  |  |  | 0.18921 |  | 12866603.5951 | 0
D | C |  |  | Repair Work Shop | ANC-01-D-C-EE-051~060 |  |  |  |  | 0.79234 |  | 53878902.5544 | 0
|  |  | Auxiliary buildings | [6 empty] | 7.6868 | 0% | 522705771.0501 | 0
D | C |  |  | Passage post (Formwork) | UTI-01-D-C-EE-001~010 |  |  |  |  | 0.39026 |  | 26537369.9149 | 0
D | C |  |  | Passage post (Reinforcement) | UTI-01-D-C-EF-001~010 |  |  |  |  | 0.37843 |  | 25733207.1902 | 0
D | C |  |  | Electrical room (Formwork) | UTI-01-D-C-EE-011~050 |  |  |  |  | 1.1589 |  | 78807947.0199 | 0
D | C |  |  | Electrical room (Reinforcement) | UTI-01-D-C-EF-011~050 |  |  |  |  | 1.1471 |  | 78003784.2952 | 0
D | C |  |  | Strorage Tank (Formwork) | UTI-01-D-C-EE-061~100 |  |  |  |  | 0.39026 |  | 26537369.9149 | 0
D | C |  |  | Strorage Tank (Reinforcement) | UTI-01-D-C-EF-061~100 |  |  |  |  | 0.37843 |  | 25733207.1902 | 0
D | C |  |  | Compressor room (Formwork) | UTI-01-D-C-EE-101~150 |  |  |  |  | 0.39026 |  | 26537369.9149 | 0
D | C |  |  | Compressor room (Reinforcement) | UTI-01-D-C-EF-101~150 |  |  |  |  | 0.37843 |  | 25733207.1902 | 0
D | C |  |  | WTP Buildings (Formwork) | UTI-01-D-C-EE-151~400 |  |  |  |  | 1.5374 |  | 104541154.21 | 0
D | C |  |  | WTP Buildings (Reinforcement) | UTI-01-D-C-EF-151~400 |  |  |  |  | 1.5374 |  | 104541154.21 | 0
|  | Architectural | [7 empty] | 5.2507 | 0% | 357048249.7635 | 0
|  |  | Main saloon & Storage | [6 empty] | 4.281 | 0% | 291106906.3387 | 0
D | C |  |  | Main saloon & Storage | SLN-01-D-C-EL-001~020 |  |  |  |  | 4.281 |  | 291106906.3387 | 0
|  |  | Ancillary building | [6 empty] | 0.96973 | 0% | 65941343.4248 | 0
D | C |  |  | Conteen, Prayer room & Locker and Shower | ANC-01-D-C-EL-001~020 |  |  |  |  | 0.29565 |  | 20104068.1173 | 0
D | C |  |  | Administrative | ANC-01-D-C-EL-021~040 |  |  |  |  | 0.29565 |  | 20104068.1173 | 0
D | C |  |  | Guard house | ANC-01-D-C-EL-041~060 |  |  |  |  | 0.094607 |  | 6433301.7975 | 0
D | C |  |  | Bascule | ANC-01-D-C-EL-061~080 |  |  |  |  | 0.047304 |  | 3216650.8988 | 0
D | C |  |  | Saloon Toilets | ANC-01-D-C-EL-081~100 |  |  |  |  | 0.047304 |  | 3216650.8988 | 0
D | C |  |  | Repair Work Shop | ANC-01-D-C-EL-101~120 |  |  |  |  | 0.18921 |  | 12866603.5951 | 0
|  | Road and Landscape | [7 empty] | 1.5137 | 0% | 102932828.7606 | 0
D | C |  |  | Access Roads | ROD-01-D-C-DR-001~100 |  |  |  |  | 0.30747 |  | 20908230.842 | 0
D | C |  |  | Roads Plan & Profile | ROD-01-D-C-DR-100~200 |  |  |  |  | 0.30747 |  | 20908230.842 | 0
D | C |  |  | Roads Cross Section & volume Table | ROD-01-D-C-DR-200~300 |  |  |  |  | 0.30747 |  | 20908230.842 | 0
D | C |  |  | Water Draiange System | ROD-01-D-C-DW-001~100 |  |  |  |  | 0.29565 |  | 20104068.1173 | 0
D | C |  |  | Leveling & Coding | ROD-01-D-C-DS-001~100 |  |  |  |  | 0.29565 |  | 20104068.1173 | 0
| Electrical and Automation | [8 empty] | 18.8032 | 0% | 1278618732.2611 | 0
|  | Lighting and Low Current System | [7 empty] | 6.2677 | 0% | 426206244.087 | 0
D | E |  |  | Overall Lighting Block Diagram | GEN-01-D-E-52-020 |  |  |  |  | 0.17739 |  | 12062440.8704 | 0
D | E |  |  | Main Lighting Panel Single Line Diagram | GEN-01-D-E-52-030 |  |  |  |  | 0.17739 |  | 12062440.8704 | 0
D | E |  |  | Lighting, Fire Alarm, CCTV and Intercome for Process Saloon | SLN-01-D-E-52-001 |  |  |  |  | 0.94607 |  | 64333017.9754 | 0
D | E |  |  | Lighting, FDA, Tel and Network System for Administrative Building | ANC-01-D-E-52-001 |  |  |  |  | 0.70956 |  | 48249763.4816 | 0
D | E |  |  | Lighting, FDA, Tel and Network System for Conteen, Prayer room & Locker and Shower | ANC-01-D-E-52-002 |  |  |  |  | 0.70956 |  | 48249763.4816 | 0
D | E |  |  | Lighting, FDA, Tel and Network System for Guard Building | ANC-01-D-E-52-003 |  |  |  |  | 0.47304 |  | 32166508.9877 | 0
D | E |  |  | Lighting, FDA, Tel and Network System for Toilet Building | ANC-01-D-E-52-004 |  |  |  |  | 0.35478 |  | 24124881.7408 | 0
D | E |  |  | Lighting, FDA, Tel and Network System for Bascule | ANC-01-D-E-52-005 |  |  |  |  | 0.23652 |  | 16083254.4939 | 0
D | E |  |  | Lighting, FDA, Tel and Network System for Repair Workshop | ANC-01-D-E-52-006 |  |  |  |  | 0.35478 |  | 24124881.7408 | 0
D | E |  |  | Lighting, FDA, Tel and Network System for Passage Post | GEN-01-D-E-52-001 |  |  |  |  | 0.35478 |  | 24124881.7408 | 0
D | E |  |  | Lighting, FDA, Tel and Network System for Electrical Room | GEN-01-D-E-52-002 |  |  |  |  | 0.47304 |  | 32166508.9877 | 0
D | E |  |  | Lighting System for Outdoor Area | GEN-01-D-E-52-003 |  |  |  |  | 0.70956 |  | 48249763.4816 | 0
D | E |  |  | Bill of Material for Lighting, FDA, Tel and Network System | GEN-01-D-E-52-010 |  |  |  |  | 0.5913 |  | 40208136.2346 | 0
|  | Cabling System | [7 empty] | 2.9565 | 0% | 201040681.1731 | 0
D | E |  |  | Embedded Cable Way, Route and Section | GEN-01-D-E-32-001 |  |  |  |  | 0.82781 |  | 56291390.7285 | 0
D | E |  |  | Exposed Cable Way, Route and Section | GEN-01-D-E-33-001 |  |  |  |  | 0.70956 |  | 48249763.4816 | 0
D | E |  |  | Power Cable List | GEN-01-L-E-43-001 |  |  |  |  | 0.70956 |  | 48249763.4816 | 0
D | E |  |  | Bill of Material for Power Cables | GEN-01-D-E-43-010 |  |  |  |  | 0.35478 |  | 24124881.7408 | 0
D | E |  |  | Bill of Material for Cable Route and Bulk Material | GEN-01-D-E-33-010 |  |  |  |  | 0.35478 |  | 24124881.7408 | 0
|  | Electrical and Instrumentation for Process Water Systems | [7 empty] | 4.3756 | 0% | 297540208.1362 | 0
D | E |  |  | MCC Panel Single Line Diagram and Typical wiring for Process Water Systems | UTI-01-D-E-03-001 |  |  |  |  | 0.76868 |  | 52270577.105 | 0
D | E |  |  | Cable Route for Process Water Systems | UTI-01-D-E-32-001 |  |  |  |  | 0.47304 |  | 32166508.9877 | 0
D | E |  |  | Lighting, FDA and Communication System for Process Water Systems | UTI-01-D-E-52-003 |  |  |  |  | 0.47304 |  | 32166508.9877 | 0
D | E |  |  | Instrument Datasheet for Process Water Systems | UTI-01-D-I-06-001 |  |  |  |  | 0.76868 |  | 52270577.105 | 0
D | E |  |  | Power and Control Cable list for Process Water Systems | UTI-01-L-E-43-001 |  |  |  |  | 0.70956 |  | 48249763.4816 | 0
D | E |  |  | LCP Typical Wiring for Process Water Systems | UTI-01-D-E-L4-001 |  |  |  |  | 0.35478 |  | 24124881.7408 | 0
D | E |  |  | Junction Box Termination for Process Water Systems | UTI-01-D-I-13-001 |  |  |  |  | 0.47304 |  | 32166508.9877 | 0
D | E |  |  | Automation & Control Specification & BOM for Process Water Systems | UTI-01-D-I-13-010 |  |  |  |  | 0.35478 |  | 24124881.7408 | 0
|  | Electrical Panel | [7 empty] | 0.94607 | 0% | 64333017.9754 | 0
D | E |  |  | 20kV Panels Single Line Diagram | GEN-01-D-E-03-001 |  |  |  |  | 0.47304 |  | 32166508.9877 | 0
D | E |  |  | Main Low Voltage Panels Single Line Diagram | GEN-01-D-E-03-002 |  |  |  |  | 0.47304 |  | 32166508.9877 | 0
D |  | Electrical Equipment Inquiry and Datasheet | [7 empty] | 0.47304 | 0% | 32166508.9877 | 0
D | E |  |  | Inquiy & Datasheet for Transformers | GEN-01-D-E-MA-001 |  |  |  |  | 0.23652 |  | 16083254.4939 | 0
D | E |  |  | Inquiy & Datasheet for UPS | GEN-01-D-E-MA-002 |  |  |  |  | 0.23652 |  | 16083254.4939 | 0
|  | Electrical Equipment Location | [7 empty] | 1.7739 | 0% | 120624408.7039 | 0
D | E |  |  | Passage post Layout | GEN-01-D-E-21-001 |  |  |  |  | 0.5913 |  | 40208136.2346 | 0
D | E |  |  | Electrical Panel Location for Process Saloon | SLN-01-D-E-21-001 |  |  |  |  | 0.70956 |  | 48249763.4816 | 0
D | E |  |  | Electrical Equipment Location for Process Water Systems | UTI-01-D-E-21-001 |  |  |  |  | 0.47304 |  | 32166508.9877 | 0
|  | Earthing and Lightning System | [7 empty] | 2.0104 | 0% | 136707663.1977 | 0
D | E |  |  | Primary Earthing Layout | GEN-01-D-E-51-001 |  |  |  |  | 0.70956 |  | 48249763.4816 | 0
D | E |  |  | Typical Secondary Earthing System | GEN-01-D-E-51-002 |  |  |  |  | 0.35478 |  | 24124881.7408 | 0
D | E |  |  | Lightning System Layout | GEN-01-D-E-51-003 |  |  |  |  | 0.5913 |  | 40208136.2346 | 0
D | E |  |  | Bill of Material for Earthing and Lightning System | GEN-01-D-E-51-010 |  |  |  |  | 0.35478 |  | 24124881.7408 | 0

## Invoice 02
Invoice No. 02
Phase | Department | 1 | 2 | Document Title | Document No. | POI | Rev. | Transmittal No. | Date | W.F (%) | Progress | Contract Price | Invoice Amount
|  |  |  | Toroq Seamless Pipe Mill | [5 empty] | 100 | 21.08% | 6800000000 | 1433741721.8543
Basic | [9 empty] | 19.5837 | 46.16% | 1331693472.0908 | 614701986.755
| Management and Project Control | [8 empty] | 0.5913 | 100% | 40208136.2346 | 40208136.2346
B | P |  |  | Numbering Method | GEN-01-P-O-00-001 | IFI | C | 98207-4-0005 | 2020-02-17 | 0.23652 | 100% | 16083254.4939 | 16083254.4939
B | P |  |  | Coordination Procedure | GEN-01-P-O-00-002 | IFI | A | 98207-4-0002 | 2020-01-25 | 0.23652 | 100% | 16083254.4939 | 16083254.4939
B | P |  |  | Overall Time Schedule | GEN-01-P-O-00-003 | IFI | A | 98207-4-0015 | 2020-04-15 | 0.11826 | 100% | 8041627.2469 | 8041627.2469
| Fluid Engineering | [8 empty] | 2.4834 | 0% | 168874172.1854 | 0
B | M |  |  | Process Flow Diagram | GEN-01-D-U-01-001 |  |  |  |  | 1.7739 |  | 120624408.7039 | 0
B | M |  |  | Fire Fighting Concept | GEN-01-S-U-01-050 |  |  |  |  | 0.70956 |  | 48249763.4816 | 0
| Civil & Structure | [8 empty] | 14.1438 | 59.73% | 961778618.7323 | 574493850.5203
|  | General Basic | [7 empty] | 11.14 | 73.98% | 757521286.6604 | 560421002.8382
B | C |  |  | General Layout | GEN-01-D-P-00-001 | IFC | 1 | 98207-4-0009 | 2020-03-11 | 3.8907 | 100% | 264569536.4238 | 264569536.4238
B | C |  |  | Steel work general notes | GEN-01-S-S-GN-001 | IFA | A | 98207-4-0014 | 2020-04-15 | 0.47304 | 70% | 32166508.9877 | 22516556.2914
B | C |  |  | Civil work general notes | GEN-01-S-C-GN-001 | IFA | A | 98207-4-0014 | 2020-04-15 | 0.47304 | 70% | 32166508.9877 | 22516556.2914
B | C |  |  | Road Plan & Profile | ROD-01-D-C-DR-001 | IFA | A | 98207-4-0013 | 2020-04-13 | 0.74503 | 70% | 50662251.6556 | 35463576.1589
B | C |  |  | Site Condition | GEN-01-R-C-SC-001 |  |  |  |  | 0.74503 |  | 50662251.6556 | 0
B | C |  |  | Water Draiange System | ROD-01-D-C-00-051~100 |  |  |  |  | 0.74503 |  | 50662251.6556 | 0
B | C |  |  | MAIN Building & STORAGE BASIC |  | IFA | A | 98207-4-0007 | 2020-03-09 | 3.0038 | 70% | 204257332.0719 | 142980132.4503
|  |  |  | MAIN Building & STORAGE BASIC-PLAN | SLN-01-D-S-BA-001 | IFA | A | 98207-4-0007 | 2020-03-09 |  | 70% | 0 | 0
|  |  |  | MAIN Building & STORAGE BASIC-Building SECTION(2) | SLN-01-D-S-BA-002 | IFA | A | 98207-4-0007 | 2020-03-09 |  | 70% | 0 | 0
|  |  |  | MAIN Building & STORAGE BASIC-CRANE BEAMS & WALKWAY PLAN | SLN-01-D-S-BA-003 | IFA | A | 98207-4-0007 | 2020-03-09 |  |  | 0 | 0
|  |  |  | MAIN Building & STORAGE BASIC-FRAME PLAN | SLN-01-D-S-BA-004 | IFA | A | 98207-4-0007 | 2020-03-09 |  |  | 0 | 0
|  |  |  | MAIN Building & STORAGE BASIC-VIEWS | SLN-01-D-S-BA-005 | IFA | A | 98207-4-0007 | 2020-03-09 |  |  | 0 | 0
|  |  |  | MAIN Building & STORAGE BASIC-Building SECTION(1) | SLN-01-D-S-BA-006 | IFA | A | 98207-4-0007 | 2020-03-09 |  |  | 0 | 0
|  |  |  | MAIN Building & STORAGE BASIC-VIEW FOR AXIS 01&15 | SLN-01-D-S-BA-007 | IFA | A | 98207-4-0007 | 2020-03-09 |  |  | 0 | 0
|  |  |  | MAIN Building & STORAGE BASIC-CRANES ARRANGEMENT | SLN-01-D-S-BA-008 | IFA | A | 98207-4-0007 | 2020-03-09 |  |  | 0 | 0
B | C |  |  | Building Basic Report | SLN-01-R-F-BA-001 | IFI | A | 98207-4-0004 | 2020-01-26 | 1.0643 | 100% | 72374645.2223 | 72374645.2223
|  | Ancillary building | [7 empty] | 3.0038 | 6.89% | 204257332.0719 | 14072847.6821
B | C |  |  | Conteen, Prayer room & Locker and Shower | ANC-01-D-C-BL-001~010 |  |  |  |  | 0.6859 |  | 46641438.0322 | 0
B | C |  |  | Administrative | ANC-01-D-C-BL-010~020 |  |  |  |  | 1.0052 |  | 68353831.5989 | 0
B | C |  |  | Guard house | ANC-01-D-C-BL-020~030 |  |  |  |  | 0.34295 |  | 23320719.0161 | 0
B | C |  |  | Repair Work Shop | ANC-01-D-C-BL-030~040 |  |  |  |  | 0.67408 |  | 45837275.3075 | 0
| B |  |  | Initial estimation of ancillary building | ANC-01-R-C-BL-050 | IFI | A | 98207-4-0010 | 2020-03-11 | 0.29565 | 70% | 20104068.1173 | 14072847.6821
| Electrical & Automation | [8 empty] | 2.3652 | 0% | 160832544.9385 | 0
B | E |  |  | Overal Single Line Diagram | GEN-01-D-E-03-001 |  |  |  |  | 0.94607 |  | 64333017.9754 | 0
B | E |  |  | Load List | GEN-01-L-E-11-001 |  |  |  |  | 0.70956 |  | 48249763.4816 | 0
B | E |  |  | P&ID for Process Water Systems | GEN-01-D-I-01-001 |  |  |  |  | 0.70956 |  | 48249763.4816 | 0
Detail | [9 empty] | 80.4163 | 14.98% | 5468306527.9092 | 819039735.0993
| Fluid Engineering | [8 empty] | 19.9858 | 2.651% | 1359035004.7304 | 36026490.0662
|  | Piping Engineering | [7 empty] | 10.5842 | 0% | 719725638.5998 | 0
|  |  | Interconnecting Piping | [6 empty] | 4.7304 | 0% | 321665089.877 | 0
D | M |  |  | Piping Key Plan | GEN-01-D-U-11-002 |  |  |  |  | 1.5374 |  | 104541154.21 | 0
D | M |  |  | Piping Arrangement | GEN-01-D-U-21-003 |  |  |  |  | 1.4191 |  | 96499526.9631 | 0
D | M |  |  | Standard Pipe Support | GEN-01-D-U-43-004 |  |  |  |  | 1.1826 |  | 80416272.4693 | 0
D | M |  |  | Line List | GEN-01-L-U-63-005 |  |  |  |  | 0.5913 |  | 40208136.2346 | 0
|  |  | WTP (Pump Station, Cooling System) | [6 empty] | 3.1339 | 0% | 213103122.0435 | 0
D | M |  |  | Piping Arrangement | COO-01-D-U-21-006 |  |  |  |  | 3.1339 |  | 213103122.0435 | 0
|  |  | Material Take Off | [6 empty] | 1.1235 | 0% | 76395458.8458 | 0
D | M |  |  | MTO for Metal Piping | GEN-01-D-U-61-007 |  |  |  |  | 0.41391 |  | 28145695.3642 | 0
D | M |  |  | MTO for Non-Metal piping | GEN-01-D-U-61-008 |  |  |  |  | 0.41391 |  | 28145695.3642 | 0
D | M |  |  | Valve List | GEN-01-L-U-61-009 |  |  |  |  | 0.29565 |  | 20104068.1173 | 0
|  |  | ISO Metric Drawings | [6 empty] | 1.1235 | 0% | 76395458.8458 | 0
D | M |  |  | ISO Metric for Cooling Water | GEN-01-D-U-51-010 |  |  |  |  | 0.41391 |  | 28145695.3642 | 0
D | M |  |  | ISO Metric for Natural Gas | GEN-01-D-U-51-011 |  |  |  |  | 0.41391 |  | 28145695.3642 | 0
D | M |  |  | ISO Metric for Compressed Air | GEN-01-D-U-51-012 |  |  |  |  | 0.29565 |  | 20104068.1173 | 0
|  |  | Specification | [6 empty] | 0.28382 | 0% | 19299905.3926 | 0
D | M |  |  | Specification For Coating & Wrapping Of Underground Piping | GEN-01-S-U-10-046 |  |  |  |  | 0.094607 |  | 6433301.7975 | 0
D | M |  |  | Specification For Painting | GEN-01-S-U-10-047 |  |  |  |  | 0.094607 |  | 6433301.7975 | 0
D | M |  |  | Specification For Welding | GEN-01-S-U-10-048 |  |  |  |  | 0.094607 |  | 6433301.7975 | 0
|  |  | Underground Piping | [6 empty] | 0.18921 | 0% | 12866603.5951 | 0
D | M |  |  | Underground Piping Arrangement | GEN-01-D-U-02-013 |  |  |  |  | 0.094607 |  | 6433301.7975 | 0
D | M |  |  | MTO for Underground Piping | GEN-01-D-U-61-014 |  |  |  |  | 0.094607 |  | 6433301.7975 | 0
|  | Utility Engineering | [7 empty] | 3.0747 | 0% | 209082308.4201 | 0
D | M |  |  | Equipment Arrangement For Cooling System | COO-01-D-U-11-015 |  |  |  |  | 0.23652 |  | 16083254.4939 | 0
D | M |  |  | Equipment List For Cooling System | COO-01-L-U-64-016 |  |  |  |  | 0.23652 |  | 16083254.4939 | 0
D | M |  |  | Sewage Collection Network | UTI-01-D-U-02-017 |  |  |  |  | 0.70956 |  | 48249763.4816 | 0
D | M |  |  | MTO for Sewage system | UTI-01-D-U-61-018 |  |  |  |  | 0.23652 |  | 16083254.4939 | 0
D | M |  |  | Utitlity Consumption List | UTI-01-L-U-09-049 |  |  |  |  | 0.11826 |  | 8041627.2469 | 0
D | M |  |  | Firefighting System | UTI-01-D-U-11-019 |  |  |  |  | 0.23652 |  | 16083254.4939 | 0
D | M |  |  | Industrial Wastewater System | UTI-01-D-U-11-020 |  |  |  |  | 1.3009 |  | 88457899.7162 | 0
|  | HVAC Engineering | [7 empty] | 2.5426 | 0% | 172894985.8089 | 0
|  |  | Administrative Building | [6 empty] | 0.47304 | 0% | 32166508.9877 | 0
D | M |  |  | Cooling and Heating System | ANC-01-D-U-91-021 |  |  |  |  | 0.11826 |  | 8041627.2469 | 0
D | M |  |  | Ventilation System | ANC-01-D-U-91-022 |  |  |  |  | 0.11826 |  | 8041627.2469 | 0
D | M |  |  | Sewage System | ANC-01-D-U-91-023 |  |  |  |  | 0.11826 |  | 8041627.2469 | 0
D | M |  |  | Plumbing System | ANC-01-D-U-91-024 |  |  |  |  | 0.11826 |  | 8041627.2469 | 0
|  |  | Locker and Shower Building | [6 empty] | 0.47304 | 0% | 32166508.9877 | 0
D | M |  |  | Cooling and Heating System | ANC-01-D-U-91-025 |  |  |  |  | 0.11826 |  | 8041627.2469 | 0
D | M |  |  | Ventilation System | ANC-01-D-U-91-026 |  |  |  |  | 0.11826 |  | 8041627.2469 | 0
D | M |  |  | Sewage System | ANC-01-D-U-91-027 |  |  |  |  | 0.11826 |  | 8041627.2469 | 0
D | M |  |  | Plumbing System | ANC-01-D-U-91-028 |  |  |  |  | 0.11826 |  | 8041627.2469 | 0
|  |  | Conteen Building | [6 empty] | 0.35478 | 0% | 24124881.7408 | 0
D | M |  |  | Cooling and Heating System | ANC-01-D-U-91-029 |  |  |  |  | 0.094607 |  | 6433301.7975 | 0
D | M |  |  | Ventilation System | ANC-01-D-U-91-030 |  |  |  |  | 0.094607 |  | 6433301.7975 | 0
D | M |  |  | Sewage System | ANC-01-D-U-91-031 |  |  |  |  | 0.082781 |  | 5629139.0728 | 0
D | M |  |  | Plumbing System | ANC-01-D-U-91-032 |  |  |  |  | 0.082781 |  | 5629139.0728 | 0
|  |  | Guarde Building | [6 empty] | 0.29565 | 0% | 20104068.1173 | 0
D | M |  |  | Cooling and Heating System | ANC-01-D-U-91-033 |  |  |  |  | 0.082781 |  | 5629139.0728 | 0
D | M |  |  | Ventilation System | ANC-01-D-U-91-034 |  |  |  |  | 0.070956 |  | 4824976.3482 | 0
D | M |  |  | Sewage System | ANC-01-D-U-91-035 |  |  |  |  | 0.070956 |  | 4824976.3482 | 0
D | M |  |  | Plumbing System | ANC-01-D-U-91-036 |  |  |  |  | 0.070956 |  | 4824976.3482 | 0
|  |  | Process Building | [6 empty] | 0.94607 | 0% | 64333017.9754 | 0
D | M |  |  | Ventilation System | SLN-01-D-U-91-037 |  |  |  |  | 0.35478 |  | 24124881.7408 | 0
D | M |  |  | Sewage System | SLN-01-D-U-91-038 |  |  |  |  | 0.29565 |  | 20104068.1173 | 0
D | M |  |  | Plumbing System | SLN-01-D-U-91-039 |  |  |  |  | 0.29565 |  | 20104068.1173 | 0
|  | Inquiry Documents | [7 empty] | 3.7843 | 14% | 257332071.9016 | 36026490.0662
|  |  | Utility | [6 empty] | 3.2876 | 16.12% | 223557237.4645 | 36026490.0662
D | M |  |  | Inquiry & Data Sheet for RO System | COO-01-I-U-62-040 | IFI | A | 98207-4-0008 | 2020-03-09 | 0.75686 | 70% | 51466414.3803 | 36026490.0662
D | M |  |  | Inquiry & Data Sheet fot Cooling Tower | COO-01-I-U-62-041 |  |  |  |  | 0.5913 |  | 40208136.2346 | 0
D | M |  |  | Inquiry & Data Sheet for Water Pumps | COO-01-I-U-62-042 |  |  |  |  | 0.5913 |  | 40208136.2346 | 0
D | M |  |  | Inquiry & Data Sheet for Industrial Gas Racks | UTI-01-I-U-62-044 |  |  |  |  | 0.5913 |  | 40208136.2346 | 0
D | M |  |  | Inquiry & Data Sheet for Compressed Air System | UTI-01-I-U-62-043 |  |  |  |  | 0.75686 |  | 51466414.3803 | 0
|  |  | HVAC | [6 empty] | 0.49669 | 0% | 33774834.4371 | 0
D | M |  |  | Inquiry & Data Sheet for Package Unit | ANC-01-I-U-62-045 |  |  |  |  | 0.49669 |  | 33774834.4371 | 0
| Civil and Structure | [8 empty] | 41.6272 | 27.66% | 2830652790.9177 | 783013245.0331
|  | Civil and St. St. | [7 empty] | 34.8628 | 32.44% | 2370671712.3936 | 768940397.351
|  |  | Main Building & Storage | [6 empty] | 17.1358 | 65.99% | 1165231788.0795 | 768940397.351
D | C |  |  | Main Building & Storage structure | SLN-01-D-S-E3-001 | IFA | A | 98207-4-0011 | 2020-03-24 | 9.4607 | 70% | 643330179.754 | 450331125.8278
|  |  |  | MAIN SALOON & STORAGE-GRID 1 , 15 | SLN-01-D-S-E3-002 | IFA | A | 98207-4-0011 | 2020-03-24 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-GRID 2 ,3,4,5,6,9,10,11,12,13,14 | SLN-01-D-S-E3-003 | IFA | A | 98207-4-0011 | 2020-03-24 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-GRID 7 , 8 | SLN-01-D-S-E3-004 | IFA | A | 98207-4-0011 | 2020-03-24 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-GRID A , B , C | SLN-01-D-S-E3-005 | IFA | A | 98207-4-0011 | 2020-03-24 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-PLAN +9.000 ( CRANE BEAMS & WALKWAY PLAN ) | SLN-01-D-S-E3-006 | IFA | A | 98207-4-0011 | 2020-03-24 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-GRID 1a, 2a ,. 3a , 4a , 5a , 6a , 9a , 10a | SLN-01-D-S-E3-007 | IFA | A | 98207-4-0011 | 2020-03-24 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-FRAMES PLAN | SLN-01-D-S-E3-008 | IFA | A | 98207-4-0011 | 2020-03-24 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE- ROOF BRACING PLAN | SLN-01-D-S-E3-009 | IFA | A | 98207-4-0011 | 2020-03-24 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-ROOF BEAM | SLN-01-D-S-E3-010 | IFA | A | 98207-4-0011 | 2020-03-24 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR1 | SLN-01-D-S-E3-015 | IFA | A | 98207-4-0011 | 2020-03-24 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR1 | SLN-01-D-S-E3-016 | IFA | A | 98207-4-0011 | 2020-03-24 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR2 | SLN-01-D-S-E3-020 | IFA | A | 98207-4-0011 | 2020-03-24 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR2 | SLN-01-D-S-E3-021 | IFA | A | 98207-4-0011 | 2020-03-24 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR3,5 | SLN-01-D-S-E3-025 | IFA | A | 98207-4-0011 | 2020-03-24 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR4 | SLN-01-D-S-E3-028 | IFA | A | 98207-4-0011 | 2020-03-24 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR4 | SLN-01-D-S-E3-029 | IFA | A | 98207-4-0011 | 2020-03-24 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR6 | SLN-01-D-S-E3-032 | IFA | A | 98207-4-0011 | 2020-03-24 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR6 | SLN-01-D-S-E3-033 | IFA | A | 98207-4-0011 | 2020-03-24 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR7 | SLN-01-D-S-E3-036 | IFA | A | 98207-4-0011 | 2020-03-24 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR7 | SLN-01-D-S-E3-037 | IFA | A | 98207-4-0011 | 2020-03-24 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR8 | SLN-01-D-S-E3-040 | IFA | A | 98207-4-0011 | 2020-03-24 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR8 | SLN-01-D-S-E3-041 | IFA | A | 98207-4-0011 | 2020-03-24 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-BEAM B1 , B2 , B3 , B4 | SLN-01-D-S-E3-045 | IFA | A | 98207-4-0011 | 2020-03-24 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-COLUMN 1 | SLN-01-D-S-E3-050 | IFA | A | 98207-4-0011 | 2020-03-24 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-COLUMN 2 | SLN-01-D-S-E3-052 | IFA | A | 98207-4-0011 | 2020-03-24 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-RAFTER | SLN-01-D-S-E3-053 | IFA | A | 98207-4-0011 | 2020-03-24 |  | 70% | 0 | 0
D | C |  |  | MAIN BUILDING & STORAGE FOUNDATION-EXCAVATION PLAN | SLN-01-D-C-EE-001 | IFA | A | 98207-4-0014 | 2020-04-15 | 2.3652 | 70% | 160832544.9385 | 112582781.457
|  |  |  | MAIN BUILDING & STORAGE FOUNDATION-FOUNDATIONS PLAN | SLN-01-D-C-EE-002 | [6 empty] | 0 | 0
|  |  |  | MAIN BUILDING & STORAGE FOUNDATION-FOUNDATIONS FORMWORK | SLN-01-D-C-EE-003 | [6 empty] | 0 | 0
|  |  |  | MAIN BUILDING & STORAGE FOUNDATION-ANCHOR "2A-056" DETAILS | SLN-01-D-C-EE-004 | [6 empty] | 0 | 0
D | C |  |  | MAIN BUILDING & STORAGE FOUNDATION-FOUNDATON "F1"REINFORCEMENT | SLN-01-D-C-EF-001 | IFA | A | 98207-4-0014 | 2020-04-15 | 2.3652 | 70% | 160832544.9385 | 112582781.457
|  |  |  | MAIN BUILDING & STORAGE FOUNDATION-FOUNDATON "F1"REINFORCEMENT | SLN-01-D-C-EF-002 | [6 empty] | 0 | 0
D | C |  |  | Main Building & Storage MTO | SLN-01-D-C-MT-001 | IFA | A | 98207-4-0011 | 2020-03-24 | 0.98155 | 70% | 66745506.1495 | 46721854.3046
D | C |  |  | Main Building & Storage Pavement | SLN-01-D-C-EM-001 |  |  |  |  | 0.98155 |  | 66745506.1495 | 0
D | C |  |  | Main Building & Storge Calculation sheet | SLN-01-C-S-CA-001 | IFA | A | 98207-4-0012 | 2020-04-04 | 0.98155 | 70% | 66745506.1495 | 46721854.3046
|  |  | Equipment Foundation | [6 empty] | 6.114 | 0% | 415752128.666 | 0
D | C |  |  | Cold disk saw (Formwork) | COL-01-D-C-EE-001 |  |  |  |  | 0.29565 |  | 20104068.1173 | 0
D | C |  |  | Cold disk saw (Reinforcement) | COL-01-D-C-EF-001 |  |  |  |  | 0.28382 |  | 19299905.3926 | 0
D | C |  |  | Heating furnace (Formwork) | HEA-01-D-C-EE-001 |  |  |  |  | 0.28382 |  | 19299905.3926 | 0
D | C |  |  | Heating furnace (Reinforcement) | HEA-01-D-C-EF-001 |  |  |  |  | 0.28382 |  | 19299905.3926 | 0
D | C |  |  | Piercing mill (Formwork) | PIE-01-D-C-EE-001 |  |  |  |  | 0.28382 |  | 19299905.3926 | 0
D | C |  |  | Piercing mill (Reinforcement) | PIE-01-D-C-EF-001 |  |  |  |  | 0.28382 |  | 19299905.3926 | 0
D | C |  |  | Elongator (Formwork) | ELO-01-D-C-EE-001 |  |  |  |  | 0.28382 |  | 19299905.3926 | 0
D | C |  |  | Elongator (Reinforcement) | ELO-01-D-C-EF-001 |  |  |  |  | 0.28382 |  | 19299905.3926 | 0
D | C |  |  | Inductive heater (Formwork) | IND-01-D-C-EE-001 |  |  |  |  | 0.28382 |  | 19299905.3926 | 0
D | C |  |  | Inductive heater (Reinforcement) | IND-01-D-C-EF-001 |  |  |  |  | 0.28382 |  | 19299905.3926 | 0
D | C |  |  | Sizing mill (Formwork) | SIZ-01-D-C-EE-001 |  |  |  |  | 0.28382 |  | 19299905.3926 | 0
D | C |  |  | Sizing mill (Reinforcement) | SIZ-01-D-C-EF-001 |  |  |  |  | 0.28382 |  | 19299905.3926 | 0
D | C |  |  | Cooling bed (Formwork) | COB-01-D-C-EE-001 |  |  |  |  | 0.28382 |  | 19299905.3926 | 0
D | C |  |  | Cooling bed (Reinforcement) | COB-01-D-C-EF-001 |  |  |  |  | 0.28382 |  | 19299905.3926 | 0
D | C |  |  | Fluid lubricantion system (Formwork) | FLU-01-D-C-EE-001 |  |  |  |  | 0.28382 |  | 19299905.3926 | 0
D | C |  |  | Fluid lubricantion system (Reinforcement) | FLU-01-D-C-EF-001 |  |  |  |  | 0.28382 |  | 19299905.3926 | 0
D | C |  |  | Grease lubricantion system (Formwork) | GRE-01-D-C-EE-001 |  |  |  |  | 0.28382 |  | 19299905.3926 | 0
D | C |  |  | Grease lubricantion system (Reinforcement) | GRE-01-D-C-EF-001 |  |  |  |  | 0.28382 |  | 19299905.3926 | 0
D | C |  |  | Cooling system (Formwork) | COO-01-D-C-EE-001 |  |  |  |  | 0.28382 |  | 19299905.3926 | 0
D | C |  |  | Cooling system (Reinforcement) | COO-01-D-C-EF-001 |  |  |  |  | 0.28382 |  | 19299905.3926 | 0
D | C |  |  | Calculation Report for Foundations | GEN-01-D-C-CA-001 |  |  |  |  | 0.42573 |  | 28949858.0889 | 0
|  |  | Ancillary building | [6 empty] | 3.9262 | 0% | 266982024.5979 | 0
D | C |  |  | Conteen, Prayer room & Locker and Shower (Formwork) | ANC-01-D-C-EE-001~010 |  |  |  |  | 0.54399 |  | 36991485.3359 | 0
D | C |  |  | Conteen, Prayer room & Locker and Shower (Reinforcement) | ANC-01-D-C-EF-001~010 |  |  |  |  | 0.54399 |  | 36991485.3359 | 0
D | C |  |  | Administrative (Formwork) | ANC-01-D-C-EE-011~020 |  |  |  |  | 0.54399 |  | 36991485.3359 | 0
D | C |  |  | Administrative (Reinforcement) | ANC-01-D-C-EF-011~020 |  |  |  |  | 0.54399 |  | 36991485.3359 | 0
D | C |  |  | Guard house (Formwork) | ANC-01-D-C-EE-021~030 |  |  |  |  | 0.17739 |  | 12062440.8704 | 0
D | C |  |  | Guard house (Reinforcement) | ANC-01-D-C-EF-021~030 |  |  |  |  | 0.18921 |  | 12866603.5951 | 0
D | C |  |  | Bascule (Formwork) | ANC-01-D-C-EE-031~040 |  |  |  |  | 0.094607 |  | 6433301.7975 | 0
D | C |  |  | Bascule (Reinforcement) | ANC-01-D-C-EF-031~040 |  |  |  |  | 0.094607 |  | 6433301.7975 | 0
D | C |  |  | Building Toilets | ANC-01-D-C-EE-041~050 |  |  |  |  | 0.17739 |  | 12062440.8704 | 0
D | C |  |  | Repair Work Shop | ANC-01-D-C-EE-051~060 |  |  |  |  | 0.57947 |  | 39403973.5099 | 0
D | C |  |  | Laboratory (Formwork) | ANC-01-D-C-EE-061~070 |  |  |  |  | 0.082781 |  | 5629139.0728 | 0
D | C |  |  | Laboratory (Reinforcement) | ANC-01-D-C-EF-061~070 |  |  |  |  | 0.082781 |  | 5629139.0728 | 0
D | C |  |  | Calculation Report for Ancillary building | ANC-01-D-C-CA-001 |  |  |  |  | 0.272 |  | 18495742.6679 | 0
|  |  | Auxiliary buildings & FDN | [6 empty] | 7.6868 | 0% | 522705771.0501 | 0
D | C |  |  | Passage post (Formwork) | UTI-01-D-C-EE-001~010 |  |  |  |  | 0.35478 |  | 24124881.7408 | 0
D | C |  |  | Passage post (Reinforcement) | UTI-01-D-C-EF-001~010 |  |  |  |  | 0.35478 |  | 24124881.7408 | 0
D | C |  |  | Electrical room (Formwork) | UTI-01-D-C-EE-011~050 |  |  |  |  | 1.0762 |  | 73178807.947 | 0
D | C |  |  | Electrical room (Reinforcement) | UTI-01-D-C-EF-011~050 |  |  |  |  | 1.0643 |  | 72374645.2223 | 0
D | C |  |  | Strorage Tank (Formwork) | UTI-01-D-C-EE-061~100 |  |  |  |  | 0.3666 |  | 24929044.4655 | 0
D | C |  |  | Strorage Tank (Reinforcement) | UTI-01-D-C-EF-061~100 |  |  |  |  | 0.35478 |  | 24124881.7408 | 0
D | C |  |  | Compressor room (Formwork) | UTI-01-D-C-EE-101~150 |  |  |  |  | 0.3666 |  | 24929044.4655 | 0
D | C |  |  | Compressor room (Reinforcement) | UTI-01-D-C-EF-101~150 |  |  |  |  | 0.35478 |  | 24124881.7408 | 0
D | C |  |  | WTP Buildings (Formwork) | UTI-01-D-C-EE-151~400 |  |  |  |  | 1.4309 |  | 97303689.6878 | 0
D | C |  |  | WTP Buildings (Reinforcement) | UTI-01-D-C-EF-151~400 |  |  |  |  | 1.4309 |  | 97303689.6878 | 0
D | C |  |  | Calculation Report for Auxiliary buildings | UTI-01-D-C-CA-001 |  |  |  |  | 0.53217 |  | 36187322.6112 | 0
|  | Architectural | [7 empty] | 5.2507 | 0% | 357048249.7635 | 0
|  |  | Main Building & Storage | [6 empty] | 4.281 | 0% | 291106906.3387 | 0
D | C |  |  | Main Building & Storage | SLN-01-D-C-EL-001~020 |  |  |  |  | 3.7843 |  | 257332071.9016 | 0
D | C |  |  | SITE PLAN | GEN-01-D-C-EL-0011 |  |  |  |  | 0.49669 |  | 33774834.4371 | 0
|  |  | Ancillary building | [6 empty] | 0.96973 | 0% | 65941343.4248 | 0
D | C |  |  | Conteen, Prayer room & Locker and Shower | ANC-01-D-C-EL-001~020 |  |  |  |  | 0.29565 |  | 20104068.1173 | 0
D | C |  |  | Administrative | ANC-01-D-C-EL-021~040 |  |  |  |  | 0.29565 |  | 20104068.1173 | 0
D | C |  |  | Guard house | ANC-01-D-C-EL-041~060 |  |  |  |  | 0.094607 |  | 6433301.7975 | 0
D | C |  |  | Bascule | ANC-01-D-C-EL-061~080 |  |  |  |  | 0.047304 |  | 3216650.8988 | 0
D | C |  |  | Building Toilets | ANC-01-D-C-EL-081~100 |  |  |  |  | 0.047304 |  | 3216650.8988 | 0
D | C |  |  | Repair Work Shop | ANC-01-D-C-EL-101~120 |  |  |  |  | 0.15374 |  | 10454115.421 | 0
D | C |  |  | Laboratory | ANC-01-D-C-EL-121~130 |  |  |  |  | 0.035478 |  | 2412488.1741 | 0
|  | Road and Landscape | [7 empty] | 1.5137 | 13.67% | 102932828.7606 | 14072847.6821
D | C |  |  | Access Roads | ROD-01-D-C-DR-001~100 |  |  |  |  | 0.30747 |  | 20908230.842 | 0
D | C |  |  | Roads Plan & Profile | ROD-01-D-C-DR-100~200 |  |  |  |  | 0.30747 |  | 20908230.842 | 0
D | C |  |  | Roads Cross Section & volume Table | ROD-01-D-C-DR-200~300 |  |  |  |  | 0.30747 |  | 20908230.842 | 0
D | C |  |  | Water Draiange System | ROD-01-D-C-DW-001~100 | IFA | A | 98207-4-0016 | 2020-04-18 | 0.29565 | 70% | 20104068.1173 | 14072847.6821
D | C |  |  | Leveling & Coding | ROD-01-D-C-DS-001~100 |  |  |  |  | 0.29565 |  | 20104068.1173 | 0
| Electrical and Automation | [8 empty] | 18.8032 | 0% | 1278618732.2611 | 0
|  | Lighting and Low Current System | [7 empty] | 5.9484 | 0% | 404493850.5203 | 0
D | E |  |  | Overall Lighting Block Diagram | GEN-01-D-E-52-020 |  |  |  |  | 0.16556 |  | 11258278.1457 | 0
D | E |  |  | Main Lighting Panel Single Line Diagram | GEN-01-D-E-52-030 |  |  |  |  | 0.16556 |  | 11258278.1457 | 0
D | E |  |  | Lighting, Fire Alarm, CCTV and Intercome for Process Building | SLN-01-D-E-52-001 |  |  |  |  | 0.88694 |  | 60312204.3519 | 0
D | E |  |  | Lighting, FDA, Tel and Network System for Administrative Building | ANC-01-D-E-52-001 |  |  |  |  | 0.67408 |  | 45837275.3075 | 0
D | E |  |  | Lighting, FDA, Tel and Network System for Conteen, Prayer room & Locker and Shower | ANC-01-D-E-52-002 |  |  |  |  | 0.67408 |  | 45837275.3075 | 0
D | E |  |  | Lighting, FDA, Tel and Network System for Guard Building | ANC-01-D-E-52-003 |  |  |  |  | 0.44939 |  | 30558183.5383 | 0
D | E |  |  | Lighting, FDA, Tel and Network System for Toilet Building | ANC-01-D-E-52-004 |  |  |  |  | 0.34295 |  | 23320719.0161 | 0
D | E |  |  | Lighting, FDA, Tel and Network System for Bascule | ANC-01-D-E-52-005 |  |  |  |  | 0.22469 |  | 15279091.7692 | 0
D | E |  |  | Lighting, FDA, Tel and Network System for Repair Workshop | ANC-01-D-E-52-006 |  |  |  |  | 0.34295 |  | 23320719.0161 | 0
D | E |  |  | Lighting, FDA, Tel and Network System for Passage Post | GEN-01-D-E-52-001 |  |  |  |  | 0.34295 |  | 23320719.0161 | 0
D | E |  |  | Lighting, FDA, Tel and Network System for Electrical Room | GEN-01-D-E-52-002 |  |  |  |  | 0.44939 |  | 30558183.5383 | 0
D | E |  |  | Lighting System for Outdoor Area | GEN-01-D-E-52-003 |  |  |  |  | 0.67408 |  | 45837275.3075 | 0
D | E |  |  | Bill of Material for Lighting, FDA, Tel and Network System | GEN-01-D-E-52-010 |  |  |  |  | 0.55582 |  | 37795648.0605 | 0
|  | Cabling System | [7 empty] | 2.8146 | 0% | 191390728.4768 | 0
D | E |  |  | Embedded Cable Way, Route and Section | GEN-01-D-E-32-001 |  |  |  |  | 0.78051 |  | 53074739.8297 | 0
D | E |  |  | Exposed Cable Way, Route and Section | GEN-01-D-E-33-001 |  |  |  |  | 0.67408 |  | 45837275.3075 | 0
D | E |  |  | Power Cable List | GEN-01-L-E-43-001 |  |  |  |  | 0.67408 |  | 45837275.3075 | 0
D | E |  |  | Bill of Material for Power Cables | GEN-01-D-E-43-010 |  |  |  |  | 0.34295 |  | 23320719.0161 | 0
D | E |  |  | Bill of Material for Cable Route and Bulk Material | GEN-01-D-E-33-010 |  |  |  |  | 0.34295 |  | 23320719.0161 | 0
|  | Electrical and Instrumentation for Process Water Systems | [7 empty] | 4.1391 | 0% | 281456953.6424 | 0
D | E |  |  | MCC Panel Single Line Diagram and Typical wiring for Process Water Systems | UTI-01-D-E-03-001 |  |  |  |  | 0.73321 |  | 49858088.9309 | 0
D | E |  |  | Cable Route for Process Water Systems | UTI-01-D-E-32-001 |  |  |  |  | 0.44939 |  | 30558183.5383 | 0
D | E |  |  | Lighting, FDA and Communication System for Process Water Systems | UTI-01-D-E-52-003 |  |  |  |  | 0.44939 |  | 30558183.5383 | 0
D | E |  |  | Instrument Datasheet for Process Water Systems | UTI-01-D-I-06-001 |  |  |  |  | 0.73321 |  | 49858088.9309 | 0
D | E |  |  | Power and Control Cable list for Process Water Systems | UTI-01-L-E-43-001 |  |  |  |  | 0.66225 |  | 45033112.5828 | 0
D | E |  |  | LCP Typical Wiring for Process Water Systems | UTI-01-D-E-L4-001 |  |  |  |  | 0.33113 |  | 22516556.2914 | 0
D | E |  |  | Junction Box Termination for Process Water Systems | UTI-01-D-I-13-001 |  |  |  |  | 0.44939 |  | 30558183.5383 | 0
D | E |  |  | Automation & Control Specification & BOM for Process Water Systems | UTI-01-D-I-13-010 |  |  |  |  | 0.33113 |  | 22516556.2914 | 0
|  | Electrical Panel | [7 empty] | 0.89877 | 0% | 61116367.0766 | 0
D | E |  |  | 20kV Panels Single Line Diagram | GEN-01-D-E-03-012 |  |  |  |  | 0.44939 |  | 30558183.5383 | 0
D | E |  |  | Main Low Voltage Panels Single Line Diagram | GEN-01-D-E-03-013 |  |  |  |  | 0.44939 |  | 30558183.5383 | 0
D |  | Electrical Equipment Inquiry and Datasheet | [7 empty] | 0.44939 | 0% | 30558183.5383 | 0
D | E |  |  | Inquiy & Datasheet for Transformers | GEN-01-D-E-MA-001 |  |  |  |  | 0.22469 |  | 15279091.7692 | 0
D | E |  |  | Inquiy & Datasheet for UPS | GEN-01-D-E-MA-002 |  |  |  |  | 0.22469 |  | 15279091.7692 | 0
|  | Electrical Equipment Location | [7 empty] | 1.6911 | 0% | 114995269.631 | 0
D | E |  |  | Passage post Layout | GEN-01-D-E-21-001 |  |  |  |  | 0.56764 |  | 38599810.7852 | 0
D | E |  |  | Electrical Panel Location for Process Building | SLN-01-D-E-21-001 |  |  |  |  | 0.67408 |  | 45837275.3075 | 0
D | E |  |  | Electrical Equipment Location for Process Water Systems | UTI-01-D-E-21-001 |  |  |  |  | 0.44939 |  | 30558183.5383 | 0
|  | Earthing and Lightning System | [7 empty] | 1.9158 | 0% | 130274361.4002 | 0
D | E |  |  | Primary Earthing Layout | GEN-01-D-E-51-001 |  |  |  |  | 0.67408 |  | 45837275.3075 | 0
D | E |  |  | Typical Secondary Earthing System | GEN-01-D-E-51-002 |  |  |  |  | 0.34295 |  | 23320719.0161 | 0
D | E |  |  | Lightning System Layout | GEN-01-D-E-51-003 |  |  |  |  | 0.55582 |  | 37795648.0605 | 0
D | E |  |  | Bill of Material for Earthing and Lightning System | GEN-01-D-E-51-010 |  |  |  |  | 0.34295 |  | 23320719.0161 | 0
|  | Fire Alarm System | [7 empty] | 0.94607 | 0% | 64333017.9754 | 0
D | E |  |  | Fire Alarm System Layout | GEN-01-D-E-FA-001 |  |  |  |  | 0.35478 |  | 24124881.7408 | 0
D | E |  |  | Fire Alarm System Block Diagram | GEN-01-D-E-FA-002 |  |  |  |  | 0.35478 |  | 24124881.7408 | 0
D | E |  |  | Fire Alarm System BOM | GEN-01-D-E-FA-003 |  |  |  |  | 0.23652 |  | 16083254.4939 | 0

## Invoice 03
Main Document Registry
Phase | Department | 1 | 2 | Document Title | Document No. | POI | Rev. | Transmittal No. | Date | W.F (%) | Progress | Contract Price | Invoice Amount
|  |  |  | Toroq Seamless Pipe Mill | [5 empty] | 100 | 25.98% | 6800000000 | 1766866130.5582
Basic | [9 empty] | 19.5837 | 61.94% | 1331693472.0908 | 824869914.8534
| Management and Project Control | [8 empty] | 0.5913 | 100% | 40208136.2346 | 40208136.2346
B | P |  |  | Numbering Method | GEN-01-P-O-00-001 | IFI | D | 98207-4-0017 | 2020-04-19 | 0.23652 | 100% | 16083254.4939 | 16083254.4939
B | P |  |  | Coordination Procedure | GEN-01-P-O-00-002 | IFI | A | 98207-4-0002 | 2020-01-25 | 0.23652 | 100% | 16083254.4939 | 16083254.4939
B | P |  |  | Overall Time Schedule | GEN-01-P-O-00-003 | IFI | A | 98207-4-0015 | 2020-04-15 | 0.11826 | 100% | 8041627.2469 | 8041627.2469
| Fluid Engineering | [8 empty] | 2.4834 | 0% | 168874172.1854 | 0
B | M |  |  | Process Flow Diagram | GEN-01-D-U-01-001 |  |  |  |  | 1.7739 |  | 120624408.7039 | 0
B | M |  |  | Fire Fighting Concept | GEN-01-S-U-01-050 |  |  |  |  | 0.70956 |  | 48249763.4816 | 0
| Civil & Structure | [8 empty] | 14.1438 | 81.58% | 961778618.7323 | 784661778.6187
|  | General Basic | [7 empty] | 11.14 | 90.3% | 757521286.6604 | 684061021.7597
B | C |  |  | General Layout | GEN-01-D-P-00-001 | IFC | 2 | 98207-4-0024 | 2020-05-02 | 3.8907 | 100% | 264569536.4238 | 264569536.4238
B | C |  |  | Steel work general notes | GEN-01-S-S-GN-001 | IFC | 0 | 98207-4-0026 | 2020-05-16 | 0.47304 | 100% | 32166508.9877 | 32166508.9877
B | C |  |  | Civil work general notes | GEN-01-S-C-GN-001 | IFC | 0 | 98207-4-0026 | 2020-05-16 | 0.47304 | 100% | 32166508.9877 | 32166508.9877
B | C |  |  | Road Plan & Profile | ROD-01-D-C-DR-001 | IFA | A | 98207-4-0013 | 2020-04-13 | 0.74503 | 70% | 50662251.6556 | 35463576.1589
B | C |  |  | Site Condition | GEN-01-R-C-SC-001 | IFA | A | 98207-4-0020 | 2020-04-27 | 0.37252 | 70% | 25331125.8278 | 17731788.0795
|  |  |  | Grading Plan | ROD-01-D-C-BS-001 | IFC | 0 | 98207-4-0027 | 2020-05-30 | 0.37252 | 100% | 25331125.8278 | 25331125.8278
B | C |  |  | Water Draiange System | ROD-01-D-C-00-051~100 |  |  |  |  | 0.74503 |  | 50662251.6556 | 0
B | C |  |  | MAIN Building & STORAGE BASIC | [7 empty] | 0 | 0
|  |  |  | MAIN Building & STORAGE BASIC-PLAN | SLN-01-D-S-BA-001 | IFC | 0 | 98207-4-0026 | 2020-05-16 | 0.37547 | 100% | 25532166.509 | 25532166.509
|  |  |  | MAIN Building & STORAGE BASIC-Building SECTION(2) | SLN-01-D-S-BA-002 | IFC | 0 | 98207-4-0026 | 2020-05-16 | 0.37547 | 100% | 25532166.509 | 25532166.509
|  |  |  | MAIN Building & STORAGE BASIC-CRANE BEAMS & WALKWAY PLAN | SLN-01-D-S-BA-003 | IFC | 0 | 98207-4-0026 | 2020-05-16 | 0.37547 | 100% | 25532166.509 | 25532166.509
|  |  |  | MAIN Building & STORAGE BASIC-FRAME PLAN | SLN-01-D-S-BA-004 | IFC | 0 | 98207-4-0026 | 2020-05-16 | 0.37547 | 100% | 25532166.509 | 25532166.509
|  |  |  | MAIN Building & STORAGE BASIC-VIEWS | SLN-01-D-S-BA-005 | IFC | 0 | 98207-4-0026 | 2020-05-16 | 0.37547 | 100% | 25532166.509 | 25532166.509
|  |  |  | MAIN Building & STORAGE BASIC-Building SECTION(1) | SLN-01-D-S-BA-006 | IFC | 0 | 98207-4-0026 | 2020-05-16 | 0.37547 | 100% | 25532166.509 | 25532166.509
|  |  |  | MAIN Building & STORAGE BASIC-VIEW FOR AXIS 01&15 | SLN-01-D-S-BA-007 | IFC | 0 | 98207-4-0026 | 2020-05-16 | 0.37547 | 100% | 25532166.509 | 25532166.509
|  |  |  | MAIN Building & STORAGE BASIC-CRANES ARRANGEMENT | SLN-01-D-S-BA-008 | IFC | 0 | 98207-4-0026 | 2020-05-16 | 0.37547 | 100% | 25532166.509 | 25532166.509
B | C |  |  | Building Basic Report | SLN-01-R-F-BA-001 | IFI | A | 98207-4-0004 | 2020-01-26 | 1.0643 | 100% | 72374645.2223 | 72374645.2223
|  | Ancillary building | [7 empty] | 3.0038 | 49.25% | 204257332.0719 | 100600756.859
B | C |  |  | Conteen, Prayer room & Locker and Shower | ANC-01-D-C-BL-001~010 | IFA | A | 98207-4-0019 | 2020-04-27 | 0.6859 | 70% | 46641438.0322 | 32649006.6225
B | C |  |  | Administrative building-GROUND FLOOR PLAN | ANC-01-D-C-BL-010 | IFA | A | 98207-4-0023 | 2020-05-02 | 1.0052 | 70% | 68353831.5989 | 47847682.1192
|  |  |  | Administrative building-FIRST FLOOR PLAN | ANC-01-D-C-BL-011 | [6 empty] | 0 | 0
|  |  |  | Administrative building-SECOND FLOOR PLAN | ANC-01-D-C-BL-012 | [6 empty] | 0 | 0
B | C |  |  | Guard house | ANC-01-D-C-BL-020~030 |  |  |  |  | 0.34295 |  | 23320719.0161 | 0
B | C |  |  | Repair Work Shop | ANC-01-D-C-BL-030~040 |  |  |  |  | 0.67408 |  | 45837275.3075 | 0
| B |  |  | Initial estimation of ancillary building | ANC-01-R-C-BL-050 | IFI | A | 98207-4-0010 | 2020-03-11 | 0.29565 | 100% | 20104068.1173 | 20104068.1173
| Electrical & Automation | [8 empty] | 2.3652 | 0% | 160832544.9385 | 0
B | E |  |  | Overal Single Line Diagram | GEN-01-D-E-03-001 |  |  |  |  | 0.94607 |  | 64333017.9754 | 0
B | E |  |  | Load List | GEN-01-L-E-11-001 |  |  |  |  | 0.70956 |  | 48249763.4816 | 0
B | E |  |  | P&ID for Process Water Systems | GEN-01-D-I-01-001 |  |  |  |  | 0.70956 |  | 48249763.4816 | 0
Detail | [9 empty] | 80.4163 | 17.23% | 5468306527.9092 | 941996215.7048
| Fluid Engineering | [8 empty] | 19.9858 | 3.787% | 1359035004.7304 | 51466414.3803
|  | Piping Engineering | [7 empty] | 10.5842 | 0% | 719725638.5998 | 0
|  |  | Interconnecting Piping | [6 empty] | 4.7304 | 0% | 321665089.877 | 0
D | M |  |  | Piping Key Plan | GEN-01-D-U-11-002 |  |  |  |  | 1.5374 |  | 104541154.21 | 0
D | M |  |  | Piping Arrangement | GEN-01-D-U-21-003 |  |  |  |  | 1.4191 |  | 96499526.9631 | 0
D | M |  |  | Standard Pipe Support | GEN-01-D-U-43-004 |  |  |  |  | 1.1826 |  | 80416272.4693 | 0
D | M |  |  | Line List | GEN-01-L-U-63-005 |  |  |  |  | 0.5913 |  | 40208136.2346 | 0
|  |  | WTP (Pump Station, Cooling System) | [6 empty] | 3.1339 | 0% | 213103122.0435 | 0
D | M |  |  | Piping Arrangement | COO-01-D-U-21-006 |  |  |  |  | 3.1339 |  | 213103122.0435 | 0
|  |  | Material Take Off | [6 empty] | 1.1235 | 0% | 76395458.8458 | 0
D | M |  |  | MTO for Metal Piping | GEN-01-D-U-61-007 |  |  |  |  | 0.41391 |  | 28145695.3642 | 0
D | M |  |  | MTO for Non-Metal piping | GEN-01-D-U-61-008 |  |  |  |  | 0.41391 |  | 28145695.3642 | 0
D | M |  |  | Valve List | GEN-01-L-U-61-009 |  |  |  |  | 0.29565 |  | 20104068.1173 | 0
|  |  | ISO Metric Drawings | [6 empty] | 1.1235 | 0% | 76395458.8458 | 0
D | M |  |  | ISO Metric for Cooling Water | GEN-01-D-U-51-010 |  |  |  |  | 0.41391 |  | 28145695.3642 | 0
D | M |  |  | ISO Metric for Natural Gas | GEN-01-D-U-51-011 |  |  |  |  | 0.41391 |  | 28145695.3642 | 0
D | M |  |  | ISO Metric for Compressed Air | GEN-01-D-U-51-012 |  |  |  |  | 0.29565 |  | 20104068.1173 | 0
|  |  | Specification | [6 empty] | 0.28382 | 0% | 19299905.3926 | 0
D | M |  |  | Specification For Coating & Wrapping Of Underground Piping | GEN-01-S-U-10-046 |  |  |  |  | 0.094607 |  | 6433301.7975 | 0
D | M |  |  | Specification For Painting | GEN-01-S-U-10-047 |  |  |  |  | 0.094607 |  | 6433301.7975 | 0
D | M |  |  | Specification For Welding | GEN-01-S-U-10-048 |  |  |  |  | 0.094607 |  | 6433301.7975 | 0
|  |  | Underground Piping | [6 empty] | 0.18921 | 0% | 12866603.5951 | 0
D | M |  |  | Underground Piping Arrangement | GEN-01-D-U-02-013 |  |  |  |  | 0.094607 |  | 6433301.7975 | 0
D | M |  |  | MTO for Underground Piping | GEN-01-D-U-61-014 |  |  |  |  | 0.094607 |  | 6433301.7975 | 0
|  | Utility Engineering | [7 empty] | 3.0747 | 0% | 209082308.4201 | 0
D | M |  |  | Equipment Arrangement For Cooling System | COO-01-D-U-11-015 |  |  |  |  | 0.23652 |  | 16083254.4939 | 0
D | M |  |  | Equipment List For Cooling System | COO-01-L-U-64-016 |  |  |  |  | 0.23652 |  | 16083254.4939 | 0
D | M |  |  | Sewage Collection Network | UTI-01-D-U-02-017 |  |  |  |  | 0.70956 |  | 48249763.4816 | 0
D | M |  |  | MTO for Sewage system | UTI-01-D-U-61-018 |  |  |  |  | 0.23652 |  | 16083254.4939 | 0
D | M |  |  | Utitlity Consumption List | UTI-01-L-U-09-049 |  |  |  |  | 0.11826 |  | 8041627.2469 | 0
D | M |  |  | Firefighting System | UTI-01-D-U-11-019 |  |  |  |  | 0.23652 |  | 16083254.4939 | 0
D | M |  |  | Industrial Wastewater System | UTI-01-D-U-11-020 |  |  |  |  | 1.3009 |  | 88457899.7162 | 0
|  | HVAC Engineering | [7 empty] | 2.5426 | 0% | 172894985.8089 | 0
|  |  | Administrative Building | [6 empty] | 0.47304 | 0% | 32166508.9877 | 0
D | M |  |  | Cooling and Heating System | ANC-01-D-U-91-021 |  |  |  |  | 0.11826 |  | 8041627.2469 | 0
D | M |  |  | Ventilation System | ANC-01-D-U-91-022 |  |  |  |  | 0.11826 |  | 8041627.2469 | 0
D | M |  |  | Sewage System | ANC-01-D-U-91-023 |  |  |  |  | 0.11826 |  | 8041627.2469 | 0
D | M |  |  | Plumbing System | ANC-01-D-U-91-024 |  |  |  |  | 0.11826 |  | 8041627.2469 | 0
|  |  | Locker and Shower Building | [6 empty] | 0.47304 | 0% | 32166508.9877 | 0
D | M |  |  | Cooling and Heating System | ANC-01-D-U-91-025 |  |  |  |  | 0.11826 |  | 8041627.2469 | 0
D | M |  |  | Ventilation System | ANC-01-D-U-91-026 |  |  |  |  | 0.11826 |  | 8041627.2469 | 0
D | M |  |  | Sewage System | ANC-01-D-U-91-027 |  |  |  |  | 0.11826 |  | 8041627.2469 | 0
D | M |  |  | Plumbing System | ANC-01-D-U-91-028 |  |  |  |  | 0.11826 |  | 8041627.2469 | 0
|  |  | Conteen Building | [6 empty] | 0.35478 | 0% | 24124881.7408 | 0
D | M |  |  | Cooling and Heating System | ANC-01-D-U-91-029 |  |  |  |  | 0.094607 |  | 6433301.7975 | 0
D | M |  |  | Ventilation System | ANC-01-D-U-91-030 |  |  |  |  | 0.094607 |  | 6433301.7975 | 0
D | M |  |  | Sewage System | ANC-01-D-U-91-031 |  |  |  |  | 0.082781 |  | 5629139.0728 | 0
D | M |  |  | Plumbing System | ANC-01-D-U-91-032 |  |  |  |  | 0.082781 |  | 5629139.0728 | 0
|  |  | Guarde Building | [6 empty] | 0.29565 | 0% | 20104068.1173 | 0
D | M |  |  | Cooling and Heating System | ANC-01-D-U-91-033 |  |  |  |  | 0.082781 |  | 5629139.0728 | 0
D | M |  |  | Ventilation System | ANC-01-D-U-91-034 |  |  |  |  | 0.070956 |  | 4824976.3482 | 0
D | M |  |  | Sewage System | ANC-01-D-U-91-035 |  |  |  |  | 0.070956 |  | 4824976.3482 | 0
D | M |  |  | Plumbing System | ANC-01-D-U-91-036 |  |  |  |  | 0.070956 |  | 4824976.3482 | 0
|  |  | Process Building | [6 empty] | 0.94607 | 0% | 64333017.9754 | 0
D | M |  |  | Ventilation System | SLN-01-D-U-91-037 |  |  |  |  | 0.35478 |  | 24124881.7408 | 0
D | M |  |  | Sewage System | SLN-01-D-U-91-038 |  |  |  |  | 0.29565 |  | 20104068.1173 | 0
D | M |  |  | Plumbing System | SLN-01-D-U-91-039 |  |  |  |  | 0.29565 |  | 20104068.1173 | 0
|  | Inquiry Documents | [7 empty] | 3.7843 | 20% | 257332071.9016 | 51466414.3803
|  |  | Utility | [6 empty] | 3.2876 | 23.02% | 223557237.4645 | 51466414.3803
D | M |  |  | Inquiry & Data Sheet for RO System | COO-01-I-U-62-040 | IFI | A | 98207-4-0008 | 2020-03-09 | 0.75686 | 100% | 51466414.3803 | 51466414.3803
D | M |  |  | Inquiry & Data Sheet fot Cooling Tower | COO-01-I-U-62-041 |  |  |  |  | 0.5913 |  | 40208136.2346 | 0
D | M |  |  | Inquiry & Data Sheet for Water Pumps | COO-01-I-U-62-042 |  |  |  |  | 0.5913 |  | 40208136.2346 | 0
D | M |  |  | Inquiry & Data Sheet for Industrial Gas Racks | UTI-01-I-U-62-044 |  |  |  |  | 0.5913 |  | 40208136.2346 | 0
D | M |  |  | Inquiry & Data Sheet for Compressed Air System | UTI-01-I-U-62-043 |  |  |  |  | 0.75686 |  | 51466414.3803 | 0
|  |  | HVAC | [6 empty] | 0.49669 | 0% | 33774834.4371 | 0
D | M |  |  | Inquiry & Data Sheet for Package Unit | ANC-01-I-U-62-045 |  |  |  |  | 0.49669 |  | 33774834.4371 | 0
| Civil and Structure | [8 empty] | 41.6272 | 28.62% | 2830652790.9177 | 810033112.5828
|  | Civil and St. St. | [7 empty] | 34.8628 | 33.58% | 2370671712.3936 | 795960264.9007
|  |  | Main Building & Storage | [6 empty] | 17.1358 | 65.99% | 1165231788.0795 | 768940397.351
D | C |  |  | Main Building & Storage structure | SLN-01-D-S-E3-001 | IFA | B | 98207-4-0021 | 2020-04-27 | 9.4607 | 70% | 643330179.754 | 450331125.8278
|  |  |  | MAIN SALOON & STORAGE-GRID 1 , 15 | SLN-01-D-S-E3-002 | IFA | B | 98207-4-0021 | 2020-04-27 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-GRID 2 ,3,4,5,6,9,10,11,12,13,14 | SLN-01-D-S-E3-003 | IFA | B | 98207-4-0021 | 2020-04-27 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-GRID 7 , 8 | SLN-01-D-S-E3-004 | IFA | B | 98207-4-0021 | 2020-04-27 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-GRID A , B , C | SLN-01-D-S-E3-005 | IFA | B | 98207-4-0021 | 2020-04-27 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-PLAN +9.000 ( CRANE BEAMS & WALKWAY PLAN ) | SLN-01-D-S-E3-006 | IFA | B | 98207-4-0021 | 2020-04-27 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-GRID 1a, 2a ,. 3a , 4a , 5a , 6a , 9a , 10a | SLN-01-D-S-E3-007 | IFA | B | 98207-4-0021 | 2020-04-27 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-FRAMES PLAN | SLN-01-D-S-E3-008 | IFA | B | 98207-4-0021 | 2020-04-27 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE- ROOF BRACING PLAN | SLN-01-D-S-E3-009 | IFA | B | 98207-4-0021 | 2020-04-27 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-ROOF BEAM | SLN-01-D-S-E3-010 | IFA | B | 98207-4-0021 | 2020-04-27 |  | 70% | 0 | 0
|  |  |  | PURLIN & SAGROD -PLAN MAIN SALOON & STORAGE | SLN-01-D-S-E3-011 | [6 empty] | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-PURLIN & SAGROD ( DETAILS ) | SLN-01-D-S-E3-012 | [6 empty] | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-GRID 10a , 11a | SLN-01-D-S-E3-013 | [6 empty] | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-GRID 12a , 13a | SLN-01-D-S-E3-014 | [6 empty] | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR1 | SLN-01-D-S-E3-015 | IFA | B | 98207-4-0021 | 2020-04-27 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR1 | SLN-01-D-S-E3-016 | IFA | B | 98207-4-0021 | 2020-04-27 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR1 - SECTION & DETAILS | SLN-01-D-S-E3-017 | [6 empty] | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR2 | SLN-01-D-S-E3-020 | IFA | B | 98207-4-0021 | 2020-04-27 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR2 | SLN-01-D-S-E3-021 | IFA | B | 98207-4-0021 | 2020-04-27 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR2 -SECTION & DETAILS | SLN-01-D-S-E3-022 | [6 empty] | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR3,5 | SLN-01-D-S-E3-025 | IFA | B | 98207-4-0021 | 2020-04-27 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR4 | SLN-01-D-S-E3-028 | IFA | B | 98207-4-0021 | 2020-04-27 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR4 | SLN-01-D-S-E3-029 | IFA | B | 98207-4-0021 | 2020-04-27 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR4 -SECTION & DETAILS | SLN-01-D-S-E3-030 | [6 empty] | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR6 | SLN-01-D-S-E3-032 | IFA | B | 98207-4-0021 | 2020-04-27 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR6 | SLN-01-D-S-E3-033 | IFA | B | 98207-4-0021 | 2020-04-27 |  | 70% | 0 | 0
|  |  |  | CRANE BEAM CR6 -SECTION & DETAILSMAIN SALOON & STORAGE- | SLN-01-D-S-E3-034 | [6 empty] | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR7 | SLN-01-D-S-E3-036 | IFA | B | 98207-4-0021 | 2020-04-27 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR7 | SLN-01-D-S-E3-037 | IFA | B | 98207-4-0021 | 2020-04-27 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR7 & SECTION & DETAILS | SLN-01-D-S-E3-038 | [6 empty] | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR8 | SLN-01-D-S-E3-040 | IFA | B | 98207-4-0021 | 2020-04-27 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR8 | SLN-01-D-S-E3-041 | IFA | B | 98207-4-0021 | 2020-04-27 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR8 -SECTION & DETAILS | SLN-01-D-S-E3-042 | [6 empty] | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR9 | SLN-01-D-S-E3-043 | [6 empty] | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR9 | SLN-01-D-S-E3-044 | [6 empty] | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-BEAM B1 , B2 , B3 , B4 | SLN-01-D-S-E3-045 | IFA | B | 98207-4-0021 | 2020-04-27 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-BEAM B1 , B2 , B3 , B4 | SLN-01-D-S-E3-046 | [6 empty] | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR10 | SLN-01-D-S-E3-047 | [6 empty] | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR10 | SLN-01-D-S-E3-048 | [6 empty] | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CRANE BEAM CR9&10 - SECTION & DETAILS | SLN-01-D-S-E3-049 | [6 empty] | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-BASE PLATE | SLN-01-D-S-E3-050 | IFA | B | 98207-4-0021 | 2020-04-27 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-COLUMN 2 | SLN-01-D-S-E3-052 | IFA | B | 98207-4-0021 | 2020-04-27 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-RAFTER | SLN-01-D-S-E3-053 | IFA | B | 98207-4-0021 | 2020-04-27 |  | 70% | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-BRACING BR1 , BR 2 - SECTION & DETAILS ( 1 ) | SLN-01-D-S-E3-055 | [6 empty] | 0 | 0
|  |  |  | MAIN SALOON & STORAGE0BRACING - SECTION & DETAILS ( 2 ) | SLN-01-D-S-E3-056 | [6 empty] | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-BRACING - SECTION & DETAILS ( 3 ) | SLN-01-D-S-E3-057 | [6 empty] | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-AIRAROR PLAN | SLN-01-D-S-E3-060 | [6 empty] | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CLADDING GIRT 1 , 15 | SLN-01-D-S-E3-065 | [6 empty] | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CLADDING GIRT 1 , 15 & SECTION & DETAILS | SLN-01-D-S-E3-066 | [6 empty] | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CLADDING GIRT A , B | SLN-01-D-S-E3-067 | [6 empty] | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CLADDING GIRT A , B - SECTION & DETAILS ( 1 ) | SLN-01-D-S-E3-068 | [6 empty] | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CLADDING GIRT A , B - SECTION & DETAILS ( 2 ) | SLN-01-D-S-E3-069 | [6 empty] | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CLADDING GIRT A , B - SECTION & DETAILS ( 3 ) | SLN-01-D-S-E3-070 | [6 empty] | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-CLADDING GIRT 15 | SLN-01-D-S-E3-071 | [6 empty] | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-LADDER & SECTION & DETAILS | SLN-01-D-S-E3-075 | [6 empty] | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-LADDER - SECTION & DETAILS | SLN-01-D-S-E3-076 | [6 empty] | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-STOPPER & PLAN | SLN-01-D-S-E3-077 | [6 empty] | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-WALKWAY | SLN-01-D-S-E3-080 | [6 empty] | 0 | 0
|  |  |  | WALKWAY & SECTION & DETAILS MAIN SALOON & STORAGE- | SLN-01-D-S-E3-081 | [6 empty] | 0 | 0
|  |  |  | AERATOR MAIN SALOON & STORAGE- | SLN-01-D-S-E3-082 | [6 empty] | 0 | 0
|  |  |  | MAIN SALOON & STORAGE-AERATOR & SECTION & VIEW | SLN-01-D-S-E3-083 | [6 empty] | 0 | 0
D | C |  |  | MAIN BUILDING & STORAGE FOUNDATION-EXCAVATION PLAN | SLN-01-D-C-EE-001 | IFA | A | 98207-4-0014 | 2020-04-15 | 2.3652 | 70% | 160832544.9385 | 112582781.457
|  |  |  | MAIN BUILDING & STORAGE FOUNDATION-FOUNDATIONS PLAN | SLN-01-D-C-EE-002 | [6 empty] | 0 | 0
|  |  |  | MAIN BUILDING & STORAGE FOUNDATION-FOUNDATIONS FORMWORK | SLN-01-D-C-EE-003 | [6 empty] | 0 | 0
|  |  |  | MAIN BUILDING & STORAGE FOUNDATION-ANCHOR "2A-056" DETAILS | SLN-01-D-C-EE-004 | [6 empty] | 0 | 0
D | C |  |  | MAIN BUILDING & STORAGE FOUNDATION-FOUNDATON "F1"REINFORCEMENT | SLN-01-D-C-EF-001 | IFA | A | 98207-4-0014 | 2020-04-15 | 2.3652 | 70% | 160832544.9385 | 112582781.457
|  |  |  | MAIN BUILDING & STORAGE FOUNDATION-FOUNDATON "F1"REINFORCEMENT | SLN-01-D-C-EF-002 | [6 empty] | 0 | 0
D | C |  |  | Main Building & Storage MTO | SLN-01-D-C-MT-001 | IFA | B | 98207-4-0021 | 2020-04-27 | 0.98155 | 70% | 66745506.1495 | 46721854.3046
D | C |  |  | Main Building & Storage Pavement | SLN-01-D-C-EM-001 |  |  |  |  | 0.98155 |  | 66745506.1495 | 0
D | C |  |  | Main Building & Storge Calculation sheet | SLN-01-C-S-CA-001 | IFA | A | 98207-4-0012 | 2020-04-04 | 0.98155 | 70% | 66745506.1495 | 46721854.3046
|  |  | Equipment Foundation | [6 empty] | 6.114 | 6.499% | 415752128.666 | 27019867.5497
D | C |  |  | Cold disk saw (Formwork) | COL-01-D-C-EE-001 |  |  |  |  | 0.29565 |  | 20104068.1173 | 0
D | C |  |  | Cold disk saw (Reinforcement) | COL-01-D-C-EF-001 |  |  |  |  | 0.28382 |  | 19299905.3926 | 0
D | C |  |  | Heating furnace (Formwork) | HEA-01-D-C-EE-001 |  |  |  |  | 0.28382 |  | 19299905.3926 | 0
D | C |  |  | Heating furnace (Reinforcement) | HEA-01-D-C-EF-001 |  |  |  |  | 0.28382 |  | 19299905.3926 | 0
D | C |  |  | Piercing mill (Formwork) | PIE-01-D-C-EE-001 |  |  |  |  | 0.28382 |  | 19299905.3926 | 0
D | C |  |  | Piercing mill (Reinforcement) | PIE-01-D-C-EF-001 |  |  |  |  | 0.28382 |  | 19299905.3926 | 0
D | C |  |  | Elongator (Formwork) | ELO-01-D-C-EE-001 |  |  |  |  | 0.28382 |  | 19299905.3926 | 0
D | C |  |  | Elongator (Reinforcement) | ELO-01-D-C-EF-001 |  |  |  |  | 0.28382 |  | 19299905.3926 | 0
D | C |  |  | Inductive heater (Formwork) | IND-01-D-C-EE-001 |  |  |  |  | 0.28382 |  | 19299905.3926 | 0
D | C |  |  | Inductive heater (Reinforcement) | IND-01-D-C-EF-001 |  |  |  |  | 0.28382 |  | 19299905.3926 | 0
D | C |  |  | Sizing mill (Formwork) | SIZ-01-D-C-EE-001 |  |  |  |  | 0.28382 |  | 19299905.3926 | 0
D | C |  |  | Sizing mill (Reinforcement) | SIZ-01-D-C-EF-001 |  |  |  |  | 0.28382 |  | 19299905.3926 | 0
D | C |  |  | COOLING BED (FORMWORK)-PLAN | COB-01-D-C-EE-001 | IFA | A | 98207-4-0028 | 2020-06-10 | 0.28382 | 70% | 19299905.3926 | 13509933.7748
|  |  |  | COOLING BED (FORMWORK)-SECTION(1) | COB-01-D-C-EE-002 | [6 empty] | 0 | 0
|  |  |  | COOLING BED (FORMWORK)-SECTION (2) | COB-01-D-C-EE-003 | [6 empty] | 0 | 0
|  |  |  | COOLING BED (FORMWORK)-DETAILS | COB-01-D-C-EE-004 | [6 empty] | 0 | 0
D | C |  |  | COOLING BED (REINFORCEMENT)-FOUNDATION PLAN | COB-01-D-C-EF-001 | IFA | A | 98207-4-0028 | 2020-06-10 | 0.28382 | 70% | 19299905.3926 | 13509933.7748
|  |  |  | COOLING BED (REINFORCEMENT)-WALLS (1) | COB-01-D-C-EF-002 | [6 empty] | 0 | 0
|  |  |  | COOLING BED (REINFORCEMENT)-WALLS (2) | COB-01-D-C-EF-003 | [6 empty] | 0 | 0
|  |  |  | COOLING BED (REINFORCEMENT)-WALLS (3) | COB-01-D-C-EF-004 | [6 empty] | 0 | 0
|  |  |  | COOLING BED (REINFORCEMENT)-PEDESTALS | COB-01-D-C-EF-005 | [6 empty] | 0 | 0
D | C |  |  | Fluid lubricantion system (Formwork) | FLU-01-D-C-EE-001 |  |  |  |  | 0.28382 |  | 19299905.3926 | 0
D | C |  |  | Fluid lubricantion system (Reinforcement) | FLU-01-D-C-EF-001 |  |  |  |  | 0.28382 |  | 19299905.3926 | 0
D | C |  |  | Grease lubricantion system (Formwork) | GRE-01-D-C-EE-001 |  |  |  |  | 0.28382 |  | 19299905.3926 | 0
D | C |  |  | Grease lubricantion system (Reinforcement) | GRE-01-D-C-EF-001 |  |  |  |  | 0.28382 |  | 19299905.3926 | 0
D | C |  |  | Cooling system (Formwork) | COO-01-D-C-EE-001 |  |  |  |  | 0.28382 |  | 19299905.3926 | 0
D | C |  |  | Cooling system (Reinforcement) | COO-01-D-C-EF-001 |  |  |  |  | 0.28382 |  | 19299905.3926 | 0
D | C |  |  | Calculation Report for Foundations | GEN-01-D-C-CA-001 |  |  |  |  | 0.42573 |  | 28949858.0889 | 0
|  |  | Ancillary building | [6 empty] | 3.9262 | 0% | 266982024.5979 | 0
D | C |  |  | Conteen, Prayer room & Locker and Shower (Formwork) | ANC-01-D-C-EE-001~010 |  |  |  |  | 0.54399 |  | 36991485.3359 | 0
D | C |  |  | Conteen, Prayer room & Locker and Shower (Reinforcement) | ANC-01-D-C-EF-001~010 |  |  |  |  | 0.54399 |  | 36991485.3359 | 0
D | C |  |  | Administrative (Formwork) | ANC-01-D-C-EE-011~020 |  |  |  |  | 0.54399 |  | 36991485.3359 | 0
D | C |  |  | Administrative (Reinforcement) | ANC-01-D-C-EF-011~020 |  |  |  |  | 0.54399 |  | 36991485.3359 | 0
D | C |  |  | Guard house (Formwork) | ANC-01-D-C-EE-021~030 |  |  |  |  | 0.17739 |  | 12062440.8704 | 0
D | C |  |  | Guard house (Reinforcement) | ANC-01-D-C-EF-021~030 |  |  |  |  | 0.18921 |  | 12866603.5951 | 0
D | C |  |  | Bascule (Formwork) | ANC-01-D-C-EE-031~040 |  |  |  |  | 0.094607 |  | 6433301.7975 | 0
D | C |  |  | Bascule (Reinforcement) | ANC-01-D-C-EF-031~040 |  |  |  |  | 0.094607 |  | 6433301.7975 | 0
D | C |  |  | Building Toilets | ANC-01-D-C-EE-041~050 |  |  |  |  | 0.17739 |  | 12062440.8704 | 0
D | C |  |  | Repair Work Shop | ANC-01-D-C-EE-051~060 |  |  |  |  | 0.57947 |  | 39403973.5099 | 0
D | C |  |  | Laboratory (Formwork) | ANC-01-D-C-EE-061~070 |  |  |  |  | 0.082781 |  | 5629139.0728 | 0
D | C |  |  | Laboratory (Reinforcement) | ANC-01-D-C-EF-061~070 |  |  |  |  | 0.082781 |  | 5629139.0728 | 0
D | C |  |  | Calculation Report for Ancillary building | ANC-01-D-C-CA-001 |  |  |  |  | 0.272 |  | 18495742.6679 | 0
|  |  | Auxiliary buildings & FDN | [6 empty] | 7.6868 | 0% | 522705771.0501 | 0
D | C |  |  | Passage post (Formwork) | UTI-01-D-C-EE-001~010 |  |  |  |  | 0.35478 |  | 24124881.7408 | 0
D | C |  |  | Passage post (Reinforcement) | UTI-01-D-C-EF-001~010 |  |  |  |  | 0.35478 |  | 24124881.7408 | 0
D | C |  |  | Electrical room (Formwork) | UTI-01-D-C-EE-011~050 |  |  |  |  | 1.0762 |  | 73178807.947 | 0
D | C |  |  | Electrical room (Reinforcement) | UTI-01-D-C-EF-011~050 |  |  |  |  | 1.0643 |  | 72374645.2223 | 0
D | C |  |  | Strorage Tank (Formwork) | UTI-01-D-C-EE-061~100 |  |  |  |  | 0.3666 |  | 24929044.4655 | 0
D | C |  |  | Strorage Tank (Reinforcement) | UTI-01-D-C-EF-061~100 |  |  |  |  | 0.35478 |  | 24124881.7408 | 0
D | C |  |  | Compressor room (Formwork) | UTI-01-D-C-EE-101~150 |  |  |  |  | 0.3666 |  | 24929044.4655 | 0
D | C |  |  | Compressor room (Reinforcement) | UTI-01-D-C-EF-101~150 |  |  |  |  | 0.35478 |  | 24124881.7408 | 0
D | C |  |  | WTP Buildings (Formwork) | UTI-01-D-C-EE-151~400 |  |  |  |  | 1.4309 |  | 97303689.6878 | 0
D | C |  |  | WTP Buildings (Reinforcement) | UTI-01-D-C-EF-151~400 |  |  |  |  | 1.4309 |  | 97303689.6878 | 0
D | C |  |  | Calculation Report for Auxiliary buildings | UTI-01-D-C-CA-001 |  |  |  |  | 0.53217 |  | 36187322.6112 | 0
|  | Architectural | [7 empty] | 5.2507 | 0% | 357048249.7635 | 0
|  |  | Main Building & Storage | [6 empty] | 4.281 | 0% | 291106906.3387 | 0
D | C |  |  | Main Building & Storage | SLN-01-D-C-EL-001~020 |  |  |  |  | 3.7843 |  | 257332071.9016 | 0
D | C |  |  | SITE PLAN | GEN-01-D-C-EL-0011 |  |  |  |  | 0.49669 |  | 33774834.4371 | 0
|  |  | Ancillary building | [6 empty] | 0.96973 | 0% | 65941343.4248 | 0
D | C |  |  | Conteen, Prayer room & Locker and Shower | ANC-01-D-C-EL-001~020 |  |  |  |  | 0.29565 |  | 20104068.1173 | 0
D | C |  |  | Administrative | ANC-01-D-C-EL-021~040 |  |  |  |  | 0.29565 |  | 20104068.1173 | 0
D | C |  |  | Guard house | ANC-01-D-C-EL-041~060 |  |  |  |  | 0.094607 |  | 6433301.7975 | 0
D | C |  |  | Bascule | ANC-01-D-C-EL-061~080 |  |  |  |  | 0.047304 |  | 3216650.8988 | 0
D | C |  |  | Building Toilets | ANC-01-D-C-EL-081~100 |  |  |  |  | 0.047304 |  | 3216650.8988 | 0
D | C |  |  | Repair Work Shop | ANC-01-D-C-EL-101~120 |  |  |  |  | 0.15374 |  | 10454115.421 | 0
D | C |  |  | Laboratory | ANC-01-D-C-EL-121~130 |  |  |  |  | 0.035478 |  | 2412488.1741 | 0
|  | Road and Landscape | [7 empty] | 1.5137 | 13.67% | 102932828.7606 | 14072847.6821
D | C |  |  | Access Roads | ROD-01-D-C-DR-001~100 |  |  |  |  | 0.30747 |  | 20908230.842 | 0
D | C |  |  | Roads Plan & Profile | ROD-01-D-C-DR-100~200 |  |  |  |  | 0.30747 |  | 20908230.842 | 0
D | C |  |  | Roads Cross Section & volume Table | ROD-01-D-C-DR-200~300 |  |  |  |  | 0.30747 |  | 20908230.842 | 0
D | C |  |  | Water Draiange System | ROD-01-D-C-DW-001~100 | IFA | A | 98207-4-0016 | 2020-04-18 | 0.29565 | 70% | 20104068.1173 | 14072847.6821
D | C |  |  | Leveling & Coding | ROD-01-D-C-DS-001~100 |  |  |  |  | 0.29565 |  | 20104068.1173 | 0
| Electrical and Automation | [8 empty] | 18.8032 | 6.296% | 1278618732.2611 | 80496688.7417
|  | Lighting and Low Current System | [7 empty] | 5.9484 | 7.932% | 404493850.5203 | 32086092.7152
D | E |  |  | Overall Lighting Block Diagram | GEN-01-D-E-52-020 |  |  |  |  | 0.16556 |  | 11258278.1457 | 0
D | E |  |  | Main Lighting Panel Single Line Diagram | GEN-01-D-E-52-030 |  |  |  |  | 0.16556 |  | 11258278.1457 | 0
|  |  |  | Lighting & Socket System-Lighting Panel LP01 | GEN-01-D-E-52-031 | [6 empty] | 0 | 0
D | E |  |  | Lighting, Fire Alarm, CCTV and Intercome for Process Building | SLN-01-D-E-52-001 |  |  |  |  | 0.88694 |  | 60312204.3519 | 0
D | E |  |  | Lighting, FDA, Tel and Network System for Administrative Building | ANC-01-D-E-52-001 |  |  |  |  | 0.67408 |  | 45837275.3075 | 0
D | E |  |  | Lighting, FDA, Tel and Network System for Conteen, Prayer room & Locker and Shower | ANC-01-D-E-52-002 |  |  |  |  | 0.67408 |  | 45837275.3075 | 0
D | E |  |  | Lighting, FDA, Tel and Network System for Guard Building | ANC-01-D-E-52-003 |  |  |  |  | 0.44939 |  | 30558183.5383 | 0
D | E |  |  | Lighting, FDA, Tel and Network System for Toilet Building | ANC-01-D-E-52-004 |  |  |  |  | 0.34295 |  | 23320719.0161 | 0
D | E |  |  | Lighting, FDA, Tel and Network System for Bascule | ANC-01-D-E-52-005 |  |  |  |  | 0.22469 |  | 15279091.7692 | 0
D | E |  |  | Lighting, FDA, Tel and Network System for Repair Workshop | ANC-01-D-E-52-006 |  |  |  |  | 0.34295 |  | 23320719.0161 | 0
D | E |  |  | Lighting, FDA, Tel and Network System for Passage Post | GEN-01-D-E-52-001 |  |  |  |  | 0.34295 |  | 23320719.0161 | 0
D | E |  |  | Lighting, FDA, Tel and Network System for Electrical Room | GEN-01-D-E-52-002 |  |  |  |  | 0.44939 |  | 30558183.5383 | 0
D | E |  |  | Lighting System for Outdoor Area | GEN-01-D-E-52-003 | IFA | A | 98207-4-0018 | 2020-04-25 | 0.67408 | 70% | 45837275.3075 | 32086092.7152
|  |  |  | Lighting System for Basic Road | GEN-01-D-E-52-004 | IFA | A | 98207-4-0018 | 2020-04-25 |  | 70% | 0 | 0
D | E |  |  | Bill of Material for Lighting, FDA, Tel and Network System | GEN-01-D-E-52-010 |  |  |  |  | 0.55582 |  | 37795648.0605 | 0
|  | Cabling System | [7 empty] | 2.8146 | 0% | 191390728.4768 | 0
D | E |  |  | Embedded Cable Way, Route and Section | GEN-01-D-E-32-001 |  |  |  |  | 0.78051 |  | 53074739.8297 | 0
D | E |  |  | Exposed Cable Way, Route and Section | GEN-01-D-E-33-001 |  |  |  |  | 0.67408 |  | 45837275.3075 | 0
D | E |  |  | Power Cable List | GEN-01-L-E-43-001 |  |  |  |  | 0.67408 |  | 45837275.3075 | 0
D | E |  |  | Bill of Material for Power Cables | GEN-01-D-E-43-010 |  |  |  |  | 0.34295 |  | 23320719.0161 | 0
D | E |  |  | Bill of Material for Cable Route and Bulk Material | GEN-01-D-E-33-010 |  |  |  |  | 0.34295 |  | 23320719.0161 | 0
|  | Electrical and Instrumentation for Process Water Systems | [7 empty] | 4.1391 | 0% | 281456953.6424 | 0
D | E |  |  | MCC Panel Single Line Diagram and Typical wiring for Process Water Systems | UTI-01-D-E-03-001 |  |  |  |  | 0.73321 |  | 49858088.9309 | 0
D | E |  |  | Cable Route for Process Water Systems | UTI-01-D-E-32-001 |  |  |  |  | 0.44939 |  | 30558183.5383 | 0
D | E |  |  | Lighting, FDA and Communication System for Process Water Systems | UTI-01-D-E-52-003 |  |  |  |  | 0.44939 |  | 30558183.5383 | 0
D | E |  |  | Instrument Datasheet for Process Water Systems | UTI-01-D-I-06-001 |  |  |  |  | 0.73321 |  | 49858088.9309 | 0
D | E |  |  | Power and Control Cable list for Process Water Systems | UTI-01-L-E-43-001 |  |  |  |  | 0.66225 |  | 45033112.5828 | 0
D | E |  |  | LCP Typical Wiring for Process Water Systems | UTI-01-D-E-L4-001 |  |  |  |  | 0.33113 |  | 22516556.2914 | 0
D | E |  |  | Junction Box Termination for Process Water Systems | UTI-01-D-I-13-001 |  |  |  |  | 0.44939 |  | 30558183.5383 | 0
D | E |  |  | Automation & Control Specification & BOM for Process Water Systems | UTI-01-D-I-13-010 |  |  |  |  | 0.33113 |  | 22516556.2914 | 0
|  | Electrical Panel | [7 empty] | 0.89877 | 35% | 61116367.0766 | 21390728.4768
D | E |  |  | 20kV Panels Single Line Diagram | GEN-01-D-E-03-012 | IFA | A | 98207-4-0022 | 2020-04-28 | 0.44939 | 70% | 30558183.5383 | 21390728.4768
D | E |  |  | Main Low Voltage Panels Single Line Diagram | GEN-01-D-E-03-013 |  |  |  |  | 0.44939 |  | 30558183.5383 | 0
D |  | Electrical Equipment Inquiry and Datasheet | [7 empty] | 0.44939 | 0% | 30558183.5383 | 0
D | E |  |  | Inquiy & Datasheet for Transformers | GEN-01-D-E-MA-001 |  |  |  |  | 0.22469 |  | 15279091.7692 | 0
D | E |  |  | Inquiy & Datasheet for UPS | GEN-01-D-E-MA-002 |  |  |  |  | 0.22469 |  | 15279091.7692 | 0
|  | Electrical Equipment Location | [7 empty] | 1.6911 | 23.5% | 114995269.631 | 27019867.5497
D | E |  |  | Passage post Layout | GEN-01-D-E-21-001 | IFA | A | 98207-4-0022 | 2020-04-28 | 0.56764 | 70% | 38599810.7852 | 27019867.5497
D | E |  |  | Electrical Panel Location for Process Building | SLN-01-D-E-21-001 |  |  |  |  | 0.67408 |  | 45837275.3075 | 0
D | E |  |  | Electrical Equipment Location for Process Water Systems | UTI-01-D-E-21-001 |  |  |  |  | 0.44939 |  | 30558183.5383 | 0
|  | Earthing and Lightning System | [7 empty] | 1.9158 | 0% | 130274361.4002 | 0
D | E |  |  | Primary Earthing Layout | GEN-01-D-E-51-001 |  |  |  |  | 0.67408 |  | 45837275.3075 | 0
D | E |  |  | Typical Secondary Earthing System | GEN-01-D-E-51-002 |  |  |  |  | 0.34295 |  | 23320719.0161 | 0
D | E |  |  | Lightning System Layout | GEN-01-D-E-51-003 |  |  |  |  | 0.55582 |  | 37795648.0605 | 0
D | E |  |  | Bill of Material for Earthing and Lightning System | GEN-01-D-E-51-010 |  |  |  |  | 0.34295 |  | 23320719.0161 | 0
|  | Fire Alarm System | [7 empty] | 0.94607 | 0% | 64333017.9754 | 0
D | E |  |  | Fire Alarm System Layout | GEN-01-D-E-FA-001 |  |  |  |  | 0.35478 |  | 24124881.7408 | 0
D | E |  |  | Fire Alarm System Block Diagram | GEN-01-D-E-FA-002 |  |  |  |  | 0.35478 |  | 24124881.7408 | 0
D | E |  |  | Fire Alarm System BOM | GEN-01-D-E-FA-003 |  |  |  |  | 0.23652 |  | 16083254.4939 | 0
[9 empty] | Management and Project Control | 0.5913 | 100%
[9 empty] | Fluid Engineering | 22.4693 | 3.368%
[9 empty] | Civil & Structure | 55.7711 | 42.05%
[9 empty] | Electrical & Automation | 21.1684 | 5.592%

## MDR for Client (hidden)
Main Document Registry
| Document No. | Document Title | Client Tag Number | W.F (%) | POI | Rev. | Transmittal No. | Date | Comment No. | Comment Date | CM | Progress | Dec | POI | Rev. | Transmittal No. | Date | Comment No. | Comment Date | CM |  | POI | Rev. | Transmittal No. | Date | Comment No. | Comment Date | CM
| Sarooj Lime Plant |  |  | 100 | [7 empty] | 0% | 1st | [7 empty] | 2nd
|  | Basic |  | 18.4247 | [7 empty] | 0%
|  | Mechanical, Piping and Utility |  | 12.8872 | [7 empty] | 0%
|  | General Drawings |  | 12.8872 | [7 empty] | 0%
|  | Layout |  | 1.218
|  | Layout- Plan View |  | 0.60901
|  | Steel binding - assembly I |  | 0.60901
|  | Steel binding - assembly II |  | 0.60901
| SLDQ05001001 | PFD |  | 4.2843
|  | Blower house basic drawing |  | 1.218
|  | Material comparison |  | 0.24361
|  | Tolerances |  | 0.24361
|  | Painting instructions |  | 0.24361
|  | Welding symbol |  | 0.24361
|  | Sequence of erection I |  | 0.1218
|  | Sequence of erection II |  | 0.1218
|  | Lubricating instructions for kiln |  | 0.1218
|  | Final GA Drawing with Loading based on Purchased Equipment |  | 2
|  | Erection Instruction |  | 0.5
|  | Operation and Maintenance Manual and Instruction |  | 0.5
|  | Civil & Structure |  | 0.66541 | [7 empty] | 0%
|  | Civil & Structure |  | 0.66541 | [7 empty] | 0%
| SLSC2BP01001 | Kiln foundation load list |  | 0.36541
| SLSC2BP01002 | Bin and Skip Loading Drawing |  | 0.3
SLSC2BP01003
SLSC2BP01004
SLSC2BP01005
SLSC2BP01006
SLSC2BP01007
SLSC2BP01008
SLSC2BP01009
SLSC2BP01010
SLSC2BP01011
|  | Electrical & Automation |  | 4.8721 | [7 empty] | 0%
|  | Electrical & Automation |  | 4.8721 | [7 empty] | 0%
|  | PI-Diagram kiln |  | 2.4361
|  | Configuration control system |  | 0.60901
|  | Motor list kiln |  | 1.827
|  | Detail |  | 81.5753 | [7 empty] | 0%
|  | Mechanical, Piping and Utility |  | 47.8359 | [7 empty] | 0%
|  | Inquiry |  | 10.121 | [7 empty] | 0%
|  | Vibrating Feeder 01 | 351.VF.080 | 0.97442
|  | Vibrating Feeder 02 & 03 | 431.VF.100 & 431.VF.110 | 0.97442
|  | Charging Conveyor-Drive Unit | 351.BC.090 | 0.97442
|  | Charging Conveyor-Belt |  | 0.97442
|  | Burner Inquiry |  | 0.97442
|  | Material Handling Inquiry |  | 0.97442
|  | Hydraulic Inquiry | 431.HU.220 & 431.HU.230 & 431.HU.240 & 431.HU.250 & 431.HU.260 | 0.97442
|  | Winch for Skip | 351.SK.060 | 0.5
|  | Shut-off Valve Train for Burner |  | 0.5
|  | Blowers Inquiry | 431.BL.130 & 431.BL.??? | 1
|  | Hoist and Moniorails Inquriry |  | 0.5
|  | Inquiry for Waste Gas Bag Filter | 341.FN.020 & 341.BF.010 & 341.SC.011& 341.RF.013 & 341.SC.012 & 341.RF.014 & 341.BI.030 & 341.SG.031 & 341.RF.032 & 341.SG.040 & 341.TT.050 | 0.8
|  | Kiln |  | 9.0414 | [7 empty] | 0%
|  | shaft Kiln Body | 431.KL.010 | 1.11
|  | Shaft Kiln Auxiliary |  | 1.0743
|  | Lance boxes |  | 0.42857
|  | Shaft trap pivotable |  | 0.42857
|  | Reversal trap |  | 0.42857
|  | Discharge trap |  | 0.42857
|  | Hopper above discharge trap | 431.HP.020 & 431.HP.030 & 431.CH.040 & 431.CH.050 | 4.2857
|  | Discharge hopper upper & lower part |  | 0.42857
|  | Discharge table |  | 0.42857
|  | MHS |  | 6.4555 | [7 empty] | 0%
|  | Skip Hopper | 351.CB.040 & 351.SG.050 | 0.24361
|  | Skip | 351.SK.060 | 0.36541
|  | Kiln Hopper | 351.BI.070 | 0.85262
|  | Reversible belt conveyor | 351.BC.090 | 2.0706
|  | Rotating Hopper | 351.BI.100 & 351.BI.110 | 0.36541
|  | Stone distributor | 431.KL.010 | 0.24361
|  | Discharge hopper | 431.HP.060 & 431.HP.070 & 431.SG.080 & 431.SG.090 | 1.0962
|  | Discharge Two-way Chutes | 431.CH.120 & 431.CH.130 | 1.218
|  | Piping & Hvac |  | 7 | [7 empty] | 0%
|  | Gas Piping |  | 4.5405
|  | Lance Cooling air pipe |  | 0.28378
|  | Lance Cooling air pipe |  | 0.28378
|  | Compressed air |  | 1.8919
|  | Ducting |  | 9 | [7 empty] | 0%
|  | Process Air Ducting |  | 7.4348
|  | Waste Cooling Air Ducting |  | 1.5652
|  | Hydraulic |  | 5 | [7 empty] | 0%
|  | Hydraulic Details | 431.HU.220 & 431.HU.230 & 431.HU.240 & 431.HU.250 & 431.HU.260 | 5
|  | Refractory |  | 1.218 | [7 empty] | 0%
|  | Refractory | 431.KL.010 | 1.218
|  | Civil and Structure |  | 5.7247
|  | Steel Structure |  | 5.7247
|  | Skip bridge Steel Structure |  | 0.85262
|  | Kiln Structure |  | 0.85262
|  | Steel Structures for Covering |  | 3.0451
|  | Discharge Hopper Support |  | 0.48721
|  | Supporting Frame |  | 0.48721
|  | Electrical and Automation |  | 28.0146
|  | Electrical |  | 16.4434
|  | MCC kiln (fix speed motors) SLD & Typical Wiring Diagram |  | 3.6541
|  | MCC kiln (VFD motors) SLD & Typical Wiring Diagram |  | 3.0451
|  | Typical Electrical Connection Diagram |  | 3.6541
|  | Local Control Panel |  | 1.218
|  | Cable Routing (power & Control & Instrument) |  | 1.218
|  | Cable List & Schedule (power & Control & Instrument) |  | 1.218
|  | Electrical Equipment Location |  | 0.60901
|  | Lighting system kiln |  | 0.60901
|  | Electrical Room Equipment Location |  | 0.60901
|  | Earthing system kiln |  | 0.60901
|  | Automation & Instrumentation |  | 11.5713
|  | Inquiry Document For Control System and HMI |  | 1.218
|  | Typical Wiring Diagram PLC & RIO |  | 3.6541
|  | I/O list kiln |  | 1.827
|  | Control/Monitoring Software |  | 1.218
|  | Instrumentation Equipment Location |  | 1.218
|  | Automation Earthing system |  | 1.218
|  | Instrument list kiln |  | 1.218
|  | Mechanical, Piping and Utility |  | 60.7231 | [5 empty] | 12.99% |  | 0%
|  | Civil & Structure |  | 6.3901 | [5 empty] | 6% |  | 0%
|  | Electrical & Automation |  | 32.8867 | [5 empty] | 0% |  | 0%

## Invoice No. 1 (hidden)
Sarooj Lian Lime Kiln Invoice No. 01
Document No. | Document Title | POI | Rev. | Transmittal No. | Date | Comment No. | Comment Date | CM | W.F (%) | Progress | Contract Price | Designer Submitted Gross Amount
Sarooj Lime Plant | [8 empty] | 100 | 9.007% | 9000000000 | 810667600.4872
| Basic | [7 empty] | 18.4247 | 30.37% | 1658223925.5264 | 503669049.9391
| Mechanical, Piping and Utility | [7 empty] | 12.8872 | 39.81% | 1159847555.2462 | 461748343.4836
| General Drawings | [7 empty] | 12.8872 | 39.81% | 1159847555.2462 | 461748343.4836
| Layout | [7 empty] | 1.218 | 70% | 109622411.6931 | 76735688.1851
| Layout- Plan View | [7 empty] | 0.60901 | 70% | 54811205.8465 | 38367844.0926
| Steel binding - assembly I | [7 empty] | 0.60901 |  | 54811205.8465 | 0
| Steel binding - assembly II | [7 empty] | 0.60901 |  | 54811205.8465 | 0
SLDQ05001001 | PFD | IFA | A | 98202-001 | 2019-09-08 |  |  |  | 4.2843 | 70% | 385584461.4582 | 269909123.0207
| Blower house basic drawing | [7 empty] | 1.218 |  | 109622411.6931 | 0
SLSQ0TS34501 | Material comparison | IFA | A | 98202-010 | 2019-10-28 |  |  |  | 0.24361 | 70% | 21924482.3386 | 15347137.637
SLSQ0TS34601 | GENERAL TOLERANCES | IFA | A | 98202-008 | 2019-10-26 |  |  |  | 0.24361 | 70% | 21924482.3386 | 15347137.637
SLSQ0TS34701 | Painting instructions | IFA | A | 98202-011 | 2019-10-28 |  |  |  | 0.24361 | 70% | 21924482.3386 | 15347137.637
SLSQ0TS34901 | Welding symbol | IFA | A | 98202-007 | 2019-10-26 |  |  |  | 0.24361 | 70% | 21924482.3386 | 15347137.637
SLMM3HH49601 | Sequence of erection I | IFA | A | 98202-009 | 2019-10-28 |  |  |  | 0.1218 | 70% | 10962241.1693 | 7673568.8185
SLMM3HH49611 | Sequence of erection II | IFA | A | 98202-009 | 2019-10-28 |  |  |  | 0.1218 | 70% | 10962241.1693 | 7673568.8185
| Lubricating instructions for kiln | [7 empty] | 0.1218 |  | 10962241.1693 | 0
| Final GA Drawing with Loading based on Purchased Equipment | [7 empty] | 2 |  | 180000000 | 0
| Erection Instruction | [7 empty] | 0.5 |  | 45000000 | 0
| Operation and Maintenance Manual and Instruction | [7 empty] | 0.5 |  | 45000000 | 0
| Civil & Structure | [7 empty] | 0.66541 | 70% | 59886723.5079 | 41920706.4555
| Civil & Structure | [7 empty] | 0.66541 | 70% | 59886723.5079 | 41920706.4555
SLSC2BP01001 | Kiln foundation load list | IFA | B | 98202-003 | 2019-09-24 |  |  |  | 0.36541 | 70% | 32886723.5079 | 23020706.4555
SLSC2BP01002 | Bin and Skip Loading Drawing | [7 empty] | 0.3 | 70% | 27000000 | 18900000
SLSC2BP01003 | Loads on foundation(2) | [8 empty] | 70% | 0 | 0
SLSC2BP01004 | Loads on foundation(3) | [8 empty] | 70% | 0 | 0
SLSC2BP01005 | Loads on foundation(4) | [8 empty] | 70% | 0 | 0
SLSC2BP01006 | Kiln foundation-Kiln 1 | [8 empty] | 70% | 0 | 0
SLSC2BP01007 | Kiln foundation-Details | [8 empty] | 70% | 0 | 0
SLSC2BP01008 | Kiln foundation-Sequence of erection | [8 empty] | 70% | 0 | 0
SLSC2BP01009 | Kiln foundation-Sequence of erection | [8 empty] | 70% | 0 | 0
SLSC2BP01010 | Details | [8 empty] | 70% | 0 | 0
SLSC2BP01011 | Anchor bolts | [8 empty] | 70% | 0 | 0
| Electrical & Automation | [7 empty] | 4.8721 | 0% | 438489646.7722 | 0
| Electrical & Automation | [7 empty] | 4.8721 | 0% | 438489646.7722 | 0
| PI-Diagram kiln | [7 empty] | 2.4361 |  | 219244823.3861 | 0
| Configuration control system | [7 empty] | 0.60901 |  | 54811205.8465 | 0
| Motor list kiln | [7 empty] | 1.827 |  | 164433617.5396 | 0
| Detail | [7 empty] | 81.5753 | 4.182% | 7341776074.4736 | 306998550.5481
| Mechanical, Piping and Utility | [7 empty] | 47.8359 | 7.131% | 4305235270.576 | 306998550.5481
| Inquiry | [7 empty] | 10.121 | 6.739% | 910885505.4811 | 61388550.5481
SLIM1VF08001 | Vibrating Feeder 01 | IFA | A | 98202-012 | 2019-11-10 |  |  |  | 0.97442 | 70% | 87697929.3544 | 61388550.5481
| Vibrating Feeder 02 & 03 | [7 empty] | 0.97442 |  | 87697929.3544 | 0
| Charging Conveyor-Drive Unit | [7 empty] | 0.97442 |  | 87697929.3544 | 0
| Charging Conveyor-Belt | [7 empty] | 0.97442 |  | 87697929.3544 | 0
| Burner Inquiry | [7 empty] | 0.97442 |  | 87697929.3544 | 0
| Material Handling Inquiry | [7 empty] | 0.97442 |  | 87697929.3544 | 0
| Hydraulic Inquiry | [7 empty] | 0.97442 |  | 87697929.3544 | 0
| Winch for Skip | [7 empty] | 0.5 |  | 45000000 | 0
| Shut-off Valve Train for Burner | [7 empty] | 0.5 |  | 45000000 | 0
| Blowers Inquiry | [7 empty] | 1 |  | 90000000 | 0
| Hoist and Moniorails Inquriry | [7 empty] | 0.5 |  | 45000000 | 0
| Inquiry for Waste Gas Bag Filter | [7 empty] | 0.8 |  | 72000000 | 0
| Kiln | [7 empty] | 9.0414 | 30.18% | 813728571.4286 | 245610000
| shaft Kiln Body | [7 empty] | 1.11 | 70% | 99900000 | 69930000
SLDQ20104501 | Shaft part I - Assembly | IFA | A | 98202-004 | 2019-10-22 |  |  |  | 0.12 | 70% | 10800000 | 7560000
SLDQ20104511 | Shaft part I - Details | IFA | A | 98202-004 | 2019-10-22 |  |  |  | 0.11 | 70% | 9900000 | 6930000
SLDQ20104701 | Shaft part II - Assembly | IFA | A | 98202-004 | 2019-10-22 |  |  |  | 0.11 | 70% | 9900000 | 6930000
SLDQ20104711 | Shaft part II - Details I | IFA | A | 98202-004 | 2019-10-22 |  |  |  | 0.11 | 70% | 9900000 | 6930000
SLDQ20104721 | Shaft part II - anchor bolts for casted ceiling | IFA | A | 98202-004 | 2019-10-22 |  |  |  | 0.11 | 70% | 9900000 | 6930000
SLDQ20104731 | Shaft part II - Details | IFA | A | 98202-004 | 2019-10-22 |  |  |  | 0.11 | 70% | 9900000 | 6930000
SLDQ20104801 | Shaft part III - Assembly | IFA | A | 98202-004 | 2019-10-22 |  |  |  | 0.11 | 70% | 9900000 | 6930000
SLDQ20104811 | Shaft part III - Details | IFA | A | 98202-004 | 2019-10-22 |  |  |  | 0.11 | 70% | 9900000 | 6930000
SLDQ20105101 | Shaft part IV - Assembly | IFA | A | 98202-004 | 2019-10-22 |  |  |  | 0.11 | 70% | 9900000 | 6930000
SLDQ20105111 | Shaft part IV - Details | IFA | A | 98202-004 | 2019-10-22 |  |  |  | 0.11 | 70% | 9900000 | 6930000
| Shaft Kiln Auxiliary | [7 empty] | 1.0743 | 70% | 96685714.2857 | 67680000
SLDQ20105601 | Expansion joint sheet | IFA | A | 98202-005 | 2019-10-26 |  |  |  | 0.11 | 70% | 9900000 | 6930000
SLDQ20105701 | Rupture sheet | IFA | A | 98202-005 | 2019-10-26 |  |  |  | 0.064286 | 70% | 5785714.2857 | 4050000
SLDQ20105801 | Poking door - Assembly | IFA | A | 98202-005 | 2019-10-26 |  |  |  | 0.064286 | 70% | 5785714.2857 | 4050000
SLDQ20105811 | Poking door - Details | IFA | A | 98202-005 | 2019-10-26 |  |  |  | 0.064286 | 70% | 5785714.2857 | 4050000
SLDQ20105821 | Poking door - Casting parts | IFA | A | 98202-005 | 2019-10-26 |  |  |  | 0.064286 | 70% | 5785714.2857 | 4050000
SLDQ20105901 | Poking door with measuring point | IFA | A | 98202-005 | 2019-10-26 |  |  |  | 0.064286 | 70% | 5785714.2857 | 4050000
SLDQ20106101 | Cover in connecting channel-Assembly | IFA | A | 98202-005 | 2019-10-26 |  |  |  | 0.064286 | 70% | 5785714.2857 | 4050000
SLDQ20106111 | Cover in connecting channel-Details | IFA | A | 98202-005 | 2019-10-26 |  |  |  | 0.064286 | 70% | 5785714.2857 | 4050000
SLDQ20115501 | Packing cord for steel structure | IFA | A | 98202-005 | 2019-10-26 |  |  |  | 0.064286 | 70% | 5785714.2857 | 4050000
SLDQ20115601 | Silicon rubber seals | IFA | A | 98202-005 | 2019-10-26 |  |  |  | 0.064286 | 70% | 5785714.2857 | 4050000
SLDQ20117601 | Preheating burner for gas | IFA | A | 98202-005 | 2019-10-26 |  |  |  | 0.064286 | 70% | 5785714.2857 | 4050000
SLDQ20101401 | Locking device for traps | IFA | A | 98202-005 | 2019-10-26 |  |  |  | 0.064286 | 70% | 5785714.2857 | 4050000
SLDQ20101501 | Protection for counterweights | IFA | A | 98202-005 | 2019-10-26 |  |  |  | 0.064286 | 70% | 5785714.2857 | 4050000
SLDQ20104001 | Single door ø580 | IFA | A | 98202-005 | 2019-10-26 |  |  |  | 0.064286 | 70% | 5785714.2857 | 4050000
SLDQ20104101 | Protection plate for door ø580 | IFA | A | 98202-005 | 2019-10-26 |  |  |  | 0.064286 | 70% | 5785714.2857 | 4050000
SLDQ20104201 | Reversal box | IFA | A | 98202-005 | 2019-10-26 |  |  |  | 0.064286 | 70% | 5785714.2857 | 4050000
| Lance boxes | [7 empty] | 0.42857 | 70% | 38571428.5714 | 27000000
SLDQ20106701 | Lance boxes 33 lances-Assembly | IFA | A | 98202-006 | 2019-10-26 |  |  |  | 0.085714 | 70% | 7714285.7143 | 5400000
SLDQ20106711 | Lance boxes 33 lances-Details | IFA | A | 98202-006 | 2019-10-26 |  |  |  | 0.085714 | 70% | 7714285.7143 | 5400000
SLDQ20106721 | Lance boxes 33 lances-Details | IFA | A | 98202-006 | 2019-10-26 |  |  |  | 0.085714 | 70% | 7714285.7143 | 5400000
SLDQ20106731 | Lance boxes 33 lances-Details | IFA | A | 98202-006 | 2019-10-26 |  |  |  | 0.085714 | 70% | 7714285.7143 | 5400000
SLDQ20106741 | Lance boxes 33 lances-Details | IFA | A | 98202-006 | 2019-10-26 |  |  |  | 0.085714 | 70% | 7714285.7143 | 5400000
| Shaft trap pivotable | [7 empty] | 0.42857 | 70% | 38571428.5714 | 27000000
SLDQ20108201 | Shaft trap pivotable - Assembly | IFA | A | 98202-013 | 2019-11-12 |  |  |  | 0.085714 | 70% | 7714285.7143 | 5400000
SLDQ20108211 | Shaft trap pivotable - Details I | IFA | A | 98202-013 | 2019-11-12 |  |  |  | 0.085714 | 70% | 7714285.7143 | 5400000
SLDQ20108221 | Shaft trap pivotable - Details II | IFA | A | 98202-013 | 2019-11-12 |  |  |  | 0.085714 | 70% | 7714285.7143 | 5400000
SLDQ20108231 | Shaft trap pivotable - Details III | IFA | A | 98202-013 | 2019-11-12 |  |  |  | 0.085714 | 70% | 7714285.7143 | 5400000
SLDQ20108241 | Shaft trap pivotable -Details IV | IFA | A | 98202-013 | 2019-11-12 |  |  |  | 0.085714 | 70% | 7714285.7143 | 5400000
| Reversal trap | [7 empty] | 0.42857 | 70% | 38571428.5714 | 27000000
SLDQ20109001 | Reversal trap - Assembly | IFA | A | 98202-014 | 2019-11-12 |  |  |  | 0.085714 | 70% | 7714285.7143 | 5400000
SLDQ20109011 | Reversal trap - Details I | IFA | A | 98202-014 | 2019-11-12 |  |  |  | 0.085714 | 70% | 7714285.7143 | 5400000
SLDQ20109021 | Reversal trap - Details II | IFA | A | 98202-014 | 2019-11-12 |  |  |  | 0.085714 | 70% | 7714285.7143 | 5400000
SLDQ20109031 | Reversal trap - Details III | IFA | A | 98202-014 | 2019-11-12 |  |  |  | 0.085714 | 70% | 7714285.7143 | 5400000
SLDQ20109041 | Reversal trap - Protective grating | IFA | A | 98202-014 | 2019-11-12 |  |  |  | 0.085714 | 70% | 7714285.7143 | 5400000
| Discharge trap | [7 empty] | 0.42857 | 70% | 38571428.5714 | 27000000
SLDQ20101101 | Discharge trap-Assembly | IFA | A | 98202-015 | 2019-11-12 |  |  |  | 0.15 | 70% | 13500000 | 9450000
SLDQ20101111 | Discharge trap-machined parts | IFA | A | 98202-015 | 2019-11-12 |  |  |  | 0.15 | 70% | 13500000 | 9450000
SLDQ20101121 | Discharge trap-sheet parts | IFA | A | 98202-015 | 2019-11-12 |  |  |  | 0.12857 | 70% | 11571428.5714 | 8100000
| Hopper above discharge trap | [7 empty] | 4.2857 | 0% | 385714285.7143 | 0
| Hopper above discharge trap-Assembly | [7 empty] | 2.1429 |  | 192857142.8571 | 0
| Hopper above discharge trap-Details | [7 empty] | 2.1429 |  | 192857142.8571 | 0
| Discharge hopper upper part | [7 empty] | 0.42857 | 0% | 38571428.5714 | 0
| Discharge hopper upper part-Assembly | [7 empty] | 0.064286 |  | 5785714.2857 | 0
| Discharge hopper upper part-Details I | [7 empty] | 0.064286 |  | 5785714.2857 | 0
| Discharge hopper upper part-Details II | [7 empty] | 0.064286 |  | 5785714.2857 | 0
| Discharge hopper upper part-Cone peak casting part | [7 empty] | 0.064286 |  | 5785714.2857 | 0
| Discharge hopper lower part-Assembly | [7 empty] | 0.064286 |  | 5785714.2857 | 0
| Discharge hopper lower part-Details I | [7 empty] | 0.064286 |  | 5785714.2857 | 0
| Discharge hopper lower part-Details II | [7 empty] | 0.042857 |  | 3857142.8571 | 0
| Discharge table | [7 empty] | 0.42857 | 0% | 38571428.5714 | 0
| Discharge table - Assembly | [7 empty] | 0.064286 |  | 5785714.2857 | 0
| Discharge table - Details | [7 empty] | 0.064286 |  | 5785714.2857 | 0
| Rollers for discharge table | [7 empty] | 0.064286 |  | 5785714.2857 | 0
| Driving rod | [7 empty] | 0.064286 |  | 5785714.2857 | 0
| Driving rod - Flex. Metal hose | [7 empty] | 0.064286 |  | 5785714.2857 | 0
| Driving rod-Adjustment of cylinders | [7 empty] | 0.064286 |  | 5785714.2857 | 0
| Supporting column for cross beams | [7 empty] | 0.042857 |  | 3857142.8571 | 0
| MHS | [7 empty] | 6.4555 | 0% | 580998781.9732 | 0
| Skip Hopper | [7 empty] | 0.24361 | 0% | 21924482.3386 | 0
| Skip hopper 1600/1600 - Assembly | [7 empty] | 0.048721 |  | 4384896.4677 | 0
| Skip hopper - Details | [7 empty] | 0.048721 |  | 4384896.4677 | 0
| Skip hopper - Protection | [7 empty] | 0.048721 |  | 4384896.4677 | 0
| Channel to skip bucket | [7 empty] | 0.048721 |  | 4384896.4677 | 0
| Installation load cells / test weights | [7 empty] | 0.048721 |  | 4384896.4677 | 0
| Skip | [7 empty] | 0.36541 |  | 32886723.5079 | 0
| Skip bucket - Assembly | [7 empty] | 0.048721 |  | 4384896.4677 | 0
| Skip bucket - Assembly weldings | [7 empty] | 0.048721 |  | 4384896.4677 | 0
| Skip buck - Details part 2 | [7 empty] | 0.048721 |  | 4384896.4677 | 0
| Skip buck - Details part 3 | [7 empty] | 0.048721 |  | 4384896.4677 | 0
| Skip winch | [7 empty] | 0.048721 |  | 4384896.4677 | 0
| Skip winch | [7 empty] | 0.048721 |  | 4384896.4677 | 0
| Skip winch - Slack rope device | [7 empty] | 0.036541 |  | 3288672.3508 | 0
| Skip winch - Slack rope device | [7 empty] | 0.036541 |  | 3288672.3508 | 0
| Kiln Hopper | [7 empty] | 0.85262 |  | 76735688.1851 | 0
| Kiln hopper | [7 empty] | 0.85262 |  | 76735688.1851 | 0
| Reversible belt conveyor | [7 empty] | 2.0706 |  | 186358099.8782 | 0
| Reversible belt conveyor | [7 empty] | 2.0706 |  | 186358099.8782 | 0
| Rotating Hopper | [7 empty] | 0.36541 |  | 32886723.5079 | 0
| Rotating bucket - Assembly | [7 empty] | 0.048721 |  | 4384896.4677 | 0
| Rotating bucket - Details | [7 empty] | 0.048721 |  | 4384896.4677 | 0
| Rotating and lifting gear - Assembly | [7 empty] | 0.048721 |  | 4384896.4677 | 0
| Rotating and lifting gear - Details | [7 empty] | 0.036541 |  | 3288672.3508 | 0
| Rotating and lifting gear | [7 empty] | 0.036541 |  | 3288672.3508 | 0
| Centering of rotating bucket | [7 empty] | 0.036541 |  | 3288672.3508 | 0
| Auxiliary support for rotating bucket | [7 empty] | 0.036541 |  | 3288672.3508 | 0
| Closing ring with packing | [7 empty] | 0.036541 |  | 3288672.3508 | 0
| Guide pulleys for lifting gear | [7 empty] | 0.036541 |  | 3288672.3508 | 0
| Stone distributor | [7 empty] | 0.24361 |  | 21924482.3386 | 0
| Stone distributor | [7 empty] | 0.060901 |  | 5481120.5847 | 0
| Stone distributor pivotable - Assembly | [7 empty] | 0.060901 |  | 5481120.5847 | 0
| Stone distributor pivotable - Sheet parts | [7 empty] | 0.060901 |  | 5481120.5847 | 0
| Stone distributor pivotable - Machined parts | [7 empty] | 0.060901 |  | 5481120.5847 | 0
| Discharge hopper | [7 empty] | 1.0962 |  | 98660170.5238 | 0
| Discharge hopper | [7 empty] | 0.54811 |  | 49330085.2619 | 0
| Discharge hopper | [7 empty] | 0.54811 |  | 49330085.2619 | 0
| Discharge Two-way Chutes | [7 empty] | 1.218 |  | 109622411.6931 | 0
| Discharge Two-way Chutes- Details | [7 empty] | 1.218 |  | 109622411.6931 | 0
| Piping & Hvac | [7 empty] | 7 | 0% | 630000000 | 0
| Gas Piping | [7 empty] | 4.5405 |  | 408648648.6486 | 0
| Gas lances - Assembly I | [7 empty] | 0.094595 |  | 8513513.5135 | 0
| Gas lances - Assembly II | [7 empty] | 0.094595 |  | 8513513.5135 | 0
| Gas lances - Assembly III | [7 empty] | 0.094595 |  | 8513513.5135 | 0
| Gas lances - Details I | [7 empty] | 0.094595 |  | 8513513.5135 | 0
| Gas lances - Details II | [7 empty] | 0.094595 |  | 8513513.5135 | 0
| Gas lances - Details III | [7 empty] | 0.094595 |  | 8513513.5135 | 0
| Gas ring pipe | [7 empty] | 0.14189 |  | 12770270.2703 | 0
| Gas heating scheme | [7 empty] | 0.99324 |  | 89391891.8919 | 0
| Gas heating scheme - list of materials | [7 empty] | 0.94595 |  | 85135135.1351 | 0
| Reversal gas rack | [7 empty] | 0.94595 |  | 85135135.1351 | 0
| Connections of natural gas and lance cooling air | [7 empty] | 0.94595 |  | 85135135.1351 | 0
| Lance Cooling air pipe | [7 empty] | 0.28378 |  | 25540540.5405 | 0
| Lance cooling air pipe | [7 empty] | 0.094595 |  | 8513513.5135 | 0
| Ring pipe - lance cooling air - Assembly | [7 empty] | 0.094595 |  | 8513513.5135 | 0
| Ring pipe - lance cooling air - Details | [7 empty] | 0.094595 |  | 8513513.5135 | 0
| Lance Cooling air pipe | [7 empty] | 0.28378 |  | 25540540.5405 | 0
| Preheating piping | [7 empty] | 0.14189 |  | 12770270.2703 | 0
| Preheating piping - Details | [7 empty] | 0.14189 |  | 12770270.2703 | 0
| Compressed air | [7 empty] | 1.8919 |  | 170270270.2703 | 0
| Compressed air scheme | [7 empty] | 0.47297 |  | 42567567.5676 | 0
| Compressed air scheme - Air cannon | [7 empty] | 0.47297 |  | 42567567.5676 | 0
| Compressed air scheme - list of materials | [7 empty] | 0.47297 |  | 42567567.5676 | 0
| Installation of compressed air pipes | [7 empty] | 0.47297 |  | 42567567.5676 | 0
| Ducting | [7 empty] | 9 | 0% | 810000000 | 0
| Process Air Ducting | [7 empty] | 7.4348 |  | 669130434.7826 | 0
| Preheating valve ø711 | [7 empty] | 0.26609 |  | 23947826.087 | 0
| Compensator ø711 | [7 empty] | 0.26609 |  | 23947826.087 | 0
| Compensator ø914 | [7 empty] | 0.26609 |  | 23947826.087 | 0
| Compensator ø1220 | [7 empty] | 0.26609 |  | 23947826.087 | 0
| Relief valve ø660 - Assembly | [7 empty] | 0.26609 |  | 23947826.087 | 0
| Relief valve ø660 - Machined parts | [7 empty] | 0.26609 |  | 23947826.087 | 0
| Relief valve ø660 - Sheet parts I | [7 empty] | 0.26609 |  | 23947826.087 | 0
| Relief valve ø660 - Sheet parts II | [7 empty] | 0.26609 |  | 23947826.087 | 0
| Relief valve ø660 - Protective grating | [7 empty] | 0.26609 |  | 23947826.087 | 0
| Relief valve ø864 - Assembly | [7 empty] | 0.26609 |  | 23947826.087 | 0
| Relief valve ø865 - Machined parts | [7 empty] | 0.26609 |  | 23947826.087 | 0
| Relief valve ø866 -Sheet parts I | [7 empty] | 0.26609 |  | 23947826.087 | 0
| Relief valve ø867 - Sheet parts II | [7 empty] | 0.26609 |  | 23947826.087 | 0
| Relief valve ø868 - Protective grating | [7 empty] | 0.26609 |  | 23947826.087 | 0
| Silencer for relief valve FI660 | [7 empty] | 0.26609 |  | 23947826.087 | 0
| Silencer for relief valve FI660 | [7 empty] | 0.26609 |  | 23947826.087 | 0
| Rain protection - for relief valve ø864 | [7 empty] | 0.26609 |  | 23947826.087 | 0
| Rain protection - for relief valve ø864 | [7 empty] | 0.26609 |  | 23947826.087 | 0
| Suction silencer in aspirating channel | [7 empty] | 0.26609 |  | 23947826.087 | 0
| Sound absorbing door | [7 empty] | 0.26609 |  | 23947826.087 | 0
| Filter for air intake | [7 empty] | 0.26609 |  | 23947826.087 | 0
| Combustion air duct I | [7 empty] | 0.26609 |  | 23947826.087 | 0
| Combustion air duct I | [7 empty] | 0.26609 |  | 23947826.087 | 0
| Cooling air duct - Assembly | [7 empty] | 0.26609 |  | 23947826.087 | 0
| Cooling air duct - Details | [7 empty] | 0.26609 |  | 23947826.087 | 0
| Combustion air duct II | [7 empty] | 0.26609 |  | 23947826.087 | 0
| Combustion air duct II | [7 empty] | 0.25826 |  | 23243478.2609 | 0
| Collecting duct for combustion air TYPICAL AK454/398.0 | [7 empty] | 0.25826 |  | 23243478.2609 | 0
| Waste Cooling Air Ducting | [7 empty] | 1.5652 |  | 140869565.2174 | 0
| Stack | [7 empty] | 0.78261 |  | 70434782.6087 | 0
| Waste gas duct - lower part | [7 empty] | 0.78261 |  | 70434782.6087 | 0
| Hydraulic | [7 empty] | 5 | 0% | 450000000 | 0
| Hydraulic Details | [7 empty] | 5 |  | 450000000 | 0
| Hydraulic scheme | [7 empty] | 0.71429 |  | 64285714.2857 | 0
| Installation dimensions of hydraulic cylinders | [7 empty] | 0.71429 |  | 64285714.2857 | 0
| Hydraulic scheme - list of materials | [7 empty] | 0.71429 |  | 64285714.2857 | 0
| Installation of hydraulic equipment | [7 empty] | 0.71429 |  | 64285714.2857 | 0
| Installation of hydraulic equipment, details | [7 empty] | 0.71429 |  | 64285714.2857 | 0
| Hydraulic power unit | [7 empty] | 0.71429 |  | 64285714.2857 | 0
| Valve racks AKL521/505.0 - 505.5 | [7 empty] | 0.71429 |  | 64285714.2857 | 0
| Refractory | [7 empty] | 1.218 | 0% | 109622411.6931 | 0
| Refractory | [7 empty] | 1.218 |  | 109622411.6931 | 0
| Brick lining drawing | [7 empty] | 0.24361 |  | 21924482.3386 | 0
| Brick lining drawing | [7 empty] | 0.24361 |  | 21924482.3386 | 0
| Tolerances and instructions | [7 empty] | 0.24361 |  | 21924482.3386 | 0
| Brick shapes | [7 empty] | 0.24361 |  | 21924482.3386 | 0
| Brick list | [7 empty] | 0.24361 |  | 21924482.3386 | 0
| Civil and Structure | [7 empty] | 5.7247 |  | 515225334.9574 | 0
| Steel Structure | [7 empty] | 5.7247 |  | 515225334.9574 | 0
| Skip bridge Steel Structure | [7 empty] | 0.85262 |  | 76735688.1851 | 0
| Skip bridge Gallery | [7 empty] | 0 |  | 0 | 0
| Skip bridge Connection Details | [7 empty] | 0 |  | 0 | 0
| Calc. Sheet for Steel Structure | [7 empty] | 0 |  | 0 | 0
| Kiln Structure | [7 empty] | 0.85262 |  | 76735688.1851 | 0
| Steel Structure for Platforms | [7 empty] | 0 |  | 0 | 0
| Steel Structure for Stairs | [7 empty] | 0 |  | 0 | 0
| Calc. Sheet for Steel Structure | [7 empty] | 0 |  | 0 | 0
| Steel Structures for Covering | [7 empty] | 3.0451 |  | 274056029.2326 | 0
| St. St. Assembly | [7 empty] | 0 |  | 0 | 0
| Connection Details | [7 empty] | 0 |  | 0 | 0
| Calc. Sheet for Steel Structure | [7 empty] | 0 |  | 0 | 0
| Cladding Details | [7 empty] | 0 |  | 0 | 0
| Discharge Hopper Support | [7 empty] | 0.48721 |  | 43848964.6772 | 0
| St. St. Assembly for Discharge Hopper Support | [7 empty] | 0 |  | 0 | 0
| Discharge Hopper Support Connection Details | [7 empty] | 0 |  | 0 | 0
| Supporting Frame | [7 empty] | 0.48721 |  | 43848964.6772 | 0
| Supporting structure for reversal trap | [7 empty] | 0 |  | 0 | 0
| Outer supporting frame - Details I | [7 empty] | 0 |  | 0 | 0
| Outer supporting frame - Details II | [7 empty] | 0 |  | 0 | 0
| Electrical and Automation | [7 empty] | 28.0146 |  | 2521315468.9403 | 0
| Electrical | [7 empty] | 16.4434 |  | 1479902557.8563 | 0
| MCC kiln (fix speed motors) SLD & Typical Wiring Diagram | [7 empty] | 3.6541 |  | 328867235.0792 | 0
| MCC kiln (VFD motors) SLD & Typical Wiring Diagram | [7 empty] | 3.0451 |  | 274056029.2326 | 0
| Typical Electrical Connection Diagram | [7 empty] | 3.6541 |  | 328867235.0792 | 0
| Local Control Panel | [7 empty] | 1.218 |  | 109622411.6931 | 0
| Cable Routing (power & Control & Instrument) | [7 empty] | 1.218 |  | 109622411.6931 | 0
| Cable List & Schedule (power & Control & Instrument) | [7 empty] | 1.218 |  | 109622411.6931 | 0
| Electrical Equipment Location | [7 empty] | 0.60901 |  | 54811205.8465 | 0
| Lighting system kiln | [7 empty] | 0.60901 |  | 54811205.8465 | 0
| Electrical Room Equipment Location | [7 empty] | 0.60901 |  | 54811205.8465 | 0
| Earthing system kiln | [7 empty] | 0.60901 |  | 54811205.8465 | 0
| Automation & Instrumentation | [7 empty] | 11.5713 |  | 1041412911.084 | 0
| Inquiry Document For Control System and HMI | [7 empty] | 1.218 |  | 109622411.6931 | 0
| Typical Wiring Diagram PLC & RIO | [7 empty] | 3.6541 |  | 328867235.0792 | 0
| I/O list kiln | [7 empty] | 1.827 |  | 164433617.5396 | 0
| Control/Monitoring Software | [7 empty] | 1.218 |  | 109622411.6931 | 0
| Instrumentation Equipment Location | [7 empty] | 1.218 |  | 109622411.6931 | 0
| Automation Earthing system | [7 empty] | 1.218 |  | 109622411.6931 | 0
| Instrument list kiln | [7 empty] | 1.218 |  | 109622411.6931 | 0
| Mechanical, Piping and Utility | [5 empty] | 12.99% |  | 60.7231 | 15.67%
| Civil & Structure | [5 empty] | 6% |  | 6.3901 | 7.289%
| Electrical & Automation | [5 empty] | 0% |  | 32.8867 | 0%

## TOTAL (hidden)
پروژه مهندسی طراحی پایه و تفصیلی کوره آهک 350 تن در روز شماره قرارداد: 10164/98 صورت وضعیت شماره یک
مبلغ کل قرارداد: 9،000،000،000 ریال
| شرح | به عدد (ریال) | به حروف (ریال)
| ناخالص صورت وضعیت تجمعی دوره قبل | 0 | -
| ناخالص صورت وضعیت تجمعی تاکنون | 810667600.4872 | هشتصد و ده میلیون و ششصد و شصت و هفت هزار و ششصد
| ناخالص صورت وضعیت این دوره | 810667600.4872 | هشتصد و ده میلیون و ششصد و شصت و هفت هزار و ششصد
| امضاء کارفرما |  |  | امضاء طراح
کارفرما: شرکت ساروج لیان خلیج فارس
طراح: شرکت فراتحقيق سپاهان
تـاریخ : 1398/08/22
شماره: S98/982023/0001

## COMULATIVE (hidden)
پروژه مهندسی طراحی پایه و تفصیلی کوره آهک 350 تن در روز شماره قرارداد: 10164/98 صورت وضعیت شماره یک
مبلغ کل قرارداد: 9،000،000،000 ریال
ردیف | شرح | از تاریخ | تا تاریخ | ناخالص صورت وضعیت تجمعی دوره قبل |  | ناخالص صورت وضعیت تجمعی تاکنون |  | ناخالص صورت وضعیت این دوره
1 | صورت وضعیت شماره یک | 1398/06/01 | 1398/08/20 | 0 | ریال | 810667600.4872 | ریال | 810667600.4872 | ریال
| امضاء کارفرما | [6 empty] | امضاء طراح
تـاریخ : 1398/08/22
شماره: S98/982023/0001

## Budget (hidden)
| Man- Hour | Budget
Engineering | 8210 | 2709300000 | 33.87%
3D Modeling | 1000 | 330000000 | 4.125%
Management & Control | 750 | 247500000 | 3.094%
Project Overhead |  | 400000000 | 5%
|  | 3686800000 | 46.09%

## Extra & Re- Work (hidden)
| دلیل انجام | نتیجه | نفر ساعت
بررسی نقشه هاي فونداسیون کوره آهک |  | 12980